## est_to_complete
Activity ID | Spreadsheet Field | 2021-09-25 | 2021-10-02 | 2021-10-09 | 2021-10-16 | 2021-10-23 | 2021-10-30 | 2021-11-06 | 2021-11-13 | 2021-11-20 | 2021-11-27 | 2021-12-04 | 2021-12-11 | 2021-12-18 | 2021-12-25 | 2022-01-01 | 2022-01-08 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-05 | 2022-02-12 | 2022-02-19 | 2022-02-26
2252-1.T2.PI.1095 | Estimate To Complete Labor Units | 2021-11-27: 151.52; 2021-12-04: 160.88; 2021-12-11: 160.88; 2022-01-01: 111.74
2252-1T2.PI.CS-AIN.1000 | Estimate To Complete Labor Units | 2021-10-30: 40.89; 2021-11-06: 11.53
2252-1T2.PI.CS-AIN.1032 | Estimate To Complete Labor Units | 2021-11-13: 269.39; 2021-11-20: 439.53
2252-1T2.PI.CS-AIN.1055 | Estimate To Complete Labor Units | 2021-09-25: 132.53
2252-1T2.PI.CS-AIN.1056 | Estimate To Complete Labor Units | 2021-10-23: 181.4; 2021-10-30: 295.98
2252-1T2.PI.CS-AIN.1061 | Estimate To Complete Labor Units | 2022-01-22: 61.69; 2022-01-29: 245.87; 2022-02-05: 245.87; 2022-02-12: 245.87; 2022-02-19: 94.77
2252-1T2.PI.CS-GCD.1003 | Estimate To Complete Labor Units | 2021-11-20: 51.09; 2021-11-27: 113.31; 2021-12-04: 35.43
2252-1T2.PI.CS-GCD.1045 | Estimate To Complete Labor Units | 2021-10-30: 28.47
2252-1T2.PI.CS-GSL.1006 | Estimate To Complete Labor Units | 2021-12-04: 104.46; 2021-12-11: 47.53
2252-1T2.PI.CS-GSL.1027 | Estimate To Complete Labor Units | 2021-12-11: 91.36
2252-1T2.PI.CS-GVE.1028 | Estimate To Complete Labor Units | 2021-10-30: 5.98
2252-1T2.PI.CS-GVE.1041 | Estimate To Complete Labor Units | 2021-10-02: 5.47; 2021-10-09: 22.56
2252-1T2.PI.CS-GVE.1042 | Estimate To Complete Labor Units | 2021-10-30: 57.05
2252-1T2.PI.CS-LPB.1022 | Estimate To Complete Labor Units
2252-1T2.PI.CS-LPB.1029 | Estimate To Complete Labor Units | 2021-10-30: 37.84; 2021-11-06: 116.93; 2021-11-13: 57.83
2252-1T2.PI.CS-LPB.1046 | Estimate To Complete Labor Units | 2021-11-06: 7.48; 2021-11-13: 5.88
2252-1T2.PI.CS-LPB.1047 | Estimate To Complete Labor Units | 2021-11-13: 109.5; 2021-11-20: 205.62
2252-1T2.PI.CS-LPN.1047 | Estimate To Complete Labor Units | 2021-11-13: 247.29; 2021-11-20: 43.09
2252-1T2.PI.CS-LSH.1048 | Estimate To Complete Labor Units | 2021-11-20: 68.71
2252-1T2.PI.CS-LSH.1049 | Estimate To Complete Labor Units | 2021-12-04: 57.01; 2021-12-11: 16.46
2252-1T2.PI.CS-SPB.1042 | Estimate To Complete Labor Units | 2021-10-09: 141.15; 2021-10-16: 44.58
2252-1T2.PI.CS-SPB.1043 | Estimate To Complete Labor Units | 2021-12-04: 36.02; 2021-12-11: 30.68
2252-1T2.PI.CS-WFI.1057 | Estimate To Complete Labor Units | 2021-09-25: 44.63; 2021-10-02: 111.11
2252-1T2.PI.CS-WFI.1058 | Estimate To Complete Labor Units | 2021-10-02: 164.58
2252-1T2.PI.FRP-LPA.1012 | Estimate To Complete Labor Units | 2021-11-13: 104.86; 2021-11-20: 64.27
2252-1T2.PI.FRP-LPA.1024 | Estimate To Complete Labor Units | 2022-02-19: 41.36; 2022-02-26: 19.82
2252-1T2.PI.HDPE-WCW.1015 | Estimate To Complete Labor Units | 2021-11-06: 190.86; 2021-11-13: 193.42
2252-1T2.PI.HDPE-WFI.1016 | Estimate To Complete Labor Units | 2022-01-29: 11.61
2252-1T2.PI.HDPE-WPO.1058 | Estimate To Complete Labor Units | 2021-09-25: 775.74
2252-1T2.PI.HDPE-WRO.1059 | Estimate To Complete Labor Units | 2021-10-02: 14.66
2252-1T2.PI.HDPE-WRO.1060 | Estimate To Complete Labor Units | 2021-11-13: 19.15; 2021-11-20: 11.74
2252-1T2.PI.SS-GVE.1018 | Estimate To Complete Labor Units | 2021-12-11: 39.73
2252-1T2.PI.SS-GVE.1030 | Estimate To Complete Labor Units | 2021-10-30: 11.99; 2021-11-06: 37.03; 2021-11-13: 11.58
2252-1T2.PI.SS-GVE.1036 | Estimate To Complete Labor Units | 2022-01-01: 31.81; 2022-01-08: 48.52
2252-1T2.PI.SS-GVE.1044 | Estimate To Complete Labor Units | 2021-10-16: 33.87
2252-1T2.PI.SS-LPB.1019 | Estimate To Complete Labor Units | 2021-11-27: 126.23; 2021-12-04: 129.04; 2021-12-11: 129.04; 2022-01-01: 117.31; 2022-01-08: 14.55
2252-1T2.PI.SS-LPB.1025 | Estimate To Complete Labor Units
2252-1T2.PI.SS-LPB.1051 | Estimate To Complete Labor Units | 2021-12-11: 18.71; 2022-01-01: 14.11
2252-1T2.PI.SS-SPB.1031 | Estimate To Complete Labor Units | 2021-10-30: 207.11; 2021-11-06: 238.3; 2021-11-13: 74.52
2252-1T2.PI.SS-SPB.1034 | Estimate To Complete Labor Units | 2021-10-16: 55.18; 2021-10-23: 389.1; 2021-10-30: 50.94
2252-1T2.PI.SS-SPB.1037 | Estimate To Complete Labor Units | 2021-10-30: 162.44; 2021-11-06: 186.91; 2021-11-13: 186.91; 2021-11-20: 186.91; 2021-11-27: 186.91; 2021-12-04: 129.82
2252-1T2.PI.SS-SPB.1039 | Estimate To Complete Labor Units | 2021-11-20: 41.63; 2021-11-27: 128.63; 2021-12-04: 128.63; 2021-12-11: 128.63; 2022-01-01: 70.63
2252-1T2.PI.SS-SPB.1052 | Estimate To Complete Labor Units | 2021-10-16: 96.33
2252-1T2.PI.SS-WCW.1020 | Estimate To Complete Labor Units | 2021-11-27: 6.89
2252-1T2.PI.SS-WPO.1060 | Estimate To Complete Labor Units | 2022-01-22: 71.78; 2022-01-29: 286.08; 2022-02-05: 286.08; 2022-02-12: 214.3
2252-1T2.PI.SS-WRO.1053 | Estimate To Complete Labor Units | 2021-10-23: 14.75; 2021-10-30: 104.01; 2021-11-06: 104.01; 2021-11-13: 60.89
2252-1T2.PI.SS-WRO.1059 | Estimate To Complete Labor Units | 2021-12-11: 100.33; 2022-01-01: 220.02; 2022-01-08: 242.02; 2022-01-15: 242.02; 2022-01-22: 181.3
2252-1T2.PI.SS-WRO.1060 | Estimate To Complete Labor Units | 2022-01-15: 3.63; 2022-01-22: 71.32; 2022-01-29: 15.82
2252-1T2.PI.SS-WSC.1021 | Estimate To Complete Labor Units | 2021-10-02: 14.04; 2021-10-09: 160.86; 2021-10-16: 160.86; 2021-10-23: 160.86; 2021-10-30: 160.86; 2021-11-06: 73.7
2252-1T2.PI.SS-WSC.1026 | Estimate To Complete Labor Units | 2021-11-13: 6.18
2252-1T2.PI.SS-WSC.1038 | Estimate To Complete Labor Units | 2021-12-04: 33.81; 2021-12-11: 110.68; 2022-01-01: 76.87
2252-1T2.PI.SS-WSC.1040 | Estimate To Complete Labor Units | 2022-01-01: 104.69; 2022-01-08: 159.69
2252-1T2.PI.SS-WSC.1054 | Estimate To Complete Labor Units | 2021-11-27: 152.25; 2021-12-04: 45.84
2252-2T2.PI.CS-AIN.1055 | Estimate To Complete Labor Units | 2021-11-20: 67.9; 2021-11-27: 4.33
2252-2T2.PI.CS-AIN.1075 | Estimate To Complete Labor Units | 2021-09-25: 107.96; 2021-10-02: 273.73
2252-2T2.PI.CS-AIN.1083 | Estimate To Complete Labor Units | 2021-12-04: 122.54; 2021-12-11: 99.46
2252-2T2.PI.CS-SPB.1047 | Estimate To Complete Labor Units | 2021-09-25: 19.81
2252-2T2.PI.CS-SPB.1061 | Estimate To Complete Labor Units
2252-2T2.PI.CS-SPB.1069 | Estimate To Complete Labor Units
2252-2T2.PI.CS-WFI.1077 | Estimate To Complete Labor Units | 2021-11-27: 168.11
2252-2T2.PI.CS-WFI.1081 | Estimate To Complete Labor Units | 2021-11-27: 25.61; 2021-12-04: 36.64
2252-2T2.PI.HDPE-WRO.10 | Estimate To Complete Labor Units | 2021-11-27: 175.51
2252-2T2.PI.SS-LPB.1049 | Estimate To Complete Labor Units
2252-2T2.PI.SS-LPB.1051 | Estimate To Complete Labor Units | 2021-11-27: 78.52; 2021-12-04: 80.27; 2021-12-11: 80.27; 2022-01-01: 26.56
2252-2T2.PI.SS-LPB.1057 | Estimate To Complete Labor Units | 2021-10-30: 3.43; 2021-11-06: 104.78; 2021-11-13: 104.78; 2021-11-20: 104.78; 2021-11-27: 2.29
2252-2T2.PI.SS-LPB.1063 | Estimate To Complete Labor Units | 2021-09-25: 8.94
2252-2T2.PI.SS-LPB.1067 | Estimate To Complete Labor Units
2252-2T2.PI.SS-LPB.1071 | Estimate To Complete Labor Units | 2021-09-25: 48.24; 2021-10-02: 48.24; 2021-10-09: 48.24; 2021-10-16: 6.58
2252-2T2.PI.SS-WPO.1085 | Estimate To Complete Labor Units | 2021-12-04: 135.67; 2021-12-11: 135.67; 2022-01-01: 123.33; 2022-01-08: 72.77
2252-2T2.PI.SS-WRO.1079 | Estimate To Complete Labor Units | 2022-01-08: 118.42; 2022-01-15: 187.16; 2022-01-22: 187.16; 2022-01-29: 7.49
2252-2T2.PI.SS-WSC.1053 | Estimate To Complete Labor Units | 2021-10-30: 161.18
2252-2T2.PI.SS-WSC.1059 | Estimate To Complete Labor Units | 2021-10-30: 9.16; 2021-11-06: 67.14
2252-2T2.PI.SS-WSC.1065 | Estimate To Complete Labor Units | 2021-09-25: 32.93
2252-2T2.PI.SS-WSC.1073 | Estimate To Complete Labor Units | 2021-10-02: 16.41; 2021-10-09: 187.98; 2021-10-16: 137.4
2252-3 T2.Flush. 9176 | Estimate To Complete Labor Units | 2021-10-30: 127.56; 2021-11-06: 350.78; 2021-11-13: 350.78; 2021-11-20: 31.89
2252-3 T2.Flush. 9178 | Estimate To Complete Labor Units | 2022-02-12: 135.3; 2022-02-19: 418.2
2252-3 T2.Flush. 9180 | Estimate To Complete Labor Units | 2022-01-08: 199.5
2252-3 T2.HYDRO. 9168 | Estimate To Complete Labor Units | 2021-10-09: 14.35; 2021-10-16: 157.85; 2021-10-23: 157.85; 2021-10-30: 100.45
2252-3 T2.HYDRO. 9170 | Estimate To Complete Labor Units | 2022-02-05: 96.21; 2022-02-12: 135.52
2252-3 T2.HYDRO. 9172 | Estimate To Complete Labor Units | 2022-01-15: 15.17; 2022-01-22: 85.12; 2022-01-29: 69.95
2252-3 T2.Insul. 9182 | Estimate To Complete Labor Units | 2022-01-29: 797.51; 2022-02-05: 979.08; 2022-02-12: 3.56
2252-3 T2.Insul. 9184 | Estimate To Complete Labor Units | 2021-11-20: 87.39; 2021-11-27: 52.44
2252-3 T2.Insul. 9186 | Estimate To Complete Labor Units | 2022-02-05: 44.05; 2022-02-12: 136.1; 2022-02-19: 116.8
2252-3 T2.Insul. 9188 | Estimate To Complete Labor Units | 2022-01-08: 3.44; 2022-01-15: 105.04; 2022-01-22: 105.04; 2022-01-29: 105.04; 2022-02-05: 105.04; 2022-02-12: 105.04; 2022-02-19: 105.04; 2022-02-26: 42.4
2252-3 T2.Insul. 9190 | Estimate To Complete Labor Units | 2022-02-05: 88.04; 2022-02-12: 128.1; 2022-02-19: 86.64
2252-3 T2.PI.CS-AIN. 9160 | Estimate To Complete Labor Units | 2021-10-30: 109.11
2252-3 T2.PI.CS-AIN. 9688 | Estimate To Complete Labor Units | 2021-10-30: 3.44; 2021-11-06: 23.05
2252-3 T2.PI.CS-GSL. 9153 | Estimate To Complete Labor Units | 2021-12-11: 14.9; 2022-01-01: 26.81; 2022-01-08: 2.79
2252-3 T2.PI.CS-GSL. 9164 | Estimate To Complete Labor Units | 2021-12-11: 118.38
2252-3 T2.PI.CS-LPB. 9372 | Estimate To Complete Labor Units | 2021-12-11: 211.78
2252-3 T2.PI.CS-LPB. 9374 | Estimate To Complete Labor Units | 2022-01-01: 97.43; 2022-01-08: 24.87
2252-3 T2.PI.CS-WFI. 9692 | Estimate To Complete Labor Units | 2021-11-13: 11.25; 2021-11-20: 11.56
2252-3 T2.PI.HDPE-WRO. 94 | Estimate To Complete Labor Units | 2021-10-02: 195.49; 2021-10-09: 85.79
2252-3 T2.PI.PS .9161 | Estimate To Complete Labor Units | 2021-10-16: 0.53; 2021-10-23: 2.91; 2021-10-30: 2.91; 2021-11-06: 2.91; 2021-11-13: 0.26
2252-3 T2.PI.PS .9163 | Estimate To Complete Labor Units | 2021-10-16: 1.97; 2021-10-23: 10.86; 2021-10-30: 6.91
2252-3 T2.PI.PS .9165 | Estimate To Complete Labor Units | 2021-10-16: 0.73; 2021-10-23: 4.03; 2021-10-30: 4.03; 2021-11-06: 4.03; 2021-11-13: 4.03; 2021-11-20: 4.03; 2021-11-27: 1.1
2252-3 T2.PI.PS .9167 | Estimate To Complete Labor Units | 2021-10-16: 0.99; 2021-10-23: 5.43; 2021-10-30: 5.43; 2021-11-06: 5.43; 2021-11-13: 5.43; 2021-11-20: 5.43; 2021-11-27: 5.43; 2021-12-04: 3.95
2252-3 T2.PI.PS .9169 | Estimate To Complete Labor Units | 2021-10-16: 4.7; 2021-10-23: 23.51
2252-3 T2.PI.PS .9171 | Estimate To Complete Labor Units | 2021-10-16: 0.95; 2021-10-23: 4.77
2252-3 T2.PI.PS .9173 | Estimate To Complete Labor Units | 2021-10-16: 1.97; 2021-10-23: 9.86
2252-3 T2.PI.PS .9175 | Estimate To Complete Labor Units | 2021-10-16: 5.74; 2021-10-23: 11.48
2252-3 T2.PI.SS-GSL. 9162 | Estimate To Complete Labor Units | 2022-01-08: 174.32; 2022-01-15: 163.73
2252-3 T2.PI.SS-GSL. 9164 | Estimate To Complete Labor Units | 2022-01-15: 13.55; 2022-01-22: 50.36; 2022-01-29: 50.36; 2022-02-05: 50.36; 2022-02-12: 18.5
2252-3 T2.PI.SS-GSL. 9366 | Estimate To Complete Labor Units | 2022-01-15: 24.52
2252-3 T2.PI.SS-GVE. 9154 | Estimate To Complete Labor Units | 2021-11-20: 66.17
2252-3 T2.PI.SS-GVE. 9164 | Estimate To Complete Labor Units | 2022-01-15: 36.91; 2022-01-22: 112.73
2252-3 T2.PI.SS-GVE. 9165 | Estimate To Complete Labor Units | 2021-11-27: 134.25; 2021-12-04: 43.73
2252-3 T2.PI.SS-GVE. 9166 | Estimate To Complete Labor Units | 2021-11-20: 58.2
2252-3 T2.PI.SS-GVE. 9368 | Estimate To Complete Labor Units | 2022-01-22: 19.6; 2022-01-29: 20.39
2252-3 T2.PI.SS-LPB. 9167 | Estimate To Complete Labor Units | 2022-01-08: 60.04; 2022-01-15: 118.81
2252-3 T2.PI.SS-LPB. 9170 | Estimate To Complete Labor Units | 2022-01-08: 160.89
2252-3 T2.PI.SS-LPB. 9270 | Estimate To Complete Labor Units | 2022-01-15: 16.27; 2022-01-22: 50.27; 2022-01-29: 50.27; 2022-02-05: 20.29
2252-3 T2.PI.SS-LPB. 9271 | Estimate To Complete Labor Units | 2022-02-05: 30.28
2252-3 T2.PI.SS-SPB. 9157 | Estimate To Complete Labor Units | 2021-09-25: 42.12; 2021-10-02: 66.18; 2021-10-09: 60.17
2252-3 T2.PI.SS-WCW. 9158 | Estimate To Complete Labor Units | 2021-11-13: 88.77; 2021-11-20: 54.4
2252-3 T2.PI.SS-WCW. 9172 | Estimate To Complete Labor Units | 2022-01-08: 52.52
2252-3 T2.PI.SS-WCW. 9174 | Estimate To Complete Labor Units | 2022-01-01: 257.46; 2022-01-08: 174.52
2252-3 T2.PI.SS-WCW. 9374 | Estimate To Complete Labor Units | 2022-01-08: 98.01; 2022-01-15: 100.65
2252-3 T2.PI.SS-WGS. 9159 | Estimate To Complete Labor Units | 2021-09-25: 72.82; 2021-10-02: 160.2; 2021-10-09: 160.2; 2021-10-16: 131.07
2252-3 T2.PI.SS-WPO. 9694 | Estimate To Complete Labor Units | 2021-09-25: 48.1; 2021-10-02: 121.1
2252-3 T2.PI.SS-WPR. 9176 | Estimate To Complete Labor Units | 2022-01-08: 24.01
2252-3 T2.PI.SS-WRO. 9160 | Estimate To Complete Labor Units | 2021-10-09: 43.46
2252-3 T2.PI.SS-WRO. 9690 | Estimate To Complete Labor Units | 2021-10-09: 188.14; 2021-10-16: 31.65
2252-3 T2.PI.SS-WRO. 9691 | Estimate To Complete Labor Units | 2021-10-09: 50.5; 2021-10-16: 38.09
2252-3 T2.PI.SS-WSC. 9162 | Estimate To Complete Labor Units | 2021-11-06: 8.02; 2021-11-13: 157.5; 2021-11-20: 14.89
2252-3 T2.PI.SS-WSC. 9178 | Estimate To Complete Labor Units | 2021-11-20: 235.24; 2021-11-27: 10.39
2252-3 T2.PI.SS-WSC. 9180 | Estimate To Complete Labor Units | 2021-11-27: 99.86; 2021-12-04: 51.44
2252-3 T2.PI.SS-WSC. 9276 | Estimate To Complete Labor Units | 2021-12-04: 86.46; 2021-12-11: 100.15
2252-3 T2.PI.SS-WSC. 9368 | Estimate To Complete Labor Units | 2022-01-01: 123.65; 2022-01-08: 93.28
2252-3 T2.PI.SS-WSC. 9370 | Estimate To Complete Labor Units | 2022-01-01: 17.35
2252-3 T2.PI.SS-WSC. 9376 | Estimate To Complete Labor Units | 2021-12-11: 175.64
2252-3 T2.PI.SS-WSC. 9378 | Estimate To Complete Labor Units | 2021-12-11: 3.2; 2022-01-01: 2.96
2252-4T2.PI.CS-AIN.1100 | Estimate To Complete Labor Units | 2021-12-11: 174.22; 2022-01-01: 15.15
2252-4T2.PI.CS-LPB.1081 | Estimate To Complete Labor Units
2252-4T2.PI.CS-LPB.1085 | Estimate To Complete Labor Units | 2022-01-01: 9.37; 2022-01-08: 12.64
2252-4T2.PI.CS-LPB.1087 | Estimate To Complete Labor Units
2252-4T2.PI.HDPE-WRO.89 | Estimate To Complete Labor Units | 2021-10-02: 37.67
2252-4T2.PI.HDPE-WRO.96 | Estimate To Complete Labor Units | 2021-12-04: 53.38; 2021-12-11: 3.41
2252-4T2.PI.SS-LPB.1075 | Estimate To Complete Labor Units | 2021-09-25: 242.34
2252-4T2.PI.SS-LPB.1092 | Estimate To Complete Labor Units | 2021-10-02: 112.04; 2021-10-09: 214.33; 2021-10-16: 141.26
2252-4T2.PI.SS-SPB.1077 | Estimate To Complete Labor Units | 2021-09-25: 134.7
2252-4T2.PI.SS-WPO.1102 | Estimate To Complete Labor Units | 2021-12-11: 67.78; 2022-01-01: 79.56
2252-4T2.PI.SS-WRO.1098 | Estimate To Complete Labor Units | 2021-12-11: 218.88
2252-4T2.PI.SS-WSC.1079 | Estimate To Complete Labor Units | 2021-09-25: 29.21; 2021-10-02: 61.25
2252-4T2.PI.SS-WSC.1083 | Estimate To Complete Labor Units | 2021-09-25: 6.92
2252-4T2.PI.SS-WSC.1094 | Estimate To Complete Labor Units | 2021-11-27: 64.44; 2021-12-04: 256.84; 2021-12-11: 256.84; 2022-01-01: 94.33
2252-5T2.PI.CS-AIN.1094 | Estimate To Complete Labor Units | 2021-10-30: 13.23; 2021-11-06: 97
2252-5T2.PI.SS-WPO.1098 | Estimate To Complete Labor Units | 2021-11-06: 124.72
2252-5T2.PI.SS-WRO.1096 | Estimate To Complete Labor Units | 2021-11-06: 118.28
2262-1T2.PI.9277 | Estimate To Complete Labor Units | 2021-10-30: 67.99; 2021-11-06: 81.29; 2021-11-13: 81.29; 2021-11-20: 65.03
2262-1T2.PI.CS-AIN.9203 | Estimate To Complete Labor Units | 2021-09-25: 260.21; 2021-10-02: 260.21; 2021-10-09: 47.31
2262-1T2.PI.CS-AIN.9207 | Estimate To Complete Labor Units | 2021-12-11: 98.99
2262-1T2.PI.CS-AIN.9279 | Estimate To Complete Labor Units | 2021-10-02: 126.89; 2021-10-09: 256.59; 2021-10-16: 256.59; 2021-10-23: 129.69
2262-1T2.PI.CS-AIN.9315 | Estimate To Complete Labor Units | 2021-11-27: 35.99; 2021-12-04: 174.38; 2021-12-11: 59.13
2262-1T2.PI.CS-LPB.9235 | Estimate To Complete Labor Units | 2021-10-30: 30.46
2262-1T2.PI.CS-WFI.9283 | Estimate To Complete Labor Units | 2021-10-09: 430.04
2262-1T2.PI.CS-WFI.9299 | Estimate To Complete Labor Units | 2021-10-09: 94.89
2262-1T2.PI.HDPE-WCW.9239 | Estimate To Complete Labor Units | 2021-11-06: 145.87
2262-1T2.PI.HDPE-WCW.9259 | Estimate To Complete Labor Units | 2021-11-13: 15.28
2262-1T2.PI.HDPE-WRO.9291 | Estimate To Complete Labor Units | 2021-10-23: 17.06; 2021-10-30: 17.44
2262-1T2.PI.SS-GVE.9195 | Estimate To Complete Labor Units | 2021-10-30: 15.44; 2021-11-06: 9.3
2262-1T2.PI.SS-GVE.9215 | Estimate To Complete Labor Units | 2021-10-16: 76.09
2262-1T2.PI.SS-GVE.9243 | Estimate To Complete Labor Units | 2021-09-25: 42.43
2262-1T2.PI.SS-LPB.9199 | Estimate To Complete Labor Units | 2021-11-13: 14.89
2262-1T2.PI.SS-LPB.9251 | Estimate To Complete Labor Units
2262-1T2.PI.SS-LPB.9267 | Estimate To Complete Labor Units | 2021-11-06: 0.4; 2021-11-13: 25.86
2262-1T2.PI.SS-SPB.9207 | Estimate To Complete Labor Units | 2021-12-11: 19.51
2262-1T2.PI.SS-SPB.9219 | Estimate To Complete Labor Units | 2021-10-16: 211.7; 2021-10-23: 323.42; 2021-10-30: 52.92
2262-1T2.PI.SS-SPB.9227 | Estimate To Complete Labor Units | 2021-11-20: 170.04
2262-1T2.PI.SS-SPB.9271 | Estimate To Complete Labor Units | 2021-11-13: 7.94; 2021-11-20: 6.67
2262-1T2.PI.SS-WPO.9303 | Estimate To Complete Labor Units | 2021-09-25: 116.45; 2021-10-02: 71.01
2262-1T2.PI.SS-WRO.9295 | Estimate To Complete Labor Units
2262-1T2.PI.SS-WRO.9311 | Estimate To Complete Labor Units | 2021-11-06: 0.09; 2021-11-13: 5.88
2262-1T2.PI.SS-WRO.9312 | Estimate To Complete Labor Units | 2021-11-13: 11.57; 2021-11-20: 146.32; 2021-11-27: 146.32; 2021-12-04: 121.44
2262-1T2.PI.SS-WSC.9211 | Estimate To Complete Labor Units | 2021-12-11: 41.54; 2022-01-01: 66.25; 2022-01-08: 72.88; 2022-01-15: 72.88; 2022-01-22: 37.96
2262-1T2.PI.SS-WSC.9223 | Estimate To Complete Labor Units | 2021-11-06: 302.25; 2021-11-13: 39.42
2262-1T2.PI.SS-WSC.9231 | Estimate To Complete Labor Units | 2021-11-13: 103.67
2262-1T2.PI.SS-WSC.9247 | Estimate To Complete Labor Units | 2021-09-25: 244.6; 2021-10-02: 123.64
2262-1T2.PI.SS-WSC.9255 | Estimate To Complete Labor Units
2262-1T2.PI.SS-WSC.9263 | Estimate To Complete Labor Units | 2021-11-06: 0.2; 2021-11-13: 1.25
2262-1T2.PI.SS-WSC.9275 | Estimate To Complete Labor Units | 2021-11-13: 18.88
2262-2 T2.Flush. 9181 | Estimate To Complete Labor Units | 2021-11-20: 11.39; 2021-11-27: 50.11
2262-2 T2.Flush. 9182 | Estimate To Complete Labor Units | 2021-10-30: 36.38; 2021-11-06: 142.92; 2021-11-13: 142.92; 2021-11-20: 46.77
2262-2 T2.Flush. 9183 | Estimate To Complete Labor Units | 2021-10-09: 184.5
2262-2 T2.Flush. 9184 | Estimate To Complete Labor Units | 2021-11-06: 18.79; 2021-11-13: 657.71
2262-2 T2.HYDRO. 9173 | Estimate To Complete Labor Units | 2021-10-09: 4.45; 2021-10-16: 244.79; 2021-10-23: 244.79; 2021-10-30: 182.48
2262-2 T2.HYDRO. 9174 | Estimate To Complete Labor Units | 2021-09-25: 132.55; 2021-10-02: 197.04; 2021-10-09: 39.41
2262-2 T2.HYDRO. 9175 | Estimate To Complete Labor Units | 2021-11-13: 23.06; 2021-11-20: 38.44
2262-2 T2.Insul. 9191 | Estimate To Complete Labor Units | 2021-10-23: 2.96; 2021-10-30: 162.68; 2021-11-06: 162.68; 2021-11-13: 162.68; 2021-11-20: 162.68; 2021-11-27: 162.68; 2021-12-04: 162.68; 2021-12-11: 162.68; 2022-01-01: 127.19
2262-2 T2.Insul. 9192 | Estimate To Complete Labor Units | 2021-11-20: 136.93; 2021-11-27: 203.55; 2021-12-04: 203.55; 2021-12-11: 203.55; 2022-01-01: 185.04
2262-2 T2.Insul. 9193 | Estimate To Complete Labor Units | 2021-10-02: 185.16; 2021-10-09: 216.67; 2021-10-16: 47.27
2262-2 T2.Insul. 9194 | Estimate To Complete Labor Units | 2021-11-13: 145.8; 2021-11-20: 400.94; 2021-11-27: 400.94; 2021-12-04: 400.94; 2021-12-11: 400.94
2262-2 T2.Insul. 9195 | Estimate To Complete Labor Units | 2021-11-27: 99.35; 2021-12-04: 165.58; 2021-12-11: 165.58; 2022-01-01: 111.39
2262-2 T2.PI.SS-GSL. 9367 | Estimate To Complete Labor Units | 2021-10-16: 52.08
2262-2 T2.PI.SS-GSL. 9368 | Estimate To Complete Labor Units | 2021-10-16: 8.46; 2021-10-23: 12.04
2262-2 T2.PI.SS-GSL. 9369 | Estimate To Complete Labor Units | 2021-10-23: 9.52; 2021-10-30: 29.08; 2021-11-06: 29.08; 2021-11-13: 13.22
2262-2 T2.PI.SS-GSL. 9372 | Estimate To Complete Labor Units | 2021-10-23: 19.16
2262-2 T2.PI.SS-GVE. 9369 | Estimate To Complete Labor Units | 2021-09-25: 8.22
2262-2 T2.PI.SS-GVE. 9371 | Estimate To Complete Labor Units | 2021-09-25: 9.75; 2021-10-02: 18.69; 2021-10-09: 0.44
2262-2 T2.PI.SS-GVE. 9372 | Estimate To Complete Labor Units | 2021-10-16: 65.84; 2021-10-23: 25.61
2262-2 T2.PI.SS-GVE. 9373 | Estimate To Complete Labor Units | 2021-10-23: 98.33
2262-2 T2.PI.SS-GVE. 9697 | Estimate To Complete Labor Units | 2021-10-23: 0.54; 2021-10-30: 15.77
2262-2 T2.PI.SS-LPB. 9471 | Estimate To Complete Labor Units | 2021-10-02: 42.34
2262-2 T2.PI.SS-LPB. 9473 | Estimate To Complete Labor Units | 2021-10-02: 173.89; 2021-10-09: 198.74
2262-2 T2.PI.SS-LPB. 9474 | Estimate To Complete Labor Units | 2021-10-09: 39.37; 2021-10-16: 69.84; 2021-10-23: 69.84; 2021-10-30: 69.84; 2021-11-06: 69.84; 2021-11-13: 36.83
2262-2 T2.PI.SS-LPB. 9475 | Estimate To Complete Labor Units | 2021-11-13: 6.92; 2021-11-20: 5.85
2262-2 T2.PI.SS-SPB. 9173 | Estimate To Complete Labor Units | 2021-10-09: 51.49
2262-2 T2.PI.SS-SPB. 9390 | Estimate To Complete Labor Units | 2021-11-27: 4.59; 2021-12-04: 30.21; 2021-12-11: 30.21; 2022-01-01: 0.91
2262-2 T2.PI.SS-SPB. 9391 | Estimate To Complete Labor Units | 2022-01-01: 46.52; 2022-01-08: 1.59
2262-2 T2.PI.SS-WCW. 9375 | Estimate To Complete Labor Units | 2021-11-06: 0.99; 2021-11-13: 155.23; 2021-11-20: 46.99
2262-2 T2.PI.SS-WCW. 9376 | Estimate To Complete Labor Units
2262-2 T2.PI.SS-WCW. 9377 | Estimate To Complete Labor Units | 2021-11-20: 29.12; 2021-11-27: 1.25
2262-2 T2.PI.SS-WCW. 9378 | Estimate To Complete Labor Units | 2021-11-27: 255.47
2262-2 T2.PI.SS-WGS. 9160 | Estimate To Complete Labor Units
2262-2 T2.PI.SS-WGS. 9705 | Estimate To Complete Labor Units | 2021-12-11: 8.74
2262-2 T2.PI.SS-WGS. 9707 | Estimate To Complete Labor Units | 2021-12-11: 118.15
2262-2 T2.PI.SS-WPR. 9177 | Estimate To Complete Labor Units | 2021-11-27: 17.88
2262-2 T2.PI.SS-WSC. 9379 | Estimate To Complete Labor Units | 2021-09-25: 79.85
2262-2 T2.PI.SS-WSC. 9380 | Estimate To Complete Labor Units | 2021-10-09: 2.57
2262-2 T2.PI.SS-WSC. 9381 | Estimate To Complete Labor Units | 2021-10-09: 3.84; 2021-10-16: 72.97
2262-2 T2.PI.SS-WSC. 9382 | Estimate To Complete Labor Units | 2021-10-16: 91.54; 2021-10-23: 139.85; 2021-10-30: 99.17
2262-2 T2.PI.SS-WSC. 9384 | Estimate To Complete Labor Units | 2021-10-30: 13.48
2262-2 T2.PI.SS-WSC. 9385 | Estimate To Complete Labor Units | 2021-10-30: 3.51; 2021-11-06: 66.71
2262-2 T2.PI.SS-WSC. 9386 | Estimate To Complete Labor Units | 2021-11-06: 114.16
2262-2 T2.PI.SS-WWW. 9709 | Estimate To Complete Labor Units | 2021-09-25: 38.86
2262-2.T2.PI.CS-GSL.9203 | Estimate To Complete Labor Units | 2021-10-09: 2.85; 2021-10-16: 54.24
2262-2.T2.PI.CS-GVE.9190 | Estimate To Complete Labor Units | 2021-10-30: 58.94
2262-2.T2.PI.CS-LPB.9189 | Estimate To Complete Labor Units | 2021-09-25: 115.4; 2021-10-02: 12.82
2262-2.T2.PI.CS-LPN.9179 | Estimate To Complete Labor Units | 2021-09-25: 56.51
2262-2.T2.PI.CS-WFI.9646 | Estimate To Complete Labor Units | 2021-12-04: 23.85
2262-2.T2.PI.HDPE-WCW.80 | Estimate To Complete Labor Units | 2021-10-02: 53.02
2262-2.T2.PI.HDPE-WRO.92 | Estimate To Complete Labor Units | 2021-12-04: 76.13; 2021-12-11: 12.52
2262-2.T2.PI.SS-LPB.9181 | Estimate To Complete Labor Units | 2021-09-25: 244.54
2262-2.T2.PI.SS-SPB.9223 | Estimate To Complete Labor Units | 2021-10-09: 413.11
2262-2.T2.PI.SS-WPO.9650 | Estimate To Complete Labor Units | 2021-11-27: 27.53; 2021-12-04: 169.71
2262-2.T2.PI.SS-WRO.9654 | Estimate To Complete Labor Units | 2021-12-11: 307.28
2262-2.T2.PI.SS-WSC.9239 | Estimate To Complete Labor Units | 2021-11-20: 81.27; 2021-11-27: 109.45
2262-3.T2.PI.1435 | Estimate To Complete Labor Units | 2021-10-09: 16.21; 2021-10-16: 17.77
2262-3.T2.PI.CS-GSL.1394 | Estimate To Complete Labor Units | 2021-09-25: 4.43
2262-3.T2.PI.CS-GSL.1426 | Estimate To Complete Labor Units | 2021-09-25: 32.58
2262-3.T2.PI.CS-GSL.1438 | Estimate To Complete Labor Units | 2021-09-25: 16.05; 2021-10-02: 91.24
2262-3.T2.PI.CS-LPB.1442 | Estimate To Complete Labor Units | 2021-09-25: 5.46
2262-3.T2.PI.CS-LPN.1446 | Estimate To Complete Labor Units | 2021-09-25: 24.6; 2021-10-02: 193.29; 2021-10-09: 193.29; 2021-10-16: 193.29; 2021-10-23: 80.83
2262-3.T2.PI.CS-WRA.1439 | Estimate To Complete Labor Units | 2021-10-16: 20.09
2262-3.T2.PI.HDPE-WR.1440 | Estimate To Complete Labor Units | 2021-10-16: 25.62
2262-3.T2.PI.PS.1434 | Estimate To Complete Labor Units | 2021-10-16: 1.34; 2021-10-23: 70.99
2262-3.T2.PI.SS-LPB.1430 | Estimate To Complete Labor Units
2262-3.T2.PI.SS-SPB.1454 | Estimate To Complete Labor Units | 2021-09-25: 89.36
2262-3.T2.PI.SS-SPB.1458 | Estimate To Complete Labor Units | 2021-10-02: 10.23; 2021-10-09: 37.03; 2021-10-16: 8.28
2262-3.T2.PI.SS-WSC.1422 | Estimate To Complete Labor Units | 2021-09-25: 14.76
2262-3.T2.PI.SS-WSC.1434 | Estimate To Complete Labor Units | 2021-09-25: 2.71
2272-1.T2.PI.1224 | Estimate To Complete Labor Units | 2021-10-16: 26.51; 2021-10-23: 145.81; 2021-10-30: 92.79
2272-1.T2.PI.1225 | Estimate To Complete Labor Units | 2021-10-30: 57.43; 2021-11-06: 157.95; 2021-11-13: 157.95; 2021-11-20: 152.2
2272-1.T2.PI.1228 | Estimate To Complete Labor Units | 2021-11-20: 5.9; 2021-11-27: 162.35; 2021-12-04: 162.35; 2021-12-11: 156.45
2272-1.T2.PI.1229 | Estimate To Complete Labor Units | 2021-12-11: 9.6; 2022-01-01: 240.07; 2022-01-08: 264.07; 2022-01-15: 240.07
2272-1.T2.PI.1230 | Estimate To Complete Labor Units | 2022-01-01: 97.01
2272-1.T2.PI.1232 | Estimate To Complete Labor Units | 2022-01-01: 8.07; 2022-01-08: 221.98; 2022-01-15: 52.47
2272-1.T2.PI.1233 | Estimate To Complete Labor Units | 2022-01-15: 191.46; 2022-01-22: 127.64
2272-1.T2.PI.1234 | Estimate To Complete Labor Units | 2022-01-22: 129.44; 2022-01-29: 254.09
2272-1.T2.PI.1235 | Estimate To Complete Labor Units | 2022-01-29: 5.14; 2022-02-05: 141.25; 2022-02-12: 141.25; 2022-02-19: 59.07
2272-1.T2.PI.1236 | Estimate To Complete Labor Units | 2022-01-29: 53.72; 2022-02-05: 246.24; 2022-02-12: 246.24; 2022-02-19: 102.97
2272-1.T2.PI.1238 | Estimate To Complete Labor Units | 2022-01-29: 22.29; 2022-02-05: 175.1; 2022-02-12: 175.1; 2022-02-19: 73.22
2272-2.T2.HY.1164 | Estimate To Complete Labor Units | 2022-01-22: 5.38; 2022-01-29: 295.97; 2022-02-05: 129.15
2272-2.T2.IN.1168 | Estimate To Complete Labor Units | 2022-01-29: 106.66; 2022-02-05: 225.63; 2022-02-12: 225.63; 2022-02-19: 139.48
2272-2.T2.PI.1140 | Estimate To Complete Labor Units | 2021-11-20: 32.49; 2021-11-27: 89.34; 2021-12-04: 1.62
2272-2.T2.PI.1144 | Estimate To Complete Labor Units | 2021-12-04: 268.95
2272-2.T2.PI.1146 | Estimate To Complete Labor Units | 2021-12-04: 19.27; 2021-12-11: 221.66
2272-2.T2.PI.1148 | Estimate To Complete Labor Units | 2021-12-11: 13.84; 2022-01-01: 29.85
2272-2.T2.PI.1150 | Estimate To Complete Labor Units | 2022-01-01: 162.48; 2022-01-08: 4.17
2272-2.T2.PI.1152 | Estimate To Complete Labor Units | 2022-01-01: 33.8; 2022-01-08: 116.43
2272-2.T2.PI.1154 | Estimate To Complete Labor Units | 2022-01-08: 80.12; 2022-01-15: 129.61; 2022-01-22: 4.71
2272-2.T2.PI.1156 | Estimate To Complete Labor Units | 2022-01-08: 10.69; 2022-01-15: 147; 2022-01-22: 64.14
2272-2.T2.PI.1158 | Estimate To Complete Labor Units | 2022-01-22: 5.2
2272-2.T2.PI.1162 | Estimate To Complete Labor Units | 2022-01-08: 58.61; 2022-01-15: 179.09; 2022-01-22: 175.83
2272-2.T2.PI.1166 | Estimate To Complete Labor Units | 2022-01-15: 104.64; 2022-01-22: 166.2
4242.T2.PI.CS-AIN.1663 | Estimate To Complete Labor Units
4242.T2.PI.CS-AIN.1681 | Estimate To Complete Labor Units
4242.T2.PI.CS-AIN.1701 | Estimate To Complete Labor Units
4242.T2.PI.CS-AIN.1722 | Estimate To Complete Labor Units | 2021-12-04: 32.22
4242.T2.PI.CS-AIN.1746 | Estimate To Complete Labor Units | 2021-11-13: 47.04
4242.T2.PI.CS-AIN.1774 | Estimate To Complete Labor Units | 2021-09-25: 21.83; 2021-10-02: 18.92
4242.T2.PI.CS-AIN.1802 | Estimate To Complete Labor Units
4242.T2.PI.CS-AIN.1820 | Estimate To Complete Labor Units
4242.T2.PI.CS-AIN.1842 | Estimate To Complete Labor Units
4242.T2.PI.CS-GCD.1665 | Estimate To Complete Labor Units
4242.T2.PI.CS-GCD.1683 | Estimate To Complete Labor Units
4242.T2.PI.CS-GCD.1703 | Estimate To Complete Labor Units
4242.T2.PI.CS-GSL.1705 | Estimate To Complete Labor Units
4242.T2.PI.CS-GSL.1724 | Estimate To Complete Labor Units | 2021-12-04: 33.22
4242.T2.PI.CS-GSL.1748 | Estimate To Complete Labor Units | 2021-11-13: 39.07
4242.T2.PI.CS-GSL.1776 | Estimate To Complete Labor Units | 2021-10-02: 46.5
4242.T2.PI.CS-GSL.1856 | Estimate To Complete Labor Units
4242.T2.PI.CS-GSL.1858 | Estimate To Complete Labor Units | 2022-01-01: 82.8; 2022-01-08: 114.65
4242.T2.PI.CS-GSL.1860 | Estimate To Complete Labor Units | 2022-01-08: 60.51; 2022-01-15: 136.94
4242.T2.PI.CS-GSL.1862 | Estimate To Complete Labor Units | 2022-01-15: 17.05; 2022-01-22: 78.13; 2022-01-29: 78.13; 2022-02-05: 24.15
4242.T2.PI.CS-LCC.1750 | Estimate To Complete Labor Units | 2021-11-20: 56.58
4242.T2.PI.CS-LCC.1778 | Estimate To Complete Labor Units | 2021-10-02: 23.29; 2021-10-09: 23.29
4242.T2.PI.CS-LPB.1685 | Estimate To Complete Labor Units
4242.T2.PI.CS-LPB.1707 | Estimate To Complete Labor Units
4242.T2.PI.CS-LPB.1726 | Estimate To Complete Labor Units | 2021-12-04: 14.94; 2021-12-11: 44.81
4242.T2.PI.CS-LPB.1752 | Estimate To Complete Labor Units | 2021-11-20: 68.78; 2021-11-27: 28.02
4242.T2.PI.CS-LPB.1780 | Estimate To Complete Labor Units | 2021-10-09: 85.21
4242.T2.PI.CS-LPB.1804 | Estimate To Complete Labor Units
4242.T2.PI.CS-LPB.1822 | Estimate To Complete Labor Units
4242.T2.PI.CS-LSH.1709 | Estimate To Complete Labor Units
4242.T2.PI.CS-LSH.1728 | Estimate To Complete Labor Units | 2021-12-11: 19.04
4242.T2.PI.CS-LSH.1754 | Estimate To Complete Labor Units | 2021-11-27: 19.04
4242.T2.PI.CS-LSH.1782 | Estimate To Complete Labor Units | 2021-10-09: 2.71; 2021-10-16: 6.33
4242.T2.PI.CS-LSH.1806 | Estimate To Complete Labor Units | 2021-09-25: 9.04
4242.T2.PI.CS-LSH.1824 | Estimate To Complete Labor Units
4242.T2.PI.CS-LSH.1844 | Estimate To Complete Labor Units
4242.T2.PI.CS-SPB.1711 | Estimate To Complete Labor Units
4242.T2.PI.CS-SPB.1730 | Estimate To Complete Labor Units | 2021-12-11: 19.04
4242.T2.PI.CS-SPB.1756 | Estimate To Complete Labor Units | 2021-11-27: 24.86
4242.T2.PI.CS-SPB.1784 | Estimate To Complete Labor Units | 2021-10-30: 31.03
4242.T2.PI.CS-SPB.1808 | Estimate To Complete Labor Units
4242.T2.PI.CS-SPB.1826 | Estimate To Complete Labor Units
4242.T2.PI.FRP-LPA.1667 | Estimate To Complete Labor Units
4242.T2.PI.FRP-LPA.1687 | Estimate To Complete Labor Units
4242.T2.PI.FRP-LPA.1712 | Estimate To Complete Labor Units | 2021-10-09: 16.93; 2021-10-16: 74.99
4242.T2.PI.FRP-LPA.1732 | Estimate To Complete Labor Units | 2021-11-20: 29.5
4242.T2.PI.FRP-LPA.1758 | Estimate To Complete Labor Units | 2021-11-06: 19.67; 2021-11-13: 9.83
4242.T2.PI.FRP-LPA.1786 | Estimate To Complete Labor Units | 2021-10-02: 19.75
4242.T2.PI.FRP-LPA.1810 | Estimate To Complete Labor Units
4242.T2.PI.FRP-LPA.1828 | Estimate To Complete Labor Units
4242.T2.PI.FRP-LPA.1846 | Estimate To Complete Labor Units
4242.T2.PI.FRP-LSD.1713 | Estimate To Complete Labor Units | 2021-10-16: 29.5
4242.T2.PI.FRP-LSD.1734 | Estimate To Complete Labor Units | 2021-11-20: 29.5
4242.T2.PI.FRP-LSD.1788 | Estimate To Complete Labor Units | 2021-10-02: 38.99
4242.T2.PI.FRP-LSD.1830 | Estimate To Complete Labor Units
4242.T2.PI.FRP-LSD.1848 | Estimate To Complete Labor Units
4242.T2.PI.FRP-WCW.1669 | Estimate To Complete Labor Units | 2021-09-25: 143.45; 2021-10-02: 65.21
4242.T2.PI.FRP-WCW.1689 | Estimate To Complete Labor Units | 2021-10-02: 11.88; 2021-10-09: 35.63
4242.T2.PI.FRP-WCW.1714 | Estimate To Complete Labor Units | 2021-10-16: 18.57; 2021-10-23: 72.94; 2021-10-30: 39.78
4242.T2.PI.FRP-WCW.1736 | Estimate To Complete Labor Units | 2021-11-20: 65.18; 2021-11-27: 19.84
4242.T2.PI.FRP-WCW.1760 | Estimate To Complete Labor Units | 2021-11-13: 85.02
4242.T2.PI.FRP-WCW.1790 | Estimate To Complete Labor Units | 2021-10-02: 27.7; 2021-10-09: 27.7
4242.T2.PI.HDPE-WCW.1671 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WCW.1691 | Estimate To Complete Labor Units | 2021-10-02: 16.25
4242.T2.PI.HDPE-WCW.1715 | Estimate To Complete Labor Units | 2021-10-09: 16.25
4242.T2.PI.HDPE-WCW.1738 | Estimate To Complete Labor Units | 2021-11-13: 16.25
4242.T2.PI.HDPE-WCW.1762 | Estimate To Complete Labor Units | 2021-10-09: 23.13
4242.T2.PI.HDPE-WPO.1673 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WPO.1693 | Estimate To Complete Labor Units | 2021-10-02: 33.38
4242.T2.PI.HDPE-WPO.1716 | Estimate To Complete Labor Units | 2021-10-09: 21.69
4242.T2.PI.HDPE-WPO.1764 | Estimate To Complete Labor Units | 2021-10-09: 33.38
4242.T2.PI.HDPE-WPO.1792 | Estimate To Complete Labor Units | 2021-09-25: 46.77
4242.T2.PI.HDPE-WPO.1812 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WPO.1832 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WPO.1850 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WRA.1766 | Estimate To Complete Labor Units | 2021-10-09: 18.26
4242.T2.PI.HDPE-WRA.1794 | Estimate To Complete Labor Units | 2021-09-25: 8.26
4242.T2.PI.HDPE-WRA.1812 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WRA.1834 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WRA.1852 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WRO.1675 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WRO.1695 | Estimate To Complete Labor Units | 2021-10-02: 35.7
4242.T2.PI.HDPE-WRO.1717 | Estimate To Complete Labor Units | 2021-10-09: 41.55
4242.T2.PI.HDPE-WRO.1740 | Estimate To Complete Labor Units | 2021-11-13: 35.36; 2021-11-20: 4.42
4242.T2.PI.HDPE-WRO.1768 | Estimate To Complete Labor Units | 2021-11-06: 41.55
4242.T2.PI.HDPE-WRO.1796 | Estimate To Complete Labor Units | 2021-09-25: 26.7; 2021-10-02: 7.85
4242.T2.PI.HDPE-WRO.1814 | Estimate To Complete Labor Units
4242.T2.PI.HDPE-WRO.1836 | Estimate To Complete Labor Units
4242.T2.PI.INS.1792 | Estimate To Complete Labor Units | 2021-10-02: 6.38
4242.T2.PI.INS.1794 | Estimate To Complete Labor Units | 2021-10-02: 7.58; 2021-10-09: 7.58
4242.T2.PI.INS.1796 | Estimate To Complete Labor Units | 2021-10-16: 8.97; 2021-10-23: 15.92; 2021-10-30: 8.68
4242.T2.PI.INS.1798 | Estimate To Complete Labor Units | 2021-12-11: 16.53; 2022-01-01: 21.62
4242.T2.PI.INS.1800 | Estimate To Complete Labor Units | 2021-11-27: 27.73; 2021-12-04: 20.98
4242.T2.PI.INS.1802 | Estimate To Complete Labor Units | 2021-10-23: 14.81; 2021-10-30: 18.51; 2021-11-06: 18.51; 2021-11-13: 5.72
4242.T2.PI.INS.1804 | Estimate To Complete Labor Units | 2021-09-25: 11.36
4242.T2.PI.INS.1806 | Estimate To Complete Labor Units | 2021-09-25: 16.53
4242.T2.PI.INS.1808 | Estimate To Complete Labor Units | 2021-09-25: 4.81
4242.T2.PI.INS.1810 | Estimate To Complete Labor Units | 2021-09-25: 3.21; 2021-10-02: 0.58
4242.T2.PI.INS.1812 | Estimate To Complete Labor Units | 2022-01-01: 0.08; 2022-01-08: 0.1
4242.T2.PI.INS.1814 | Estimate To Complete Labor Units | 2022-01-01: 0.05; 2022-01-08: 0.07; 2022-01-15: 0.06
4242.T2.PI.INS.1816 | Estimate To Complete Labor Units | 2022-01-29: 5.21; 2022-02-05: 1.85
4242.T2.PI.SS-LPB.1677 | Estimate To Complete Labor Units
4242.T2.PI.SS-LPB.1697 | Estimate To Complete Labor Units
4242.T2.PI.SS-LPB.1718 | Estimate To Complete Labor Units
4242.T2.PI.SS-LPB.1742 | Estimate To Complete Labor Units | 2021-12-11: 36.01; 2022-01-01: 10.29
4242.T2.PI.SS-LPB.1770 | Estimate To Complete Labor Units | 2021-11-27: 40.74; 2021-12-04: 5.56
4242.T2.PI.SS-LPB.1798 | Estimate To Complete Labor Units | 2021-11-06: 34.47
4242.T2.PI.SS-LPB.1816 | Estimate To Complete Labor Units
4242.T2.PI.SS-LPB.1838 | Estimate To Complete Labor Units
4242.T2.PI.SS-WSC.1679 | Estimate To Complete Labor Units
4242.T2.PI.SS-WSC.1699 | Estimate To Complete Labor Units
4242.T2.PI.SS-WSC.1720 | Estimate To Complete Labor Units
4242.T2.PI.SS-WSC.1744 | Estimate To Complete Labor Units | 2022-01-01: 62.34
4242.T2.PI.SS-WSC.1772 | Estimate To Complete Labor Units | 2021-12-04: 41.12
4242.T2.PI.SS-WSC.1800 | Estimate To Complete Labor Units | 2021-11-06: 13.66; 2021-11-13: 29.02
4242.T2.PI.SS-WSC.1818 | Estimate To Complete Labor Units
4242.T2.PI.SS-WSC.1840 | Estimate To Complete Labor Units
4242.T2.PI.SS-WSC.1854 | Estimate To Complete Labor Units
CN.2252-1.T2.CV.1000 | Estimate To Complete Labor Units | 2021-11-13: 36
CN.2252-1.T2.MC.1000 | Estimate To Complete Labor Units
CN.2252-1.T2.MC.1010 | Estimate To Complete Labor Units | 2021-09-25: 30.8
CN.2252-1.T2.MC.1030 | Estimate To Complete Labor Units | 2021-09-25: 29.87
CN.2252-1.T2.MC.1040 | Estimate To Complete Labor Units
CN.2252-1.T2.MC.1050 | Estimate To Complete Labor Units | 2021-10-02: 15.4; 2021-10-09: 15.4
CN.2252-1.T2.MC.1060 | Estimate To Complete Labor Units
CN.2252-1.T2.MC.1070 | Estimate To Complete Labor Units | 2021-09-25: 7.7; 2021-10-02: 23.1
CN.2252-1.T2.MC.1090 | Estimate To Complete Labor Units | 2021-09-25: 22.4
CN.2252-1.T2.MC.1140 | Estimate To Complete Labor Units | 2021-10-23: 23.66
CN.2252-1.T2.MC.1150 | Estimate To Complete Labor Units | 2021-10-09: 101.1
CN.2252-1.T2.MC.1170 | Estimate To Complete Labor Units | 2021-10-09: 36.26; 2021-10-16: 326.34
CN.2252-1.T2.MC.1180 | Estimate To Complete Labor Units
CN.2252-1.T2.MC.1190 | Estimate To Complete Labor Units | 2021-11-13: 25.48; 2021-11-20: 5.27
CN.2252-1.T2.MC.1210 | Estimate To Complete Labor Units
CN.2252-1.T2.MC.1230 | Estimate To Complete Labor Units | 2021-10-16: 52.48; 2021-10-23: 209.92
CN.2252-1.T2.MC.1260 | Estimate To Complete Labor Units | 2021-11-20: 7.2
CN.2252-1.T2.MC.1280 | Estimate To Complete Labor Units | 2021-10-02: 61.6
CN.2252-1.T2.MC.1295 | Estimate To Complete Labor Units | 2021-11-06: 89.9; 2021-11-13: 130.11; 2021-11-20: 28.39
CN.2252-1.T2.MC.1483 | Estimate To Complete Labor Units | 2021-10-30: 2.73; 2021-11-06: 75.17; 2021-11-13: 4.1
CN.2252-1.T2.MC.1582 | Estimate To Complete Labor Units | 2021-10-23: 13.9; 2021-10-30: 105.21
CN.2252-1.T2.PI.1080 | Estimate To Complete Labor Units | 2021-10-09: 73.45; 2021-10-16: 194.21; 2021-10-23: 194.21; 2021-10-30: 194.21; 2021-11-06: 194.21; 2021-11-13: 166.67
CN.2252-1.T2.PI.1090 | Estimate To Complete Labor Units | 2022-01-01: 133.71; 2022-01-08: 147.67; 2022-01-15: 147.67; 2022-01-22: 147.67; 2022-01-29: 147.67; 2022-02-05: 147.67; 2022-02-12: 110.62
CN.2252-1.T2.PI.1094 | Estimate To Complete Labor Units | 2022-01-01: 70.62; 2022-01-08: 95.9; 2022-01-15: 77.59
CN.2252-1.T2.PL.11102 | Estimate To Complete Labor Units
CN.2252-1.T2.PL.11106 | Estimate To Complete Labor Units
CN.2252-1.T2.PL.11110 | Estimate To Complete Labor Units
CN.2252-1.T2.PL.11114 | Estimate To Complete Labor Units
CN.2252-1.T2.PL.11118 | Estimate To Complete Labor Units
CN.2252-1.T2.PL.11122 | Estimate To Complete Labor Units
CN.2252-1.T2.PL.11126 | Estimate To Complete Labor Units
CN.2252-1.T2.PL.1188 | Estimate To Complete Labor Units
CN.2252-1.T2.PL.1192 | Estimate To Complete Labor Units
CN.2252-1.T2.PL.1196 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1338 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1342 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1346 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1350 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1354 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1358 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1362 | Estimate To Complete Labor Units | 2021-09-25: 7.11
CN.2252-1.T2.ST.1366 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1370 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1374 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1378 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1382 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1386 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1390 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1394 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1398 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1399 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1402 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1406 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1410 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1414 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1418 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1422 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1430 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1434 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1438 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1442 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1446 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1454 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1458 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1462 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1466 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1470 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1474 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1478 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1482 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1486 | Estimate To Complete Labor Units
CN.2252-1.T2.ST.1490 | Estimate To Complete Labor Units | 2021-09-25: 23.58
CN.2252-1.T2.ST.1494 | Estimate To Complete Labor Units | 2021-09-25: 19.32
CN.2252-1.T2.ST.1498 | Estimate To Complete Labor Units | 2021-09-25: 18.99
CN.2252-1.T2.ST.1502 | Estimate To Complete Labor Units | 2021-09-25: 15.22; 2021-10-02: 25.37; 2021-10-09: 0.92
CN.2252-1.T2.ST.1506 | Estimate To Complete Labor Units | 2021-09-25: 107.64; 2021-10-02: 107.64; 2021-10-09: 107.64; 2021-10-16: 107.64; 2021-10-23: 107.64; 2021-10-30: 107.64; 2021-11-06: 50.89
CN.2252-1.T2.ST.1510 | Estimate To Complete Labor Units | 2021-10-23: 98.48; 2021-10-30: 110.54; 2021-11-06: 52.26
CN.2252-2.T2.MC.1000 | Estimate To Complete Labor Units | 2021-10-09: 153.25; 2021-10-16: 240.83; 2021-10-23: 240.83; 2021-10-30: 240.83; 2021-11-06: 91.95
CN.2252-2.T2.MC.1020 | Estimate To Complete Labor Units | 2021-09-25: 52.8
CN.2252-2.T2.MC.1030 | Estimate To Complete Labor Units
CN.2252-2.T2.MC.1040 | Estimate To Complete Labor Units
CN.2252-2.T2.MC.1050 | Estimate To Complete Labor Units | 2021-09-25: 22
CN.2252-2.T2.MC.1051 | Estimate To Complete Labor Units | 2021-09-25: 4.89; 2021-10-02: 81.45; 2021-10-09: 2.52
CN.2252-2.T2.MC.1052 | Estimate To Complete Labor Units | 2021-09-25: 75
CN.2252-2.T2.MC.1053 | Estimate To Complete Labor Units
CN.2252-2.T2.MC.1054 | Estimate To Complete Labor Units | 2021-11-20: 23.63; 2021-11-27: 51.98
CN.2252-2.T2.PI.1092 | Estimate To Complete Labor Units | 2021-12-11: 168.57; 2022-01-01: 208.12; 2022-01-08: 228.93; 2022-01-15: 18.73
CN.2252-2.T2.ST.1230 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1240 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1250 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1260 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1270 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1280 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1290 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1300 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1310 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1324 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1328 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1332 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1336 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1340 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1344 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1348 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1352 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1356 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1360 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1364 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1368 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1372 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1376 | Estimate To Complete Labor Units
CN.2252-2.T2.ST.1380 | Estimate To Complete Labor Units | 2021-09-25: 3.36; 2021-10-02: 0.92
CN.2252-2.T2.ST.1384 | Estimate To Complete Labor Units | 2021-10-02: 7.79; 2021-10-09: 3.89
CN.2252-2.T2.ST.1388 | Estimate To Complete Labor Units | 2021-09-25: 53.96; 2021-10-02: 53.96; 2021-10-09: 53.96; 2021-10-16: 53.96; 2021-10-23: 30.42
CN.2252-2.T2.ST.1392 | Estimate To Complete Labor Units | 2021-10-23: 26.52; 2021-10-30: 60.78; 2021-11-06: 56.36
CN.2252-3 T2.Insul.1223 | Estimate To Complete Labor Units | 2021-11-20: 44.9; 2021-11-27: 64.99; 2021-12-04: 31.91
CN.2252-3 T2.Insul.1294 | Estimate To Complete Labor Units | 2021-11-06: 36.85; 2021-11-13: 45.03; 2021-11-20: 13.92
CN.2252-3.T2.Insul.1296 | Estimate To Complete Labor Units
CN.2252-3.T2.Insul.1298 | Estimate To Complete Labor Units
CN.2252-3.T2.Insul.1300 | Estimate To Complete Labor Units
CN.2252-3.T2.Insul.1302 | Estimate To Complete Labor Units
CN.2252-3.T2.Insul.1304 | Estimate To Complete Labor Units | 2021-12-04: 44.07; 2021-12-11: 86.56; 2022-01-01: 78.69; 2022-01-08: 86.56; 2022-01-15: 86.56; 2022-01-22: 86.56; 2022-01-29: 86.56; 2022-02-05: 73.97
CN.2252-3.T2.MC.1001 | Estimate To Complete Labor Units
CN.2252-3.T2.MC.1200 | Estimate To Complete Labor Units
CN.2252-3.T2.MC.1220 | Estimate To Complete Labor Units | 2021-09-25: 8
CN.2252-3.T2.MC.1272 | Estimate To Complete Labor Units | 2021-09-25: 22
CN.2252-3.T2.MC.1276 | Estimate To Complete Labor Units
CN.2252-3.T2.MC.1283 | Estimate To Complete Labor Units | 2021-09-25: 33.04
CN.2252-3.T2.MC.1285 | Estimate To Complete Labor Units | 2021-09-25: 43.75
CN.2252-3.T2.MC.1290 | Estimate To Complete Labor Units
CN.2252-3.T2.MC.1291 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1180 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1190 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1200 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1210 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1220 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1230 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1250 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1260 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1270 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1280 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1290 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1300 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1310 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1320 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1324 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1332 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1336 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1344 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1348 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1352 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1360 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1364 | Estimate To Complete Labor Units
CN.2252-3.T2.ST.1368 | Estimate To Complete Labor Units | 2021-09-25: 142.75
CN.2252-3.T2.ST.1372 | Estimate To Complete Labor Units | 2021-09-25: 112.49; 2021-10-02: 137.49; 2021-10-09: 137.49; 2021-10-16: 44.75
CN.2252-3.T2.ST.1376 | Estimate To Complete Labor Units | 2021-10-09: 29.05; 2021-10-16: 42.98
CN.2252-4.T2.PI.1094 | Estimate To Complete Labor Units | 2022-01-01: 119.29; 2022-01-08: 194.11; 2022-01-15: 194.11; 2022-01-22: 21.88
CN.2252-4.T2.PI.1096 | Estimate To Complete Labor Units | 2022-01-08: 158.97; 2022-01-15: 303.58; 2022-01-22: 255.01
CN.2252-4.T2.ST.1198 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1202 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1206 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1210 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1214 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1218 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1222 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1226 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1230 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1234 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1238 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1242 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1246 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1250 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1254 | Estimate To Complete Labor Units
CN.2252-4.T2.ST.1258 | Estimate To Complete Labor Units | 2021-09-25: 33.99
CN.2252-5.T2.MC.1286 | Estimate To Complete Labor Units | 2021-09-25: 19.07; 2021-10-02: 38.13
CN.2252-5.T2.MC.1288 | Estimate To Complete Labor Units | 2021-10-16: 139.57; 2021-10-23: 279.13; 2021-10-30: 172.55
CN.2252-5.T2.MC.1291 | Estimate To Complete Labor Units | 2021-10-02: 28.6
CN.2252-5.T2.MC.1374 | Estimate To Complete Labor Units
CN.2252-5.T2.MC.1378 | Estimate To Complete Labor Units
CN.2252-5.T2.MC.1381 | Estimate To Complete Labor Units | 2021-10-02: 3.87; 2021-10-09: 6.93
CN.2252-5.T2.MC.1382 | Estimate To Complete Labor Units
CN.2252-5.T2.MC.1386 | Estimate To Complete Labor Units | 2021-09-25: 5.76
CN.2252-5.T2.PI.1098 | Estimate To Complete Labor Units | 2021-11-06: 3.75; 2021-11-13: 114.72; 2021-11-20: 114.72; 2021-11-27: 114.72; 2021-12-04: 114.72; 2021-12-11: 114.72; 2022-01-01: 23.36
CN.2252-5.T2.PI.1100 | Estimate To Complete Labor Units | 2021-11-27: 2.3; 2021-12-04: 3.74; 2021-12-11: 3.74; 2022-01-01: 3.4; 2022-01-08: 0.08
CN.2252-6.T2.ST.1380 | Estimate To Complete Labor Units
CN.2252-6.T2.ST.1390 | Estimate To Complete Labor Units | 2021-09-25: 13.46
CN.2252-7.T2.ST.1400 | Estimate To Complete Labor Units | 2021-09-25: 42.43
CN.2252-7.T2.ST.1410 | Estimate To Complete Labor Units | 2021-09-25: 26.12; 2021-10-02: 110.49; 2021-10-09: 4.02
CN.2252-7.T2.ST.1412 | Estimate To Complete Labor Units | 2021-10-09: 26.62; 2021-10-16: 8.54
CN.2262-4.T2.ST.1551 | Estimate To Complete Labor Units | 2021-11-27: 82; 2021-12-04: 86.74; 2021-12-11: 86.74; 2022-01-01: 4.73
CN.2262-4.T2.ST.1554 | Estimate To Complete Labor Units | 2022-01-01: 65.05
CN.2262.T2.MC.1010 | Estimate To Complete Labor Units
CN.2262.T2.MC.1020 | Estimate To Complete Labor Units
CN.2262.T2.MC.1030 | Estimate To Complete Labor Units
CN.2262.T2.MC.1040 | Estimate To Complete Labor Units
CN.2262.T2.MC.1060 | Estimate To Complete Labor Units
CN.2262.T2.MC.1070 | Estimate To Complete Labor Units
CN.2262.T2.MC.1080 | Estimate To Complete Labor Units
CN.2262.T2.MC.1090 | Estimate To Complete Labor Units
CN.2262.T2.MC.1100 | Estimate To Complete Labor Units
CN.2262.T2.MC.1120 | Estimate To Complete Labor Units
CN.2262.T2.MC.1160 | Estimate To Complete Labor Units
CN.2262.T2.MC.1172 | Estimate To Complete Labor Units
CN.2262.T2.MC.1173 | Estimate To Complete Labor Units | 2021-09-25: 21.24
CN.2262.T2.MC.1174 | Estimate To Complete Labor Units
CN.2262.T2.MC.1175 | Estimate To Complete Labor Units
CN.2262.T2.MC.1176 | Estimate To Complete Labor Units
CN.2262.T2.MC.1177 | Estimate To Complete Labor Units
CN.2262.T2.MC.1178 | Estimate To Complete Labor Units
CN.2262.T2.MC.1179 | Estimate To Complete Labor Units
CN.2262.T2.MC.1180 | Estimate To Complete Labor Units
CN.2262.T2.MC.1181 | Estimate To Complete Labor Units
CN.2262.T2.MC.1182 | Estimate To Complete Labor Units
CN.2262.T2.MC.1183 | Estimate To Complete Labor Units
CN.2262.T2.MC.1187 | Estimate To Complete Labor Units
CN.2262.T2.MC.1191 | Estimate To Complete Labor Units | 2021-09-25: 56.52; 2021-10-02: 60.95; 2021-10-09: 60.95; 2021-10-16: 21.05
CN.2262.T2.MC.1195 | Estimate To Complete Labor Units | 2021-10-16: 293.42; 2021-10-23: 32.6
CN.2262.T2.MC.1199 | Estimate To Complete Labor Units
CN.2262.T2.MC.1203 | Estimate To Complete Labor Units | 2021-10-23: 144
CN.2262.T2.MC.1211 | Estimate To Complete Labor Units
CN.2262.T2.MC.1215 | Estimate To Complete Labor Units
CN.2262.T2.MC.1219 | Estimate To Complete Labor Units
CN.2262.T2.MC.1221 | Estimate To Complete Labor Units | 2021-11-20: 37.95
CN.2262.T2.MC.1225 | Estimate To Complete Labor Units
CN.2262.T2.MC.1227 | Estimate To Complete Labor Units | 2021-11-20: 27; 2021-11-27: 123.75; 2021-12-04: 123.75; 2021-12-11: 40.5
CN.2262.T2.ST.1304 | Estimate To Complete Labor Units
CN.2262.T2.ST.1314 | Estimate To Complete Labor Units
CN.2262.T2.ST.1324 | Estimate To Complete Labor Units
CN.2262.T2.ST.1334 | Estimate To Complete Labor Units
CN.2262.T2.ST.1344 | Estimate To Complete Labor Units
CN.2262.T2.ST.1354 | Estimate To Complete Labor Units
CN.2262.T2.ST.1364 | Estimate To Complete Labor Units
CN.2262.T2.ST.1374 | Estimate To Complete Labor Units | 2021-09-25: 12.5
CN.2262.T2.ST.1384 | Estimate To Complete Labor Units | 2021-09-25: 1.05
CN.2262.T2.ST.1394 | Estimate To Complete Labor Units
CN.2262.T2.ST.1404 | Estimate To Complete Labor Units
CN.2262.T2.ST.1424 | Estimate To Complete Labor Units
CN.2262.T2.ST.1434 | Estimate To Complete Labor Units
CN.2262.T2.ST.1444 | Estimate To Complete Labor Units
CN.2262.T2.ST.1454 | Estimate To Complete Labor Units | 2021-09-25: 12.4
CN.2262.T2.ST.1464 | Estimate To Complete Labor Units
CN.2262.T2.ST.1474 | Estimate To Complete Labor Units
CN.2262.T2.ST.1494 | Estimate To Complete Labor Units | 2021-09-25: 5.97
CN.2262.T2.ST.1504 | Estimate To Complete Labor Units
CN.2262.T2.ST.1514 | Estimate To Complete Labor Units
CN.2262.T2.ST.1524 | Estimate To Complete Labor Units
CN.2262.T2.ST.1534 | Estimate To Complete Labor Units
CN.2262.T2.ST.1544 | Estimate To Complete Labor Units
CN.2262.T2.ST.1554 | Estimate To Complete Labor Units
CN.2262.T2.ST.1564 | Estimate To Complete Labor Units | 2021-09-25: 13.78
CN.2262.T2.ST.1574 | Estimate To Complete Labor Units
CN.2262.T2.ST.1594 | Estimate To Complete Labor Units
CN.2262.T2.ST.1598 | Estimate To Complete Labor Units | 2021-09-25: 76.38
CN.2262.T2.ST.1602 | Estimate To Complete Labor Units | 2021-09-25: 66.14; 2021-10-02: 99.21
CN.2262.T2.ST.1610 | Estimate To Complete Labor Units | 2021-09-25: 124.85; 2021-10-02: 124.85; 2021-10-09: 68.1
CN.2262.T2.ST.1614 | Estimate To Complete Labor Units | 2021-10-30: 208.94; 2021-11-06: 280.29; 2021-11-13: 280.29; 2021-11-20: 280.29; 2021-11-27: 20.38
CN.2262.T2.ST.1615 | Estimate To Complete Labor Units | 2021-09-25: 2.04; 2021-10-02: 1.03
CN.2262.T2.ST.1618 | Estimate To Complete Labor Units | 2021-10-09: 33.02; 2021-10-16: 15.3
CN.2262.T2.ST.1622 | Estimate To Complete Labor Units | 2021-09-25: 44.87; 2021-10-02: 56.09; 2021-10-09: 56.09; 2021-10-16: 56.09; 2021-10-23: 14.28
CN.2262.T2.ST.1625 | Estimate To Complete Labor Units | 2021-10-02: 8.16
CN.2262.T2.ST.1634 | Estimate To Complete Labor Units | 2021-10-02: 22.76
CN.2262.T2.ST.1638 | Estimate To Complete Labor Units | 2021-10-02: 25.92; 2021-10-09: 160.21; 2021-10-16: 160.21; 2021-10-23: 160.21; 2021-10-30: 122.63
CN.2262.T2.ST.1642 | Estimate To Complete Labor Units | 2021-10-30: 26.56
CN.2262.T2.ST.1643 | Estimate To Complete Labor Units | 2021-10-16: 0.74; 2021-10-23: 6.87; 2021-10-30: 6.87; 2021-11-06: 6.87; 2021-11-13: 1.14
CN.2262.T2.ST.1644 | Estimate To Complete Labor Units | 2021-10-30: 11.89; 2021-11-06: 110.8; 2021-11-13: 18.33
CN.2262.T2.ST.1678 | Estimate To Complete Labor Units | 2021-10-23: 77.89; 2021-10-30: 84; 2021-11-06: 84; 2021-11-13: 84; 2021-11-20: 84; 2021-11-27: 6.11
CN.2272.T2.MC.1000 | Estimate To Complete Labor Units
CN.2272.T2.MC.1010 | Estimate To Complete Labor Units
CN.2272.T2.MC.1020 | Estimate To Complete Labor Units
CN.2272.T2.MC.1030 | Estimate To Complete Labor Units | 2021-10-23: 10.97; 2021-10-30: 9.23
CN.2272.T2.MC.1040 | Estimate To Complete Labor Units
CN.2272.T2.MC.1050 | Estimate To Complete Labor Units | 2021-10-16: 133.33; 2021-10-23: 133.33; 2021-10-30: 133.33; 2021-11-06: 82.42
CN.2272.T2.MC.1070 | Estimate To Complete Labor Units | 2021-11-06: 46.44; 2021-11-13: 121.63; 2021-11-20: 61.92
CN.2272.T2.MC.1080 | Estimate To Complete Labor Units
CN.2272.T2.MC.1090 | Estimate To Complete Labor Units
CN.2272.T2.MC.1100 | Estimate To Complete Labor Units | 2021-10-09: 26.09; 2021-10-16: 35.87; 2021-10-23: 11.09
CN.2272.T2.MC.1120 | Estimate To Complete Labor Units
CN.2272.T2.MC.1160 | Estimate To Complete Labor Units | 2021-10-16: 139.58; 2021-10-23: 279.17
CN.2272.T2.MC.1180 | Estimate To Complete Labor Units | 2021-10-23: 156.1; 2021-10-30: 245.3; 2021-11-06: 245.3; 2021-11-13: 13.38
CN.2272.T2.MC.1191 | Estimate To Complete Labor Units | 2021-11-13: 214.48; 2021-11-20: 226.86; 2021-11-27: 164.99
CN.2272.T2.MC.1210 | Estimate To Complete Labor Units
CN.2272.T2.MC.1211 | Estimate To Complete Labor Units | 2021-11-27: 335.76; 2021-12-04: 1007.27
CN.2272.T2.MC.1220 | Estimate To Complete Labor Units
CN.2272.T2.MC.1221 | Estimate To Complete Labor Units | 2021-10-30: 74
CN.2272.T2.MC.1222 | Estimate To Complete Labor Units | 2021-10-30: 6.64; 2021-11-06: 121.7; 2021-11-13: 121.7; 2021-11-20: 77.45
CN.2272.T2.MC.1224 | Estimate To Complete Labor Units | 2022-02-05: 98.42; 2022-02-12: 138.8; 2022-02-19: 58.04
CN.2272.T2.ST.1320 | Estimate To Complete Labor Units
CN.2272.T2.ST.1330 | Estimate To Complete Labor Units
CN.2272.T2.ST.1340 | Estimate To Complete Labor Units
CN.2272.T2.ST.1350 | Estimate To Complete Labor Units
CN.2272.T2.ST.1360 | Estimate To Complete Labor Units
CN.2272.T2.ST.1364 | Estimate To Complete Labor Units
CN.2272.T2.ST.1368 | Estimate To Complete Labor Units
CN.2272.T2.ST.1376 | Estimate To Complete Labor Units
CN.2272.T2.ST.1380 | Estimate To Complete Labor Units
CN.2272.T2.ST.1381 | Estimate To Complete Labor Units | 2021-10-16: 314.58; 2021-10-23: 314.58; 2021-10-30: 314.58; 2021-11-06: 314.58; 2021-11-13: 314.58; 2021-11-20: 68.64
CN.2272.T2.ST.1384 | Estimate To Complete Labor Units
CN.2272.T2.ST.1388 | Estimate To Complete Labor Units | 2021-09-25: 9.52
CN.2272.T2.ST.1392 | Estimate To Complete Labor Units
CN.2272.T2.ST.1396 | Estimate To Complete Labor Units
CN.2272.T2.ST.1400 | Estimate To Complete Labor Units | 2021-10-02: 3.56; 2021-10-09: 0.97
CN.2272.T2.ST.1401 | Estimate To Complete Labor Units | 2021-11-27: 86.27; 2021-12-04: 169.45; 2021-12-11: 113.99
CN.2272.T2.ST.1404 | Estimate To Complete Labor Units | 2021-10-09: 209.9
CN.2272.T2.ST.1408 | Estimate To Complete Labor Units | 2021-10-30: 1.41; 2021-11-06: 3.51; 2021-11-13: 3.51; 2021-11-20: 2.24
CN.2272.T2.ST.1430 | Estimate To Complete Labor Units
CN.2272.T2.ST.1461 | Estimate To Complete Labor Units
CN.2272.T2.ST.1465 | Estimate To Complete Labor Units
CN.2272.T2.ST.1469 | Estimate To Complete Labor Units
CN.2272.T2.ST.1485 | Estimate To Complete Labor Units
CN.2272.T2.ST.1489 | Estimate To Complete Labor Units | 2021-09-25: 116.88
CN.2272.T2.ST.1493 | Estimate To Complete Labor Units | 2021-09-25: 87.45
CN.2272.T2.ST.1497 | Estimate To Complete Labor Units | 2021-09-25: 2.26
CN.2272.T2.ST.1501 | Estimate To Complete Labor Units | 2021-09-25: 7.62; 2021-10-02: 53.33
CN.2272.T2.ST.1505 | Estimate To Complete Labor Units | 2021-10-02: 98.61; 2021-10-09: 49.31
CN.2272.T2.ST.1509 | Estimate To Complete Labor Units | 2021-10-09: 467.07
CN.2272.T2.ST.1513 | Estimate To Complete Labor Units | 2021-10-09: 5.96
CN.2272.T2.ST.1533 | Estimate To Complete Labor Units | 2021-10-16: 56.98; 2021-10-23: 14.25
CN.2272.T2.ST.1537 | Estimate To Complete Labor Units | 2021-10-23: 148.72
CN.2272.T2.ST.1541 | Estimate To Complete Labor Units | 2021-10-23: 20.71
CN.2272.T2.ST.1545 | Estimate To Complete Labor Units | 2021-10-23: 42.01; 2021-10-30: 42.01
CN.2272.T2.ST.1549 | Estimate To Complete Labor Units | 2021-10-30: 72.01
CN.2272.T2.ST.1553 | Estimate To Complete Labor Units | 2021-10-30: 14.98
CN.2272.T2.ST.1565 | Estimate To Complete Labor Units | 2021-11-06: 112.33
CN.2272.T2.ST.1573 | Estimate To Complete Labor Units | 2021-11-06: 449.7
CN.2272.T2.ST.1577 | Estimate To Complete Labor Units | 2021-11-06: 112.42
CN.2272.T2.ST.1581 | Estimate To Complete Labor Units | 2021-12-11: 586.15; 2022-01-01: 1628.19; 2022-01-08: 1335.11
CN.2272.T2.ST.1593 | Estimate To Complete Labor Units | 2022-01-22: 241.42; 2022-01-29: 160.95
CN.2272.T2.ST.1598 | Estimate To Complete Labor Units | 2021-11-13: 28.21; 2021-11-20: 35.32; 2021-11-27: 35.32; 2021-12-04: 11.7
CN.2272.T2.ST.1606 | Estimate To Complete Labor Units | 2021-09-25: 16.05
CN.2272.T2.ST.1618 | Estimate To Complete Labor Units
CN.2272.T2.ST.1622 | Estimate To Complete Labor Units | 2021-10-02: 176.21
CN.2272.T2.ST.1626 | Estimate To Complete Labor Units | 2021-10-09: 39.55; 2021-10-16: 276.83; 2021-10-23: 276.83; 2021-10-30: 276.83; 2021-11-06: 276.83; 2021-11-13: 203.13
CN.2272.T2.ST.1672 | Estimate To Complete Labor Units | 2021-10-23: 22.4; 2021-10-30: 67.19
CN.2272.T2.ST.1674 | Estimate To Complete Labor Units | 2021-10-30: 35.25; 2021-11-06: 17.63
CN.2272.T2.ST.1676 | Estimate To Complete Labor Units | 2021-12-11: 142.33; 2022-01-01: 173.96
CN.4242.T2.IN.1665 | Estimate To Complete Labor Units
CN.4242.T2.PS.1637 | Estimate To Complete Labor Units
CN.4242.T2.PS.1641 | Estimate To Complete Labor Units
CN.4242.T2.PS.1645 | Estimate To Complete Labor Units
CN.4242.T2.PS.1649 | Estimate To Complete Labor Units
CN.4242.T2.PS.1650 | Estimate To Complete Labor Units
CN.4242.T2.PS.1653 | Estimate To Complete Labor Units | 2021-09-25: 38.47
CN.4242.T2.PS.1657 | Estimate To Complete Labor Units
CN.4242.T2.PS.1658 | Estimate To Complete Labor Units | 2021-09-25: 79.4
CN.4242.T2.PS.1661 | Estimate To Complete Labor Units
CN.4242.T2.PS.1663 | Estimate To Complete Labor Units | 2021-09-25: 52.6
CN.4242.T2.ST.1629 | Estimate To Complete Labor Units
CN.4242.T2.ST.1633 | Estimate To Complete Labor Units
CN.4242.T2.WW.1645 | Estimate To Complete Labor Units
CN.4242.T2.WW.1653 | Estimate To Complete Labor Units
CN.4242.T2.WW.1661 | Estimate To Complete Labor Units
CN.4242.T2.WW.1665 | Estimate To Complete Labor Units
CN.4242.T2.WW.1669 | Estimate To Complete Labor Units
CN.4242.T2.WW.1673 | Estimate To Complete Labor Units

## ev
Activity ID | Spreadsheet Field | 2021-05-22 | 2021-05-29 | 2021-06-05 | 2021-06-12 | 2021-06-19 | 2021-06-26 | 2021-07-03 | 2021-07-10 | 2021-07-17 | 2021-07-24 | 2021-07-31 | 2021-08-07 | 2021-08-14 | 2021-08-21 | 2021-08-28 | 2021-09-04 | 2021-09-11 | 2021-09-18
2252-1T2.PI.CS-AIN.1055 | Earned Value Labor Units | 2021-07-24: 0.64; 2021-07-31: 1.76; 2021-08-07: 1.76; 2021-08-14: 1.76; 2021-08-21: 1.76; 2021-08-28: 1.76; 2021-09-04: 1.76; 2021-09-11: 1.76; 2021-09-18: 1.76
2252-1T2.PI.CS-GSL.1006 | Earned Value Labor Units | 2021-08-07: 10.62; 2021-08-14: 29.19; 2021-08-21: 29.19; 2021-08-28: 29.19; 2021-09-04: 29.19; 2021-09-11: 29.19; 2021-09-18: 29.19
2252-1T2.PI.CS-LPB.1022 | Earned Value Labor Units | [7 empty] | 0.92 | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 2.52 | 0.92
2252-1T2.PI.CS-LPB.1029 | Earned Value Labor Units | 2021-08-07: 14.85; 2021-08-14: 40.83; 2021-08-21: 40.83; 2021-08-28: 40.83; 2021-09-04: 40.83; 2021-09-11: 40.83; 2021-09-18: 40.83
2252-1T2.PI.CS-LPB.1046 | Earned Value Labor Units | 2021-08-07: 10.02; 2021-08-14: 18.38; 2021-08-21: 18.38; 2021-08-28: 18.38; 2021-09-04: 18.38; 2021-09-11: 18.38; 2021-09-18: 18.38
2252-1T2.PI.CS-LPB.1047 | Earned Value Labor Units | 2021-07-17: 6.59; 2021-07-24: 18.12; 2021-07-31: 18.12; 2021-08-07: 18.12; 2021-08-14: 18.12; 2021-08-21: 18.12; 2021-08-28: 18.12; 2021-09-04: 18.12; 2021-09-11: 18.12; 2021-09-18: 18.12
2252-1T2.PI.CS-LSH.1048 | Earned Value Labor Units | 2021-07-24: 1.99; 2021-07-31: 5.48; 2021-08-07: 5.48; 2021-08-14: 5.48; 2021-08-21: 5.48; 2021-08-28: 5.48; 2021-09-04: 5.48; 2021-09-11: 5.48; 2021-09-18: 5.48
2252-1T2.PI.CS-WFI.1057 | Earned Value Labor Units | 2021-09-04: 0.93; 2021-09-11: 3.64; 2021-09-18: 3.64
2252-1T2.PI.HDPE-WRO.1060 | Earned Value Labor Units | 2021-09-18: 30.9
2252-1T2.PI.SS-LPB.1019 | Earned Value Labor Units | 2021-08-07: 36.05; 2021-08-14: 99.14; 2021-08-21: 99.14; 2021-08-28: 99.14; 2021-09-04: 99.14; 2021-09-11: 99.14; 2021-09-18: 99.14
2252-1T2.PI.SS-LPB.1025 | Earned Value Labor Units | [7 empty] | 8.67 | 15.89 | 15.89 | 15.89 | 15.89 | 15.89 | 15.89 | 15.89 | 15.89 | 15.89 | 10.11
2252-1T2.PI.SS-LPB.1051 | Earned Value Labor Units | 2021-07-24: 12.84; 2021-07-31: 35.32; 2021-08-07: 35.32; 2021-08-14: 35.32; 2021-08-21: 35.32; 2021-08-28: 35.32; 2021-09-04: 35.32; 2021-09-11: 35.32; 2021-09-18: 35.32
2252-1T2.PI.SS-SPB.1034 | Earned Value Labor Units | 2021-09-04: 11.79; 2021-09-11: 21.62; 2021-09-18: 21.62
2252-1T2.PI.SS-SPB.1052 | Earned Value Labor Units | 2021-08-28: 22.23; 2021-09-04: 40.75; 2021-09-11: 40.75; 2021-09-18: 40.75
2252-1T2.PI.SS-WPO.1060 | Earned Value Labor Units | 2021-08-07: 5.45; 2021-08-14: 14.98; 2021-08-21: 14.98; 2021-08-28: 14.98; 2021-09-04: 14.98; 2021-09-11: 14.98; 2021-09-18: 14.98
2252-1T2.PI.SS-WRO.1053 | Earned Value Labor Units | 2021-08-07: 30.67; 2021-08-14: 42.16; 2021-08-21: 42.16; 2021-08-28: 42.16; 2021-09-04: 42.16; 2021-09-11: 42.16; 2021-09-18: 42.16
2252-1T2.PI.SS-WSC.1021 | Earned Value Labor Units | 2021-08-21: 60.93; 2021-08-28: 167.57; 2021-09-04: 167.57; 2021-09-11: 167.57; 2021-09-18: 167.57
2252-1T2.PI.SS-WSC.1026 | Earned Value Labor Units | 2021-07-24: 2.42; 2021-07-31: 6.65; 2021-08-07: 6.65; 2021-08-14: 6.65; 2021-08-21: 6.65; 2021-08-28: 6.65; 2021-09-04: 6.65; 2021-09-11: 6.65; 2021-09-18: 6.65
2252-1T2.PI.SS-WSC.1054 | Earned Value Labor Units | 2021-07-31: 42.29; 2021-08-07: 46.51; 2021-08-14: 46.51; 2021-08-21: 46.51; 2021-08-28: 46.51; 2021-09-04: 46.51; 2021-09-11: 46.51; 2021-09-18: 46.51
2252-2T2.PI.CS-SPB.1047 | Earned Value Labor Units | 2021-07-24: 7.75; 2021-07-31: 21.31; 2021-08-07: 21.31; 2021-08-14: 21.31; 2021-08-21: 21.31; 2021-08-28: 21.31; 2021-09-04: 21.31; 2021-09-11: 21.31; 2021-09-18: 21.31
2252-2T2.PI.CS-SPB.1061 | Earned Value Labor Units | [7 empty] | 3.72 | 10.24 | 10.24 | 10.24 | 10.24 | 10.24 | 10.24 | 10.24 | 10.24 | 10.24 | 1.71
2252-2T2.PI.CS-SPB.1069 | Earned Value Labor Units | 2021-08-07: 25.63; 2021-08-14: 46.99; 2021-08-21: 46.99; 2021-08-28: 46.99; 2021-09-04: 46.99; 2021-09-11: 46.99; 2021-09-18: 29.9
2252-2T2.PI.SS-LPB.1049 | Earned Value Labor Units | 2021-08-07: 57.74; 2021-08-14: 105.86; 2021-08-21: 105.86; 2021-08-28: 105.86; 2021-09-04: 105.86; 2021-09-11: 105.86; 2021-09-18: 67.36
2252-2T2.PI.SS-LPB.1057 | Earned Value Labor Units | [7 empty] | 2.81 | 7.72 | 7.72 | 7.72 | 7.72 | 7.72 | 7.72 | 7.72 | 7.72 | 7.72 | 7.72
2252-2T2.PI.SS-LPB.1063 | Earned Value Labor Units | 2021-07-17: 9.71; 2021-07-24: 17.8; 2021-07-31: 17.8; 2021-08-07: 17.8; 2021-08-14: 17.8; 2021-08-21: 17.8; 2021-08-28: 17.8; 2021-09-04: 17.8; 2021-09-11: 17.8; 2021-09-18: 17.8
2252-2T2.PI.SS-LPB.1067 | Earned Value Labor Units | 2021-08-07: 1.39; 2021-08-14: 2.55; 2021-08-21: 2.55; 2021-08-28: 2.55; 2021-09-04: 2.55; 2021-09-11: 2.55; 2021-09-18: 1.62
2252-2T2.PI.SS-LPB.1071 | Earned Value Labor Units | 2021-07-17: 34.58; 2021-07-24: 63.4; 2021-07-31: 63.4; 2021-08-07: 63.4; 2021-08-14: 63.4; 2021-08-21: 63.4; 2021-08-28: 63.4; 2021-09-04: 63.4; 2021-09-11: 63.4; 2021-09-18: 63.4
2252-2T2.PI.SS-WSC.1053 | Earned Value Labor Units | 2021-08-07: 7.47; 2021-08-14: 10.27; 2021-08-21: 10.27; 2021-08-28: 10.27; 2021-09-04: 10.27; 2021-09-11: 10.27; 2021-09-18: 10.27
2252-2T2.PI.SS-WSC.1059 | Earned Value Labor Units | 2021-07-17: 1.09; 2021-07-24: 2; 2021-07-31: 2; 2021-08-07: 2; 2021-08-14: 2; 2021-08-21: 2; 2021-08-28: 2; 2021-09-04: 2; 2021-09-11: 2; 2021-09-18: 2
2252-2T2.PI.SS-WSC.1073 | Earned Value Labor Units | 2021-09-04: 45.78; 2021-09-11: 50.35; 2021-09-18: 50.35
2252-3 T2.PI.PS .9161 | Earned Value Labor Units | [7 empty] | 0.68 | 3.74 | 3.74 | 3.74 | 3.74 | 3.74 | 3.74 | 3.74 | 3.74 | 3.74 | 3.74
2252-3 T2.PI.PS .9163 | Earned Value Labor Units |  |  |  | 4.81 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3
2252-3 T2.PI.PS .9165 | Earned Value Labor Units | [5 empty] | 1.31 | 7.21 | 7.21 | 7.21 | 7.21 | 7.21 | 7.21 | 7.21 | 7.21 | 7.21 | 7.21 | 7.21 | 7.21
2252-3 T2.PI.PS .9167 | Earned Value Labor Units | [6 empty] | 0.41 | 2.24 | 2.24 | 2.24 | 2.24 | 2.24 | 2.24 | 2.24 | 2.24 | 2.24 | 2.24 | 2.24
2252-3 T2.PI.PS .9169 | Earned Value Labor Units | 2021-09-18: 12.09
2252-3 T2.PI.PS .9171 | Earned Value Labor Units | 2021-09-18: 2.45
2252-3 T2.PI.PS .9173 | Earned Value Labor Units | 2021-09-18: 5.07
2252-3 T2.PI.PS .9175 | Earned Value Labor Units | 2021-09-18: 7.38
2252-3 T2.PI.SS-GSL. 9162 | Earned Value Labor Units | 2021-08-14: 11.08; 2021-08-21: 20.32; 2021-08-28: 20.32; 2021-09-04: 20.32; 2021-09-11: 20.32; 2021-09-18: 20.32
2252-3 T2.PI.SS-LPB. 9167 | Earned Value Labor Units | 2021-09-04: 3.06; 2021-09-11: 8.41; 2021-09-18: 8.41
2252-3 T2.PI.SS-LPB. 9270 | Earned Value Labor Units | 2021-09-04: 26.66; 2021-09-11: 146.61; 2021-09-18: 146.61
2252-3 T2.PI.SS-SPB. 9157 | Earned Value Labor Units | 2021-08-07: 6.42; 2021-08-14: 17.65; 2021-08-21: 17.65; 2021-08-28: 17.65; 2021-09-04: 17.65; 2021-09-11: 17.65; 2021-09-18: 17.65
2252-3 T2.PI.SS-WGS. 9159 | Earned Value Labor Units | 2021-08-07: 16.13; 2021-08-14: 44.36; 2021-08-21: 44.36; 2021-08-28: 44.36; 2021-09-04: 44.36; 2021-09-11: 44.36; 2021-09-18: 44.36
2252-3 T2.PI.SS-WRO. 9160 | Earned Value Labor Units | 2021-09-18: 101.4
2252-3 T2.PI.SS-WSC. 9162 | Earned Value Labor Units | 2021-08-07: 19.14; 2021-08-14: 52.65; 2021-08-21: 52.65; 2021-08-28: 52.65; 2021-09-04: 52.65; 2021-09-11: 52.65; 2021-09-18: 52.65
2252-3 T2.PI.SS-WSC. 9178 | Earned Value Labor Units | 2021-09-04: 20.35; 2021-09-11: 55.96; 2021-09-18: 55.96
2252-3 T2.PI.SS-WSC. 9180 | Earned Value Labor Units | 2021-09-04: 2.59; 2021-09-11: 7.11; 2021-09-18: 7.11
2252-3 T2.PI.SS-WSC. 9276 | Earned Value Labor Units | 2021-09-11: 2.62; 2021-09-18: 7.2
2252-4T2.PI.CS-LPB.1081 | Earned Value Labor Units | 2021-07-24: 4.4; 2021-07-31: 24.18; 2021-08-07: 24.18; 2021-08-14: 24.18; 2021-08-21: 24.18; 2021-08-28: 24.18; 2021-09-04: 24.18; 2021-09-11: 21.76
2252-4T2.PI.CS-LPB.1085 | Earned Value Labor Units | 2021-09-04: 2.52; 2021-09-11: 3.46; 2021-09-18: 3.46
2252-4T2.PI.CS-LPB.1087 | Earned Value Labor Units | 2021-09-11: 65.91; 2021-09-18: 230.7
2252-4T2.PI.SS-LPB.1092 | Earned Value Labor Units | 2021-09-18: 24.61
2252-4T2.PI.SS-WSC.1079 | Earned Value Labor Units | 2021-07-31: 34.06; 2021-08-07: 46.83; 2021-08-14: 46.83; 2021-08-21: 46.83; 2021-08-28: 46.83; 2021-09-04: 46.83; 2021-09-11: 46.83; 2021-09-18: 46.83
2252-4T2.PI.SS-WSC.1083 | Earned Value Labor Units | 2021-07-24: 0.87; 2021-07-31: 4.79; 2021-08-07: 4.79; 2021-08-14: 4.79; 2021-08-21: 4.79; 2021-08-28: 4.79; 2021-09-04: 4.79; 2021-09-11: 4.79; 2021-09-18: 4.79
2262-1T2.PI.CS-AIN.9207 | Earned Value Labor Units | 2021-07-31: 1.04; 2021-08-07: 1.42; 2021-08-14: 1.42; 2021-08-21: 1.42; 2021-08-28: 1.42; 2021-09-04: 1.42; 2021-09-11: 1.42; 2021-09-18: 1.42
2262-1T2.PI.CS-LPB.9235 | Earned Value Labor Units | 2021-09-04: 36.98; 2021-09-11: 67.8; 2021-09-18: 67.8
2262-1T2.PI.HDPE-WCW.9239 | Earned Value Labor Units | 2021-08-28: 101.77; 2021-09-04: 111.94; 2021-09-11: 111.94; 2021-09-18: 111.94
2262-1T2.PI.HDPE-WCW.9259 | Earned Value Labor Units | 2021-08-28: 2.48; 2021-09-04: 6.81; 2021-09-11: 6.81; 2021-09-18: 6.81
2262-1T2.PI.HDPE-WRO.9291 | Earned Value Labor Units | 2021-09-11: 82.8; 2021-09-18: 227.71
2262-1T2.PI.SS-GVE.9195 | Earned Value Labor Units | 2021-09-04: 23.19; 2021-09-11: 25.51; 2021-09-18: 25.51
2262-1T2.PI.SS-LPB.9199 | Earned Value Labor Units | [7 empty] | 14.63 | 26.82 | 26.82 | 26.82 | 26.82 | 26.82 | 26.82 | 26.82 | 26.82 | 26.82 | 26.82
2262-1T2.PI.SS-LPB.9251 | Earned Value Labor Units | 2021-06-26: 5.44; 2021-07-03: 14.95; 2021-07-10: 14.95; 2021-07-17: 9.51
2262-1T2.PI.SS-LPB.9267 | Earned Value Labor Units | 2021-08-28: 28.51; 2021-09-04: 156.82; 2021-09-11: 156.82; 2021-09-18: 156.82
2262-1T2.PI.SS-SPB.9207 | Earned Value Labor Units | 2021-08-07: 48.77; 2021-08-14: 53.64; 2021-08-21: 53.64; 2021-08-28: 53.64; 2021-09-04: 53.64; 2021-09-11: 53.64; 2021-09-18: 53.64
2262-1T2.PI.SS-SPB.9219 | Earned Value Labor Units | 2021-09-11: 120.01; 2021-09-18: 132.01
2262-1T2.PI.SS-SPB.9271 | Earned Value Labor Units | 2021-07-31: 26.12; 2021-08-07: 35.92; 2021-08-14: 35.92; 2021-08-21: 35.92; 2021-08-28: 35.92; 2021-09-04: 35.92; 2021-09-11: 35.92; 2021-09-18: 35.92
2262-1T2.PI.SS-WPO.9303 | Earned Value Labor Units | 2021-08-21: 127.47; 2021-08-28: 233.7; 2021-09-04: 233.7; 2021-09-11: 233.7; 2021-09-18: 233.7
2262-1T2.PI.SS-WRO.9295 | Earned Value Labor Units | 2021-09-04: 14.82
2262-1T2.PI.SS-WRO.9311 | Earned Value Labor Units | 2021-08-28: 3.68; 2021-09-04: 6.74; 2021-09-11: 6.74; 2021-09-18: 6.74
2262-1T2.PI.SS-WSC.9211 | Earned Value Labor Units | 2021-08-21: 19.01; 2021-08-28: 104.56; 2021-09-04: 104.56; 2021-09-11: 104.56; 2021-09-18: 104.56
2262-1T2.PI.SS-WSC.9223 | Earned Value Labor Units | 2021-08-07: 15.33; 2021-08-14: 28.11; 2021-08-21: 28.11; 2021-08-28: 28.11; 2021-09-04: 28.11; 2021-09-11: 28.11; 2021-09-18: 28.11
2262-1T2.PI.SS-WSC.9231 | Earned Value Labor Units | 2021-07-24: 13.52; 2021-07-31: 37.19; 2021-08-07: 37.19; 2021-08-14: 37.19; 2021-08-21: 37.19; 2021-08-28: 37.19; 2021-09-04: 37.19; 2021-09-11: 37.19; 2021-09-18: 37.19
2262-1T2.PI.SS-WSC.9247 | Earned Value Labor Units | 2021-07-17: 101.35; 2021-07-24: 111.49; 2021-07-31: 111.49; 2021-08-07: 111.49; 2021-08-14: 111.49; 2021-08-21: 111.49; 2021-08-28: 111.49; 2021-09-04: 111.49; 2021-09-11: 111.49; 2021-09-18: 111.49
2262-1T2.PI.SS-WSC.9255 | Earned Value Labor Units | 2021-06-26: 11.2; 2021-07-03: 30.81; 2021-07-10: 30.81; 2021-07-17: 19.6
2262-1T2.PI.SS-WSC.9263 | Earned Value Labor Units | 2021-08-21: 1.09; 2021-08-28: 2.99; 2021-09-04: 2.99; 2021-09-11: 2.99; 2021-09-18: 2.99
2262-1T2.PI.SS-WSC.9275 | Earned Value Labor Units | 2021-08-28: 8.16; 2021-09-04: 22.45; 2021-09-11: 22.45; 2021-09-18: 22.45
2262-2 T2.PI.SS-GSL. 9367 | Earned Value Labor Units | 2021-09-11: 13.89; 2021-09-18: 38.19
2262-2 T2.PI.SS-GSL. 9368 | Earned Value Labor Units | 2021-09-04: 39.52; 2021-09-11: 72.46; 2021-09-18: 72.46
2262-2 T2.PI.SS-GSL. 9369 | Earned Value Labor Units | 2021-08-21: 6.74; 2021-08-28: 18.54; 2021-09-04: 18.54; 2021-09-11: 18.54; 2021-09-18: 18.54
2262-2 T2.PI.SS-GVE. 9369 | Earned Value Labor Units | 2021-09-04: 11.38; 2021-09-11: 31.29; 2021-09-18: 31.29
2262-2 T2.PI.SS-GVE. 9371 | Earned Value Labor Units | 2021-09-04: 9.29; 2021-09-11: 17.02; 2021-09-18: 17.02
2262-2 T2.PI.SS-LPB. 9471 | Earned Value Labor Units | 2021-08-07: 2.41; 2021-08-14: 10.18; 2021-08-21: 10.18; 2021-08-28: 10.18; 2021-09-04: 10.18; 2021-09-11: 10.18; 2021-09-18: 10.18
2262-2 T2.PI.SS-LPB. 9474 | Earned Value Labor Units | 2021-09-11: 18.81; 2021-09-18: 20.69
2262-2 T2.PI.SS-SPB. 9173 | Earned Value Labor Units | 2021-07-31: 14.89; 2021-08-07: 27.3; 2021-08-14: 27.3; 2021-08-21: 27.3; 2021-08-28: 27.3; 2021-09-04: 27.3; 2021-09-11: 27.3; 2021-09-18: 27.3
2262-2 T2.PI.SS-WCW. 9375 | Earned Value Labor Units | 2021-08-21: 20.84; 2021-08-28: 28.66; 2021-09-04: 28.66; 2021-09-11: 28.66; 2021-09-18: 28.66
2262-2 T2.PI.SS-WCW. 9376 | Earned Value Labor Units | 2021-09-11: 39.44
2262-2 T2.PI.SS-WGS. 9160 | Earned Value Labor Units | 2021-07-31: 150.54; 2021-08-07: 207; 2021-08-14: 207; 2021-08-21: 131.72
2262-2 T2.PI.SS-WSC. 9379 | Earned Value Labor Units | 2021-07-31: 35.49; 2021-08-07: 97.6; 2021-08-14: 97.6; 2021-08-21: 97.6; 2021-08-28: 97.6; 2021-09-04: 97.6; 2021-09-11: 97.6; 2021-09-18: 97.6
2262-2 T2.PI.SS-WSC. 9380 | Earned Value Labor Units | 2021-09-04: 3.21; 2021-09-11: 3.53; 2021-09-18: 3.53
2262-2 T2.PI.SS-WSC. 9381 | Earned Value Labor Units | 2021-09-04: 96.01; 2021-09-11: 105.61; 2021-09-18: 105.61
2262-2 T2.PI.SS-WSC. 9382 | Earned Value Labor Units | 2021-09-18: 36.73
2262-2.T2.PI.HDPE-WCW.80 | Earned Value Labor Units | 2021-08-21: 4.42; 2021-08-28: 12.15; 2021-09-04: 12.15; 2021-09-11: 12.15; 2021-09-18: 12.15
2262-2.T2.PI.SS-WPO.9650 | Earned Value Labor Units | 2021-09-04: 28.18; 2021-09-11: 51.66; 2021-09-18: 51.66
2262-3.T2.PI.CS-GSL.1394 | Earned Value Labor Units | 2021-09-04: 0.55; 2021-09-11: 1.2; 2021-09-18: 1.2
2262-3.T2.PI.CS-GSL.1426 | Earned Value Labor Units | 2021-09-18: 32.58
2262-3.T2.PI.CS-GSL.1438 | Earned Value Labor Units | 2021-07-24: 20.54; 2021-07-31: 37.67; 2021-08-07: 37.67; 2021-08-14: 37.67; 2021-08-21: 37.67; 2021-08-28: 37.67; 2021-09-04: 37.67; 2021-09-11: 37.67; 2021-09-18: 37.67
2262-3.T2.PI.CS-LPB.1442 | Earned Value Labor Units | 2021-09-11: 14.26; 2021-09-18: 34.87
2262-3.T2.PI.HDPE-WR.1440 | Earned Value Labor Units | 2021-09-18: 25.62
2262-3.T2.PI.PS.1434 | Earned Value Labor Units | 2021-08-14: 2.1; 2021-08-21: 5.78; 2021-08-28: 5.78; 2021-09-04: 5.78; 2021-09-11: 5.78; 2021-09-18: 5.78
2262-3.T2.PI.SS-LPB.1430 | Earned Value Labor Units | 2021-09-11: 13.42; 2021-09-18: 13.42
2262-3.T2.PI.SS-SPB.1458 | Earned Value Labor Units | 2021-08-07: 21.93; 2021-08-14: 24.12; 2021-08-21: 24.12; 2021-08-28: 24.12; 2021-09-04: 24.12; 2021-09-11: 24.12; 2021-09-18: 24.12
2262-3.T2.PI.SS-WSC.1422 | Earned Value Labor Units | 2021-09-04: 87.66; 2021-09-11: 96.42; 2021-09-18: 96.42
2262-3.T2.PI.SS-WSC.1434 | Earned Value Labor Units | 2021-09-11: 10.62; 2021-09-18: 13.74
2272-2.T2.PI.1140 | Earned Value Labor Units | 2021-07-24: 1.97; 2021-07-31: 3.61; 2021-08-07: 3.61; 2021-08-14: 3.61; 2021-08-21: 3.61; 2021-08-28: 3.61; 2021-09-04: 3.61; 2021-09-11: 3.61; 2021-09-18: 3.61
4242.T2.PI.CS-AIN.1663 | Earned Value Labor Units | 2021-06-12: 17.85; 2021-06-19: 19.63; 2021-06-26: 5.35
4242.T2.PI.CS-AIN.1681 | Earned Value Labor Units | 2021-06-05: 4.25; 2021-06-12: 7.3; 2021-06-19: 7.3; 2021-06-26: 5.97
4242.T2.PI.CS-AIN.1701 | Earned Value Labor Units | 2021-06-12: 6.15; 2021-06-19: 17.79; 2021-06-26: 17.79; 2021-07-03: 1.62
4242.T2.PI.CS-AIN.1802 | Earned Value Labor Units | 2021-07-17: 14.81
4242.T2.PI.CS-AIN.1820 | Earned Value Labor Units | 2021-06-19: 10.1; 2021-06-26: 18.52; 2021-07-03: 8.42
4242.T2.PI.CS-AIN.1842 | Earned Value Labor Units | 2021-06-12: 7.33; 2021-06-19: 13.44; 2021-06-26: 13.44; 2021-07-03: 1.22
4242.T2.PI.CS-GCD.1665 | Earned Value Labor Units | 2021-06-12: 31.51
4242.T2.PI.CS-GCD.1683 | Earned Value Labor Units | 2021-06-05: 22.79
4242.T2.PI.CS-GCD.1703 | Earned Value Labor Units | 2021-06-12: 19.31
4242.T2.PI.CS-GSL.1705 | Earned Value Labor Units | 2021-06-05: 17.38; 2021-06-12: 23.9; 2021-06-19: 15.21
4242.T2.PI.CS-GSL.1856 | Earned Value Labor Units | 2021-06-19: 197.45
4242.T2.PI.CS-LPB.1685 | Earned Value Labor Units | 2021-06-05: 33.29
4242.T2.PI.CS-LPB.1707 | Earned Value Labor Units | 2021-06-05: 27.12; 2021-06-12: 47.45
4242.T2.PI.CS-LPB.1804 | Earned Value Labor Units | 2021-06-12: 12.36; 2021-06-19: 16.99; 2021-06-26: 16.99; 2021-07-03: 10.81
4242.T2.PI.CS-LPB.1822 | Earned Value Labor Units | 2021-06-12: 62.47
4242.T2.PI.CS-LSH.1709 | Earned Value Labor Units | 2021-06-12: 19.04
4242.T2.PI.CS-LSH.1824 | Earned Value Labor Units | 2021-06-12: 37.08
4242.T2.PI.CS-LSH.1844 | Earned Value Labor Units | 2021-06-12: 7.67; 2021-06-19: 14.06; 2021-06-26: 14.06; 2021-07-03: 1.28
4242.T2.PI.CS-SPB.1711 | Earned Value Labor Units | 2021-06-12: 6.92; 2021-06-19: 12.12
4242.T2.PI.CS-SPB.1808 | Earned Value Labor Units | 2021-06-19: 35.55
4242.T2.PI.CS-SPB.1826 | Earned Value Labor Units | 2021-06-19: 18.08
4242.T2.PI.FRP-LPA.1667 | Earned Value Labor Units | 2021-09-11: 14.86; 2021-09-18: 26.76
4242.T2.PI.FRP-LPA.1687 | Earned Value Labor Units | 2021-09-18: 30.81
4242.T2.PI.FRP-LPA.1810 | Earned Value Labor Units | 2021-09-18: 19.5
4242.T2.PI.FRP-LPA.1828 | Earned Value Labor Units | 2021-09-18: 19.5
4242.T2.PI.FRP-LPA.1846 | Earned Value Labor Units | 2021-09-11: 12.19; 2021-09-18: 7.31
4242.T2.PI.FRP-LSD.1830 | Earned Value Labor Units | 2021-09-18: 38.99
4242.T2.PI.FRP-LSD.1848 | Earned Value Labor Units | 2021-09-18: 12.18
4242.T2.PI.HDPE-WCW.1671 | Earned Value Labor Units | 2021-06-26: 6.25
4242.T2.PI.HDPE-WPO.1673 | Earned Value Labor Units | 2021-06-26: 41.67
4242.T2.PI.HDPE-WPO.1812 | Earned Value Labor Units | 2021-07-10: 23.38
4242.T2.PI.HDPE-WPO.1832 | Earned Value Labor Units | 2021-06-26: 18.71; 2021-07-03: 28.06
4242.T2.PI.HDPE-WPO.1850 | Earned Value Labor Units | 2021-06-19: 6.31; 2021-06-26: 34.71; 2021-07-03: 3.15
4242.T2.PI.HDPE-WRA.1812 | Earned Value Labor Units | 2021-07-10: 8.26
4242.T2.PI.HDPE-WRA.1834 | Earned Value Labor Units | 2021-07-03: 8.26
4242.T2.PI.HDPE-WRA.1852 | Earned Value Labor Units | 2021-07-03: 12.72
4242.T2.PI.HDPE-WRO.1675 | Earned Value Labor Units | 2021-06-19: 13.72; 2021-06-26: 20.58
4242.T2.PI.HDPE-WRO.1814 | Earned Value Labor Units | 2021-07-10: 11.69
4242.T2.PI.HDPE-WRO.1836 | Earned Value Labor Units | 2021-07-03: 26.63
4242.T2.PI.SS-LPB.1677 | Earned Value Labor Units | 2021-06-12: 36.3
4242.T2.PI.SS-LPB.1697 | Earned Value Labor Units | 2021-06-05: 18.91; 2021-06-12: 33.1
4242.T2.PI.SS-LPB.1718 | Earned Value Labor Units | 2021-06-12: 19.25; 2021-06-19: 33.7
4242.T2.PI.SS-LPB.1816 | Earned Value Labor Units | 2021-06-19: 9.66
4242.T2.PI.SS-LPB.1838 | Earned Value Labor Units | 2021-06-19: 9.66
4242.T2.PI.SS-WSC.1679 | Earned Value Labor Units | 2021-06-12: 55.73
4242.T2.PI.SS-WSC.1699 | Earned Value Labor Units | 2021-06-05: 37.74
4242.T2.PI.SS-WSC.1720 | Earned Value Labor Units | 2021-06-12: 22.53; 2021-06-19: 39.43
4242.T2.PI.SS-WSC.1818 | Earned Value Labor Units | 2021-07-03: 23.37
4242.T2.PI.SS-WSC.1840 | Earned Value Labor Units | 2021-06-19: 30.03
4242.T2.PI.SS-WSC.1854 | Earned Value Labor Units | 2021-06-12: 51.6
CN.2252-1.T2.CV.1000 | Earned Value Labor Units | [5 empty] | 1.57 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87 | 2.87
CN.2252-1.T2.MC.1000 | Earned Value Labor Units |  |  |  |  | 1.7 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68 | 4.68 | 2.98
CN.2252-1.T2.MC.1010 | Earned Value Labor Units |  |  |  | 2.15 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93
CN.2252-1.T2.MC.1030 | Earned Value Labor Units |  |  |  | 2.74 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77 | 3.77
CN.2252-1.T2.MC.1040 | Earned Value Labor Units | 2021-06-26: 10.25; 2021-07-03: 11.28; 2021-07-10: 11.28; 2021-07-17: 11.28; 2021-07-24: 7.18
CN.2252-1.T2.MC.1050 | Earned Value Labor Units |  |  |  | 1.45 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98 | 3.98
CN.2252-1.T2.MC.1060 | Earned Value Labor Units | 2021-07-17: 29.56; 2021-07-24: 54.2; 2021-07-31: 34.49
CN.2252-1.T2.MC.1070 | Earned Value Labor Units |  |  |  | 2.15 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93 | 3.93
CN.2252-1.T2.MC.1090 | Earned Value Labor Units |  |  |  | 2.54 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79 | 2.79
CN.2252-1.T2.MC.1140 | Earned Value Labor Units |  |  |  |  | 11.28 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51 | 15.51
CN.2252-1.T2.MC.1150 | Earned Value Labor Units |  |  |  | 5.97 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42 | 16.42
CN.2252-1.T2.MC.1180 | Earned Value Labor Units | 2021-07-17: 424; 2021-07-24: 371
CN.2252-1.T2.MC.1190 | Earned Value Labor Units | [5 empty] | 1.34 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45 | 2.45
CN.2252-1.T2.MC.1210 | Earned Value Labor Units | 2021-07-17: 252.27; 2021-07-24: 220.73
CN.2252-1.T2.MC.1230 | Earned Value Labor Units | 2021-09-18: 65.6
CN.2252-1.T2.MC.1260 | Earned Value Labor Units | [5 empty] | 4.56 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02 | 5.02
CN.2252-1.T2.MC.1280 | Earned Value Labor Units |  |  |  | 2.9 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96 | 7.96
CN.2252-1.T2.MC.1295 | Earned Value Labor Units | 2021-09-18: 27.6
CN.2252-1.T2.MC.1483 | Earned Value Labor Units |  |  |  |  | 4.34 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97
CN.2252-1.T2.MC.1582 | Earned Value Labor Units |  |  |  |  | 11.19 | 20.52 | 20.52 | 20.52 | 20.52 | 20.52 | 20.52 | 20.52 | 20.52 | 20.52 | 20.52 | 20.52 | 20.52 | 20.52
CN.2252-1.T2.PL.11102 | Earned Value Labor Units | 2021-06-12: 3.7; 2021-06-19: 5.09; 2021-06-26: 5.09; 2021-07-03: 5.09; 2021-07-10: 5.09; 2021-07-17: 2.31
CN.2252-1.T2.PL.11106 | Earned Value Labor Units | 2021-06-12: 4.37; 2021-06-19: 12.03; 2021-06-26: 12.03; 2021-07-03: 12.03; 2021-07-10: 12.03; 2021-07-17: 7.65
CN.2252-1.T2.PL.11110 | Earned Value Labor Units |  |  |  | 1.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 2.01
CN.2252-1.T2.PL.11114 | Earned Value Labor Units |  |  |  | 2.29 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 6.31 | 4.01
CN.2252-1.T2.PL.11118 | Earned Value Labor Units |  |  |  | 3.39 | 6.22 | 6.22 | 6.22 | 6.22 | 6.22 | 6.22 | 6.22 | 6.22 | 6.22 | 6.22 | 6.22 | 6.22 | 3.96
CN.2252-1.T2.PL.11122 | Earned Value Labor Units |  |  |  |  | 2.8 | 7.69 | 7.69 | 7.69 | 7.69 | 7.69 | 7.69 | 7.69 | 7.69 | 7.69 | 7.69 | 7.69 | 4.89
CN.2252-1.T2.PL.11126 | Earned Value Labor Units | 2021-07-10: 69.55; 2021-07-17: 121.7
CN.2252-1.T2.PL.1188 | Earned Value Labor Units | 2021-06-05: 0.96; 2021-06-12: 5.28; 2021-06-19: 5.28; 2021-06-26: 5.28; 2021-07-03: 5.28; 2021-07-10: 4.32
CN.2252-1.T2.PL.1192 | Earned Value Labor Units | 2021-06-12: 5.18; 2021-06-19: 5.18; 2021-06-26: 5.18; 2021-07-03: 5.18; 2021-07-10: 5.18; 2021-07-17: 0.47
CN.2252-1.T2.PL.1196 | Earned Value Labor Units | 2021-06-12: 4.63; 2021-06-19: 5.09; 2021-06-26: 5.09; 2021-07-03: 5.09; 2021-07-10: 5.09; 2021-07-17: 1.39
CN.2252-1.T2.ST.1338 | Earned Value Labor Units | 2021-05-29: 119.61; 2021-06-05: 153.79
CN.2252-1.T2.ST.1342 | Earned Value Labor Units | 2021-05-29: 142.16; 2021-06-05: 260.62; 2021-06-12: 23.69
CN.2252-1.T2.ST.1346 | Earned Value Labor Units | 2021-05-29: 35.51; 2021-06-05: 97.65; 2021-06-12: 8.88
CN.2252-1.T2.ST.1350 | Earned Value Labor Units | 2021-05-29: 11.32; 2021-06-05: 62.26; 2021-06-12: 16.98
CN.2252-1.T2.ST.1354 | Earned Value Labor Units | 2021-06-05: 100.41; 2021-06-12: 45.64
CN.2252-1.T2.ST.1358 | Earned Value Labor Units | 2021-06-05: 187.75; 2021-06-12: 123.91
CN.2252-1.T2.ST.1362 | Earned Value Labor Units |  |  | 6.24 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59 | 8.59
CN.2252-1.T2.ST.1366 | Earned Value Labor Units | 2021-06-05: 114.28; 2021-06-12: 133.33
CN.2252-1.T2.ST.1370 | Earned Value Labor Units | 2021-06-12: 37.87; 2021-06-19: 28.4
CN.2252-1.T2.ST.1374 | Earned Value Labor Units | 2021-06-19: 660.13
CN.2252-1.T2.ST.1378 | Earned Value Labor Units | 2021-06-19: 312.93
CN.2252-1.T2.ST.1382 | Earned Value Labor Units | 2021-06-19: 460.16
CN.2252-1.T2.ST.1386 | Earned Value Labor Units | 2021-06-26: 457.49
CN.2252-1.T2.ST.1390 | Earned Value Labor Units | 2021-06-12: 27.01; 2021-06-19: 74.26; 2021-06-26: 74.26; 2021-07-03: 74.26; 2021-07-10: 74.26; 2021-07-17: 74.26; 2021-07-24: 6.75
CN.2252-1.T2.ST.1394 | Earned Value Labor Units | 2021-07-03: 41.73; 2021-07-10: 45.9; 2021-07-17: 45.9; 2021-07-24: 45.9; 2021-07-31: 45.9; 2021-08-07: 45.9; 2021-08-14: 45.9; 2021-08-21: 45.9; 2021-08-28: 29.21
CN.2252-1.T2.ST.1398 | Earned Value Labor Units | 2021-08-07: 18.83; 2021-08-14: 51.78; 2021-08-21: 32.95
CN.2252-1.T2.ST.1399 | Earned Value Labor Units | 2021-08-14: 381.59
CN.2252-1.T2.ST.1402 | Earned Value Labor Units | 2021-08-21: 7.84
CN.2252-1.T2.ST.1406 | Earned Value Labor Units | 2021-08-21: 260.48
CN.2252-1.T2.ST.1410 | Earned Value Labor Units | 2021-08-28: 11.57
CN.2252-1.T2.ST.1414 | Earned Value Labor Units | 2021-08-21: 64.35; 2021-08-28: 225.22
CN.2252-1.T2.ST.1418 | Earned Value Labor Units | 2021-08-28: 38.18
CN.2252-1.T2.ST.1422 | Earned Value Labor Units | 2021-08-21: 70.31; 2021-08-28: 246.09
CN.2252-1.T2.ST.1430 | Earned Value Labor Units | 2021-09-04: 132.18
CN.2252-1.T2.ST.1434 | Earned Value Labor Units | 2021-09-04: 189.3
CN.2252-1.T2.ST.1438 | Earned Value Labor Units | 2021-09-11: 107.63; 2021-09-18: 56.16
CN.2252-1.T2.ST.1442 | Earned Value Labor Units | 2021-09-11: 105.23; 2021-09-18: 63.63
CN.2252-1.T2.ST.1446 | Earned Value Labor Units | 2021-06-26: 4.46; 2021-07-03: 8.17; 2021-07-10: 8.17; 2021-07-17: 8.17; 2021-07-24: 5.2
CN.2252-1.T2.ST.1454 | Earned Value Labor Units | 2021-06-19: 66.16; 2021-06-26: 33.08
CN.2252-1.T2.ST.1458 | Earned Value Labor Units | 2021-06-19: 22.04; 2021-06-26: 40.4; 2021-07-03: 40.4; 2021-07-10: 40.4; 2021-07-17: 25.71
CN.2252-1.T2.ST.1462 | Earned Value Labor Units | 2021-06-26: 11.18; 2021-07-03: 30.73; 2021-07-10: 30.73; 2021-07-17: 19.56
CN.2252-1.T2.ST.1466 | Earned Value Labor Units | 2021-06-26: 17.1; 2021-07-03: 47.03; 2021-07-10: 47.03; 2021-07-17: 47.03; 2021-07-24: 29.93
CN.2252-1.T2.ST.1470 | Earned Value Labor Units | 2021-06-19: 156.43; 2021-06-26: 215.1; 2021-07-03: 215.1; 2021-07-10: 136.88
CN.2252-1.T2.ST.1474 | Earned Value Labor Units | 2021-06-19: 62.81; 2021-06-26: 86.36; 2021-07-03: 86.36; 2021-07-10: 54.96
CN.2252-1.T2.ST.1478 | Earned Value Labor Units | 2021-06-19: 119.24; 2021-06-26: 163.96; 2021-07-03: 163.96; 2021-07-10: 104.34
CN.2252-1.T2.ST.1482 | Earned Value Labor Units | 2021-07-03: 56.12; 2021-07-10: 154.33; 2021-07-17: 154.33; 2021-07-24: 98.21
CN.2252-1.T2.ST.1486 | Earned Value Labor Units | 2021-07-24: 22.15; 2021-07-31: 121.84; 2021-08-07: 121.84; 2021-08-14: 77.54
CN.2252-1.T2.ST.1490 | Earned Value Labor Units | 2021-08-07: 22.94; 2021-08-14: 31.54; 2021-08-21: 31.54; 2021-08-28: 31.54; 2021-09-04: 31.54; 2021-09-11: 31.54; 2021-09-18: 31.54
CN.2252-1.T2.ST.1494 | Earned Value Labor Units | 2021-08-21: 14.49; 2021-08-28: 39.85; 2021-09-04: 39.85; 2021-09-11: 39.85; 2021-09-18: 39.85
CN.2252-1.T2.ST.1498 | Earned Value Labor Units | 2021-08-28: 33.35; 2021-09-04: 45.86; 2021-09-11: 45.86; 2021-09-18: 45.86
CN.2252-1.T2.ST.1502 | Earned Value Labor Units | [5 empty] | 9.49 | 13.05 | 13.05 | 13.05 | 13.05 | 13.05 | 13.05 | 13.05 | 13.05 | 13.05 | 13.05 | 13.05 | 13.05
CN.2252-1.T2.ST.1506 | Earned Value Labor Units | 2021-08-21: 107.19; 2021-08-28: 147.39; 2021-09-04: 147.39; 2021-09-11: 147.39; 2021-09-18: 147.39
CN.2252-1.T2.ST.1510 | Earned Value Labor Units | [5 empty] | 2.56 | 7.04 | 7.04 | 7.04 | 7.04 | 7.04 | 7.04 | 7.04 | 7.04 | 7.04 | 7.04 | 7.04 | 7.04
CN.2252-2.T2.MC.1000 | Earned Value Labor Units | 2021-08-28: 121.18; 2021-09-04: 133.3; 2021-09-11: 133.3; 2021-09-18: 133.3
CN.2252-2.T2.MC.1020 | Earned Value Labor Units |  |  |  |  | 1.63 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97 | 5.97
CN.2252-2.T2.MC.1030 | Earned Value Labor Units |  |  | 8.83 | 24.29 | 24.29 | 24.29 | 24.29 | 24.29 | 24.29 | 24.29 | 24.29 | 24.29 | 24.29 | 24.29 | 24.29 | 24.29 | 22.52
CN.2252-2.T2.MC.1040 | Earned Value Labor Units |  |  |  |  | 2.52 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 | 6.94 | 2.17
CN.2252-2.T2.MC.1050 | Earned Value Labor Units |  |  |  |  | 0.6 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65
CN.2252-2.T2.MC.1053 | Earned Value Labor Units | 2021-07-03: 18.73; 2021-07-10: 32.77
CN.2252-2.T2.MC.1054 | Earned Value Labor Units | 2021-09-04: 4.98; 2021-09-11: 13.71; 2021-09-18: 13.71
CN.2252-2.T2.PI.1092 | Earned Value Labor Units | 2021-09-18: 208.12
CN.2252-2.T2.ST.1230 | Earned Value Labor Units | 2021-06-05: 487.58
CN.2252-2.T2.ST.1240 | Earned Value Labor Units | 2021-06-12: 348.8
CN.2252-2.T2.ST.1250 | Earned Value Labor Units | 2021-06-12: 205.14
CN.2252-2.T2.ST.1260 | Earned Value Labor Units | 2021-06-12: 40.27; 2021-06-19: 30.21
CN.2252-2.T2.ST.1270 | Earned Value Labor Units | 2021-06-19: 6.13
CN.2252-2.T2.ST.1280 | Earned Value Labor Units | 2021-06-19: 109.81
CN.2252-2.T2.ST.1290 | Earned Value Labor Units | 2021-06-12: 188.25
CN.2252-2.T2.ST.1300 | Earned Value Labor Units | 2021-06-12: 39.25; 2021-06-19: 68.69
CN.2252-2.T2.ST.1310 | Earned Value Labor Units | 2021-06-12: 94.76
CN.2252-2.T2.ST.1324 | Earned Value Labor Units | 2021-07-03: 237.15
CN.2252-2.T2.ST.1328 | Earned Value Labor Units | 2021-07-03: 252.25
CN.2252-2.T2.ST.1332 | Earned Value Labor Units | 2021-06-12: 50.44; 2021-06-19: 69.36; 2021-06-26: 69.36; 2021-07-03: 69.36; 2021-07-10: 6.31
CN.2252-2.T2.ST.1336 | Earned Value Labor Units | 2021-07-10: 242.32
CN.2252-2.T2.ST.1340 | Earned Value Labor Units | 2021-07-10: 306.48
CN.2252-2.T2.ST.1344 | Earned Value Labor Units | 2021-07-17: 146.16
CN.2252-2.T2.ST.1348 | Earned Value Labor Units | 2021-07-24: 8.91; 2021-07-31: 49.02; 2021-08-07: 49.02; 2021-08-14: 49.02
CN.2252-2.T2.ST.1352 | Earned Value Labor Units | 2021-06-12: 25.96; 2021-06-19: 47.6; 2021-06-26: 47.6; 2021-07-03: 47.6; 2021-07-10: 30.29
CN.2252-2.T2.ST.1356 | Earned Value Labor Units | 2021-06-26: 1.76; 2021-07-03: 3.07
CN.2252-2.T2.ST.1360 | Earned Value Labor Units | 2021-07-17: 4.57; 2021-07-24: 12.56; 2021-07-31: 12.56; 2021-08-07: 12.56; 2021-08-14: 12.56; 2021-08-21: 12.56; 2021-08-28: 12.56; 2021-09-04: 10.73
CN.2252-2.T2.ST.1364 | Earned Value Labor Units | 2021-08-14: 58.11; 2021-08-21: 127.84; 2021-08-28: 127.84; 2021-09-04: 127.84; 2021-09-11: 58.11
CN.2252-2.T2.ST.1368 | Earned Value Labor Units | 2021-07-17: 4.57; 2021-07-24: 12.58; 2021-07-31: 12.58; 2021-08-07: 12.58; 2021-08-14: 12.58; 2021-08-21: 8.01
CN.2252-2.T2.ST.1372 | Earned Value Labor Units | 2021-06-26: 137.42; 2021-07-03: 137.42; 2021-07-10: 137.42; 2021-07-17: 87.45
CN.2252-2.T2.ST.1376 | Earned Value Labor Units | 2021-07-03: 80.72; 2021-07-10: 110.99; 2021-07-17: 110.99; 2021-07-24: 110.99; 2021-07-31: 110.99; 2021-08-07: 110.99; 2021-08-14: 110.99; 2021-08-21: 110.99; 2021-08-28: 110.99; 2021-09-04: 50.45
CN.2252-2.T2.ST.1380 | Earned Value Labor Units | 2021-09-04: 1.33; 2021-09-11: 1.47; 2021-09-18: 1.47
CN.2252-2.T2.ST.1384 | Earned Value Labor Units | 2021-08-28: 43.31; 2021-09-04: 59.54; 2021-09-11: 59.54; 2021-09-18: 59.54
CN.2252-2.T2.ST.1388 | Earned Value Labor Units | 2021-07-24: 58.64; 2021-07-31: 64.5; 2021-08-07: 64.5; 2021-08-14: 64.5; 2021-08-21: 64.5; 2021-08-28: 64.5; 2021-09-04: 64.5; 2021-09-11: 64.5; 2021-09-18: 64.5
CN.2252-2.T2.ST.1392 | Earned Value Labor Units | 2021-08-14: 9.47; 2021-08-21: 10.42; 2021-08-28: 10.42; 2021-09-04: 10.42; 2021-09-11: 10.42; 2021-09-18: 10.42
CN.2252-3 T2.Insul.1223 | Earned Value Labor Units | 2021-08-21: 24.66; 2021-08-28: 135.63; 2021-09-04: 135.63; 2021-09-11: 135.63; 2021-09-18: 135.63
CN.2252-3 T2.Insul.1294 | Earned Value Labor Units | 2021-08-21: 16.66; 2021-08-28: 91.63; 2021-09-04: 91.63; 2021-09-11: 91.63; 2021-09-18: 91.63
CN.2252-3.T2.Insul.1296 | Earned Value Labor Units | 2021-08-21: 52; 2021-08-28: 26
CN.2252-3.T2.Insul.1298 | Earned Value Labor Units | 2021-08-28: 78
CN.2252-3.T2.Insul.1300 | Earned Value Labor Units | 2021-08-28: 78
CN.2252-3.T2.Insul.1302 | Earned Value Labor Units | 2021-08-28: 76
CN.2252-3.T2.Insul.1304 | Earned Value Labor Units | 2021-09-04: 134.89; 2021-09-11: 247.3; 2021-09-18: 247.3
CN.2252-3.T2.MC.1001 | Earned Value Labor Units | 2021-06-05: 474.01; 2021-06-12: 711.01
CN.2252-3.T2.MC.1200 | Earned Value Labor Units |  |  |  | 0.67 | 3.67 | 3.67 | 3.67 | 3.67 | 3.67 | 3.67 | 3.67 | 3.67 | 3.67 | 3.67 | 3.67
CN.2252-3.T2.MC.1220 | Earned Value Labor Units |  |  |  | 0.9 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65 | 1.65
CN.2252-3.T2.MC.1272 | Earned Value Labor Units |  |  |  | 1.67 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59 | 4.59
CN.2252-3.T2.MC.1276 | Earned Value Labor Units |  |  |  |  | 1.98 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 2.65
CN.2252-3.T2.MC.1283 | Earned Value Labor Units |  |  |  | 2.51 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9 | 6.9
CN.2252-3.T2.MC.1285 | Earned Value Labor Units |  |  |  | 3.32 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14 | 9.14
CN.2252-3.T2.MC.1290 | Earned Value Labor Units | 2021-09-18: 51.25
CN.2252-3.T2.MC.1291 | Earned Value Labor Units | 2021-09-18: 205
CN.2252-3.T2.ST.1180 | Earned Value Labor Units | 2021-07-10: 118.95; 2021-07-17: 208.16
CN.2252-3.T2.ST.1190 | Earned Value Labor Units | 2021-07-17: 89.24
CN.2252-3.T2.ST.1200 | Earned Value Labor Units | 2021-06-19: 171.94; 2021-06-26: 214.93
CN.2252-3.T2.ST.1210 | Earned Value Labor Units | 2021-06-12: 47.06; 2021-06-19: 164.7
CN.2252-3.T2.ST.1220 | Earned Value Labor Units | 2021-06-26: 39.8
CN.2252-3.T2.ST.1230 | Earned Value Labor Units | 2021-07-17: 18.79
CN.2252-3.T2.ST.1250 | Earned Value Labor Units | 2021-06-19: 192.68
CN.2252-3.T2.ST.1260 | Earned Value Labor Units | 2021-06-12: 305.8
CN.2252-3.T2.ST.1270 | Earned Value Labor Units | 2021-06-19: 260.46; 2021-06-26: 97.67
CN.2252-3.T2.ST.1280 | Earned Value Labor Units | [6 empty] | 5.79 | 15.92 | 15.92 | 15.92 | 15.92 | 15.92 | 15.92 | 15.92 | 15.92 | 15.92 | 5.79
CN.2252-3.T2.ST.1290 | Earned Value Labor Units | 2021-06-26: 158.02; 2021-07-03: 39.51
CN.2252-3.T2.ST.1300 | Earned Value Labor Units | 2021-08-14: 51.05; 2021-08-21: 43.76
CN.2252-3.T2.ST.1310 | Earned Value Labor Units | 2021-06-12: 115.73; 2021-06-19: 115.73
CN.2252-3.T2.ST.1320 | Earned Value Labor Units | 2021-06-26: 184.41
CN.2252-3.T2.ST.1324 | Earned Value Labor Units | 2021-07-24: 2.86; 2021-07-31: 7.88; 2021-08-07: 7.88; 2021-08-14: 7.88; 2021-08-21: 7.88; 2021-08-28: 7.88; 2021-09-04: 5.01
CN.2252-3.T2.ST.1332 | Earned Value Labor Units | 2021-07-17: 14.47; 2021-07-24: 39.8; 2021-07-31: 39.8; 2021-08-07: 39.8; 2021-08-14: 39.8; 2021-08-21: 25.33
CN.2252-3.T2.ST.1336 | Earned Value Labor Units | 2021-07-24: 0.25; 2021-07-31: 0.68; 2021-08-07: 0.68; 2021-08-14: 0.68; 2021-08-21: 0.68; 2021-08-28: 0.68; 2021-09-04: 0.68; 2021-09-11: 0.68; 2021-09-18: 0
CN.2252-3.T2.ST.1344 | Earned Value Labor Units | 2021-08-21: 10.18; 2021-08-28: 28; 2021-09-04: 28; 2021-09-11: 12.73
CN.2252-3.T2.ST.1348 | Earned Value Labor Units | 2021-09-04: 73.54
CN.2252-3.T2.ST.1352 | Earned Value Labor Units | 2021-09-11: 119.05; 2021-09-18: 83.33
CN.2252-3.T2.ST.1360 | Earned Value Labor Units | 2021-07-17: 129.99
CN.2252-3.T2.ST.1364 | Earned Value Labor Units | 2021-07-17: 0.92; 2021-07-24: 2.54; 2021-07-31: 2.54; 2021-08-07: 2.54; 2021-08-14: 2.54; 2021-08-21: 2.54; 2021-08-28: 2.54; 2021-09-04: 2.54; 2021-09-11: 2.54; 2021-09-18: 1.61
CN.2252-3.T2.ST.1372 | Earned Value Labor Units | [6 empty] | 4.61 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68 | 12.68
CN.2252-3.T2.ST.1376 | Earned Value Labor Units | 2021-08-07: 4.12; 2021-08-14: 11.32; 2021-08-21: 11.32; 2021-08-28: 11.32; 2021-09-04: 11.32; 2021-09-11: 11.32; 2021-09-18: 11.32
CN.2252-4.T2.ST.1198 | Earned Value Labor Units | 2021-06-19: 220.77; 2021-06-26: 551.94
CN.2252-4.T2.ST.1202 | Earned Value Labor Units | 2021-06-12: 17.83; 2021-06-19: 49.03; 2021-06-26: 49.03; 2021-07-03: 40.12
CN.2252-4.T2.ST.1206 | Earned Value Labor Units | 2021-06-12: 14.43; 2021-06-19: 39.69; 2021-06-26: 39.69; 2021-07-03: 39.69; 2021-07-10: 39.69; 2021-07-17: 39.69; 2021-07-24: 39.69; 2021-07-31: 18.04
CN.2252-4.T2.ST.1210 | Earned Value Labor Units |  |  |  |  | 8.14 | 22.39 | 22.39 | 22.39 | 22.39 | 22.39 | 22.39 | 22.39 | 22.39 | 22.39 | 22.39 | 14.25
CN.2252-4.T2.ST.1214 | Earned Value Labor Units | 2021-07-10: 76.89
CN.2252-4.T2.ST.1218 | Earned Value Labor Units | 2021-06-26: 4.81; 2021-07-03: 13.22; 2021-07-10: 13.22; 2021-07-17: 8.41
CN.2252-4.T2.ST.1222 | Earned Value Labor Units | 2021-06-26: 1.66; 2021-07-03: 4.58; 2021-07-10: 4.58; 2021-07-17: 2.91
CN.2252-4.T2.ST.1226 | Earned Value Labor Units | 2021-06-26: 1.87; 2021-07-03: 5.15; 2021-07-10: 5.15; 2021-07-17: 3.28
CN.2252-4.T2.ST.1230 | Earned Value Labor Units | 2021-06-12: 6.86; 2021-06-19: 18.87; 2021-06-26: 18.87; 2021-07-03: 12.01
CN.2252-4.T2.ST.1234 | Earned Value Labor Units | 2021-07-24: 19.6; 2021-07-31: 53.91; 2021-08-07: 34.31
CN.2252-4.T2.ST.1238 | Earned Value Labor Units | 2021-06-12: 6.63; 2021-06-19: 18.24; 2021-06-26: 18.24; 2021-07-03: 11.61
CN.2252-4.T2.ST.1242 | Earned Value Labor Units | 2021-06-12: 6.68; 2021-06-19: 18.36; 2021-06-26: 18.36; 2021-07-03: 11.69
CN.2252-4.T2.ST.1246 | Earned Value Labor Units | 2021-06-26: 4.76; 2021-07-03: 13.09; 2021-07-10: 13.09; 2021-07-17: 13.09; 2021-07-24: 8.33
CN.2252-4.T2.ST.1250 | Earned Value Labor Units | 2021-06-26: 8.61; 2021-07-03: 11.84; 2021-07-10: 11.84; 2021-07-17: 11.84; 2021-07-24: 11.84; 2021-07-31: 11.84; 2021-08-07: 11.84; 2021-08-14: 11.84; 2021-08-21: 11.84; 2021-08-28: 7.53
CN.2252-4.T2.ST.1254 | Earned Value Labor Units | [5 empty] | 7.67 | 21.09 | 21.09 | 21.09 | 21.09 | 21.09 | 21.09 | 21.09 | 21.09 | 21.09 | 21.09 | 18.79
CN.2252-4.T2.ST.1258 | Earned Value Labor Units | [5 empty] | 9 | 24.74 | 24.74 | 24.74 | 24.74 | 24.74 | 24.74 | 24.74 | 24.74 | 24.74 | 24.74 | 24.74 | 24.74
CN.2252-5.T2.MC.1286 | Earned Value Labor Units | 2021-07-17: 1.2; 2021-07-24: 3.29; 2021-07-31: 3.29; 2021-08-07: 3.29; 2021-08-14: 3.29; 2021-08-21: 3.29; 2021-08-28: 3.29; 2021-09-04: 3.29; 2021-09-11: 3.29; 2021-09-18: 3.29
CN.2252-5.T2.MC.1291 | Earned Value Labor Units | 2021-07-17: 0.6; 2021-07-24: 1.64; 2021-07-31: 1.64; 2021-08-07: 1.64; 2021-08-14: 1.64; 2021-08-21: 1.64; 2021-08-28: 1.64; 2021-09-04: 1.64; 2021-09-11: 1.64; 2021-09-18: 1.64
CN.2252-5.T2.MC.1374 | Earned Value Labor Units | 2021-07-24: 103.62
CN.2252-5.T2.MC.1378 | Earned Value Labor Units |  |  |  |  | 7.17 | 13.14 | 13.14 | 13.14 | 13.14 | 13.14 | 13.14 | 13.14 | 13.14 | 13.14 | 13.14 | 3.58
CN.2252-5.T2.MC.1381 | Earned Value Labor Units | 2021-09-18: 1.2
CN.2252-5.T2.MC.1382 | Earned Value Labor Units |  |  |  |  | 3.92 | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 | 7.19 | 4.58
CN.2252-5.T2.MC.1386 | Earned Value Labor Units | [6 empty] | 1.66 | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 | 4.56 | 4.56
CN.2252-6.T2.ST.1380 | Earned Value Labor Units | 2021-07-03: 16.86; 2021-07-10: 92.74; 2021-07-17: 92.74; 2021-07-24: 92.74; 2021-07-31: 59.02
CN.2252-6.T2.ST.1390 | Earned Value Labor Units | 2021-09-11: 8.28; 2021-09-18: 45.56
CN.2252-7.T2.ST.1400 | Earned Value Labor Units | [6 empty] | 2.76 | 15.18 | 15.18 | 15.18 | 15.18 | 15.18 | 15.18 | 15.18 | 15.18 | 15.18 | 15.18 | 15.18
CN.2262-4.T2.ST.1551 | Earned Value Labor Units | 2021-08-28: 26.69; 2021-09-04: 48.93; 2021-09-11: 48.93; 2021-09-18: 48.93
CN.2262-4.T2.ST.1554 | Earned Value Labor Units | 2021-08-28: 1.77; 2021-09-04: 3.24; 2021-09-11: 3.24; 2021-09-18: 3.24
CN.2262.T2.MC.1010 | Earned Value Labor Units | [6 empty] | 0.4 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 2.19 | 1.89
CN.2262.T2.MC.1020 | Earned Value Labor Units | 2021-07-17: 4.27; 2021-07-24: 4.27; 2021-07-31: 4.27; 2021-08-07: 4.27; 2021-08-14: 4.27; 2021-08-21: 4.27; 2021-08-28: 4.27; 2021-09-04: 4.27; 2021-09-11: 3.88
CN.2262.T2.MC.1030 | Earned Value Labor Units |  |  | 2.38 | 4.36 | 4.36 | 4.36 | 4.36 | 4.36 | 4.36 | 4.36 | 4.36 | 4.36 | 2.38
CN.2262.T2.MC.1040 | Earned Value Labor Units |  |  |  |  | 1.68 | 4.63 | 4.63 | 4.63 | 4.63 | 4.63 | 4.63 | 4.63 | 4.63 | 4.63 | 1.68
CN.2262.T2.MC.1060 | Earned Value Labor Units | 2021-06-12: 11.37; 2021-06-19: 1.03
CN.2262.T2.MC.1070 | Earned Value Labor Units |  |  | 1.18 | 2.16 | 2.16 | 2.16 | 2.16 | 2.16 | 2.16 | 2.16 | 2.16 | 2.16 | 1.38
CN.2262.T2.MC.1080 | Earned Value Labor Units | 2021-06-05: 52.08; 2021-06-12: 57.28; 2021-06-19: 15.62
CN.2262.T2.MC.1090 | Earned Value Labor Units |  |  | 2.76 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 7.6 | 4.84
CN.2262.T2.MC.1100 | Earned Value Labor Units |  |  | 0.63 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 1.73 | 0.63
CN.2262.T2.MC.1120 | Earned Value Labor Units | 2021-06-12: 18.66; 2021-06-19: 11.66
CN.2262.T2.MC.1160 | Earned Value Labor Units | 2021-06-12: 51.68; 2021-06-19: 60.3
CN.2262.T2.MC.1172 | Earned Value Labor Units | 2021-06-19: 23.26; 2021-06-26: 127.91; 2021-07-03: 127.91; 2021-07-10: 127.91; 2021-07-17: 127.91; 2021-07-24: 127.91; 2021-07-31: 58.14
CN.2262.T2.MC.1173 | Earned Value Labor Units | [7 empty] | 9.89 | 18.13 | 18.13 | 18.13 | 18.13 | 18.13 | 18.13 | 18.13 | 18.13 | 18.13 | 18.13
CN.2262.T2.MC.1174 | Earned Value Labor Units | 2021-07-17: 1.33; 2021-07-24: 3.67; 2021-07-31: 3.67; 2021-08-07: 3.67; 2021-08-14: 3.67; 2021-08-21: 3.67; 2021-08-28: 2.33
CN.2262.T2.MC.1175 | Earned Value Labor Units | 2021-07-03: 17.95
CN.2262.T2.MC.1176 | Earned Value Labor Units | 2021-07-03: 26.11
CN.2262.T2.MC.1177 | Earned Value Labor Units | 2021-07-03: 63
CN.2262.T2.MC.1178 | Earned Value Labor Units |  |  |  |  | 3.03 | 8.34 | 8.34 | 8.34 | 8.34 | 8.34 | 8.34 | 8.34 | 8.34 | 8.34 | 8.34 | 1.52
CN.2262.T2.MC.1179 | Earned Value Labor Units | 2021-06-19: 17.95
CN.2262.T2.MC.1180 | Earned Value Labor Units | 2021-06-26: 700.7
CN.2262.T2.MC.1181 | Earned Value Labor Units | 2021-06-26: 12
CN.2262.T2.MC.1182 | Earned Value Labor Units | 2021-07-03: 1.61; 2021-07-10: 8.84; 2021-07-17: 8.84; 2021-07-24: 8.84; 2021-07-31: 8.84; 2021-08-07: 8.84; 2021-08-14: 8.84; 2021-08-21: 8.84; 2021-08-28: 8.84; 2021-09-04: 4.82
CN.2262.T2.MC.1183 | Earned Value Labor Units | 2021-08-07: 0.94; 2021-08-14: 1.72; 2021-08-21: 1.72; 2021-08-28: 1.72; 2021-09-04: 1.72; 2021-09-11: 0.19
CN.2262.T2.MC.1187 | Earned Value Labor Units | 2021-06-19: 23.39; 2021-06-26: 128.66; 2021-07-03: 128.66; 2021-07-10: 128.66; 2021-07-17: 128.66; 2021-07-24: 128.66; 2021-07-31: 81.87
CN.2262.T2.MC.1191 | Earned Value Labor Units | 2021-09-04: 173.73; 2021-09-11: 212.33; 2021-09-18: 212.33
CN.2262.T2.MC.1199 | Earned Value Labor Units | 2021-06-05: 13.69; 2021-06-12: 25.1; 2021-06-19: 25.1; 2021-06-26: 25.1; 2021-07-03: 25.1; 2021-07-10: 25.1; 2021-07-17: 25.1; 2021-07-24: 25.1; 2021-07-31: 11.41
CN.2262.T2.MC.1203 | Earned Value Labor Units | 2021-07-24: 1.57; 2021-07-31: 4.3; 2021-08-07: 4.3; 2021-08-14: 4.3; 2021-08-21: 4.3; 2021-08-28: 4.3; 2021-09-04: 4.3; 2021-09-11: 4.3; 2021-09-18: 4.3
CN.2262.T2.MC.1211 | Earned Value Labor Units | 2021-08-07: 2.98; 2021-08-14: 5.46; 2021-08-21: 5.46; 2021-08-28: 5.46; 2021-09-04: 5.46; 2021-09-11: 1.2
CN.2262.T2.MC.1215 | Earned Value Labor Units | 2021-09-04: 15.31; 2021-09-11: 21.05; 2021-09-18: 8.61
CN.2262.T2.MC.1219 | Earned Value Labor Units | 2021-09-04: 6.35; 2021-09-11: 23.28; 2021-09-18: 15.35
CN.2262.T2.MC.1221 | Earned Value Labor Units | 2021-08-21: 14.85; 2021-08-28: 81.68; 2021-09-04: 81.68; 2021-09-11: 81.68; 2021-09-18: 81.67
CN.2262.T2.MC.1225 | Earned Value Labor Units | 2021-09-11: 55
CN.2262.T2.MC.1227 | Earned Value Labor Units | 2021-09-04: 98.44; 2021-09-11: 108.28; 2021-09-18: 108.28
CN.2262.T2.ST.1304 | Earned Value Labor Units | 2021-06-19: 6.64; 2021-06-26: 36.54; 2021-07-03: 36.54; 2021-07-10: 36.54; 2021-07-17: 36.54; 2021-07-24: 36.54; 2021-07-31: 36.54; 2021-08-07: 9.97
CN.2262.T2.ST.1314 | Earned Value Labor Units | 2021-06-26: 20.09; 2021-07-03: 27.62; 2021-07-10: 27.62; 2021-07-17: 27.62; 2021-07-24: 27.62; 2021-07-31: 27.62; 2021-08-07: 17.58
CN.2262.T2.ST.1324 | Earned Value Labor Units | 2021-06-19: 16.59; 2021-06-26: 45.63; 2021-07-03: 45.63; 2021-07-10: 45.63; 2021-07-17: 12.44
CN.2262.T2.ST.1334 | Earned Value Labor Units | 2021-06-19: 7.02; 2021-06-26: 19.29; 2021-07-03: 19.29; 2021-07-10: 19.29; 2021-07-17: 8.77
CN.2262.T2.ST.1344 | Earned Value Labor Units | 2021-06-19: 7.01; 2021-06-26: 19.27; 2021-07-03: 19.27; 2021-07-10: 19.27; 2021-07-17: 12.26
CN.2262.T2.ST.1354 | Earned Value Labor Units | 2021-06-19: 6.2; 2021-06-26: 17.05; 2021-07-03: 17.05; 2021-07-10: 17.05; 2021-07-17: 10.85
CN.2262.T2.ST.1364 | Earned Value Labor Units | 2021-06-19: 6.52; 2021-06-26: 17.92; 2021-07-03: 17.92; 2021-07-10: 17.92; 2021-07-17: 11.4
CN.2262.T2.ST.1374 | Earned Value Labor Units | 2021-08-14: 2.49; 2021-08-21: 13.67; 2021-08-28: 13.67; 2021-09-04: 13.67; 2021-09-11: 13.67; 2021-09-18: 13.67
CN.2262.T2.ST.1384 | Earned Value Labor Units |  |  |  |  | 0.38 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7
CN.2262.T2.ST.1394 | Earned Value Labor Units | 2021-06-26: 15.57; 2021-07-03: 42.81; 2021-07-10: 42.81; 2021-07-17: 42.81; 2021-07-24: 42.81; 2021-07-31: 42.81; 2021-08-07: 42.81; 2021-08-14: 42.81; 2021-08-21: 27.24
CN.2262.T2.ST.1404 | Earned Value Labor Units |  |  |  | 9.34 | 17.12 | 17.12 | 17.12 | 17.12 | 17.12 | 17.12 | 17.12 | 17.12 | 17.12 | 10.9
CN.2262.T2.ST.1424 | Earned Value Labor Units | 2021-06-12: 13.28; 2021-06-19: 26.56
CN.2262.T2.ST.1434 | Earned Value Labor Units | 2021-06-19: 70.62
CN.2262.T2.ST.1444 | Earned Value Labor Units | 2021-06-26: 154.59
CN.2262.T2.ST.1454 | Earned Value Labor Units | [5 empty] | 3.52 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33 | 19.33
CN.2262.T2.ST.1464 | Earned Value Labor Units | 2021-07-03: 27.34; 2021-07-10: 75.18; 2021-07-17: 47.84
CN.2262.T2.ST.1474 | Earned Value Labor Units | 2021-07-17: 17.25; 2021-07-24: 31.63; 2021-07-31: 31.63; 2021-08-07: 20.13
CN.2262.T2.ST.1494 | Earned Value Labor Units | 2021-07-17: 3.07; 2021-07-24: 5.62; 2021-07-31: 5.62; 2021-08-07: 5.62; 2021-08-14: 5.62; 2021-08-21: 5.62; 2021-08-28: 5.62; 2021-09-04: 5.62; 2021-09-11: 5.62; 2021-09-18: 5.62
CN.2262.T2.ST.1504 | Earned Value Labor Units | 2021-07-17: 36.05; 2021-07-24: 49.57; 2021-07-31: 49.57; 2021-08-07: 49.57; 2021-08-14: 22.53
CN.2262.T2.ST.1514 | Earned Value Labor Units | 2021-07-31: 12.9; 2021-08-07: 14.19; 2021-08-14: 14.19; 2021-08-21: 14.19; 2021-08-28: 9.03
CN.2262.T2.ST.1524 | Earned Value Labor Units | 2021-07-17: 5.25; 2021-07-24: 7.22; 2021-07-31: 7.22; 2021-08-07: 7.22; 2021-08-14: 7.22; 2021-08-21: 7.22; 2021-08-28: 7.22; 2021-09-04: 7.22; 2021-09-11: 7.22; 2021-09-18: 0.21
CN.2262.T2.ST.1534 | Earned Value Labor Units | 2021-07-17: 37.3; 2021-07-24: 68.39; 2021-07-31: 68.39; 2021-08-07: 43.52
CN.2262.T2.ST.1544 | Earned Value Labor Units | 2021-07-31: 11.02; 2021-08-07: 15.16; 2021-08-14: 15.16; 2021-08-21: 15.16; 2021-08-28: 15.16; 2021-09-04: 9.64
CN.2262.T2.ST.1554 | Earned Value Labor Units | 2021-07-17: 2.34; 2021-07-24: 4.29; 2021-07-31: 4.29; 2021-08-07: 4.29; 2021-08-14: 4.29; 2021-08-21: 4.29; 2021-08-28: 4.29; 2021-09-04: 4.29; 2021-09-11: 4.29; 2021-09-18: 0.48
CN.2262.T2.ST.1564 | Earned Value Labor Units | 2021-09-04: 26.58; 2021-09-11: 48.73; 2021-09-18: 48.73
CN.2262.T2.ST.1574 | Earned Value Labor Units | 2021-06-26: 19.68; 2021-07-03: 54.13; 2021-07-10: 54.13; 2021-07-17: 54.13; 2021-07-24: 54.13; 2021-07-31: 54.13; 2021-08-07: 54.13; 2021-08-14: 4.92
CN.2262.T2.ST.1594 | Earned Value Labor Units | 2021-09-04: 275.82; 2021-09-11: 91.94
CN.2262.T2.ST.1598 | Earned Value Labor Units | 2021-09-04: 24.55; 2021-09-11: 45.01; 2021-09-18: 45.01
CN.2262.T2.ST.1602 | Earned Value Labor Units | 2021-09-11: 44.09; 2021-09-18: 121.25
CN.2262.T2.ST.1610 | Earned Value Labor Units |  |  |  |  | 17.53 | 96.44 | 96.44 | 96.44 | 96.44 | 96.44 | 96.44 | 96.44 | 96.44 | 96.44 | 96.44 | 96.44 | 96.44 | 96.44
CN.2262.T2.ST.1615 | Earned Value Labor Units | 2021-09-11: 1.64; 2021-09-18: 7.57
CN.2262.T2.ST.1622 | Earned Value Labor Units | 2021-09-18: 40.13
CN.2262.T2.ST.1625 | Earned Value Labor Units | 2021-09-04: 2.93; 2021-09-11: 8.05; 2021-09-18: 8.05
CN.2262.T2.ST.1634 | Earned Value Labor Units | 2021-09-04: 14.63; 2021-09-11: 26.82; 2021-09-18: 26.82
CN.2262.T2.ST.1642 | Earned Value Labor Units | 2021-07-17: 17.87; 2021-07-24: 24.57; 2021-07-31: 24.57; 2021-08-07: 24.57; 2021-08-14: 24.57; 2021-08-21: 24.57; 2021-08-28: 24.57; 2021-09-04: 24.57; 2021-09-11: 24.57; 2021-09-18: 24.57
CN.2262.T2.ST.1643 | Earned Value Labor Units |  |  |  |  | 13.23 | 14.55 | 14.55 | 14.55 | 14.55 | 14.55 | 14.55 | 14.55 | 14.55 | 14.55 | 14.55 | 14.55 | 14.55 | 14.55
CN.2262.T2.ST.1678 | Earned Value Labor Units | 2021-08-21: 139.99; 2021-08-28: 384.98; 2021-09-04: 384.98; 2021-09-11: 384.98; 2021-09-18: 384.98
CN.2272.T2.MC.1000 | Earned Value Labor Units | 2021-08-07: 36
CN.2272.T2.MC.1010 | Earned Value Labor Units | 2021-08-21: 327.59
CN.2272.T2.MC.1020 | Earned Value Labor Units | 2021-08-21: 56
CN.2272.T2.MC.1030 | Earned Value Labor Units | 2021-08-21: 33.67; 2021-08-28: 37.03; 2021-09-04: 37.03; 2021-09-11: 37.03; 2021-09-18: 37.03
CN.2272.T2.MC.1040 | Earned Value Labor Units | 2021-09-04: 124.02
CN.2272.T2.MC.1050 | Earned Value Labor Units | 2021-09-18: 120.6
CN.2272.T2.MC.1080 | Earned Value Labor Units | 2021-07-31: 99.34; 2021-08-07: 347.7
CN.2272.T2.MC.1090 | Earned Value Labor Units | 2021-09-04: 82.68
CN.2272.T2.MC.1100 | Earned Value Labor Units | 2021-08-14: 10.25; 2021-08-21: 56.39; 2021-08-28: 56.39; 2021-09-04: 56.39; 2021-09-11: 56.39; 2021-09-18: 56.39
CN.2272.T2.MC.1120 | Earned Value Labor Units | 2021-08-14: 112.68
CN.2272.T2.MC.1160 | Earned Value Labor Units | 2021-08-07: 2.66; 2021-08-14: 7.31; 2021-08-21: 7.31; 2021-08-28: 7.31; 2021-09-04: 7.31; 2021-09-11: 7.31; 2021-09-18: 7.31
CN.2272.T2.MC.1210 | Earned Value Labor Units | 2021-08-07: 210.68
CN.2272.T2.MC.1220 | Earned Value Labor Units | 2021-08-14: 61.78; 2021-08-21: 216.24
CN.2272.T2.MC.1222 | Earned Value Labor Units | [5 empty] | 23.06 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37 | 25.37
CN.2272.T2.ST.1320 | Earned Value Labor Units | 2021-07-31: 7.9
CN.2272.T2.ST.1330 | Earned Value Labor Units | 2021-07-10: 1.94; 2021-07-17: 5.32; 2021-07-24: 5.32; 2021-07-31: 3.39
CN.2272.T2.ST.1340 | Earned Value Labor Units | 2021-07-10: 20.65
CN.2272.T2.ST.1350 | Earned Value Labor Units | 2021-08-14: 39.29
CN.2272.T2.ST.1360 | Earned Value Labor Units | 2021-08-14: 14.51
CN.2272.T2.ST.1364 | Earned Value Labor Units | 2021-08-14: 301.32
CN.2272.T2.ST.1368 | Earned Value Labor Units | 2021-08-14: 13.69; 2021-08-21: 37.65; 2021-08-28: 6.85
CN.2272.T2.ST.1376 | Earned Value Labor Units | 2021-08-21: 37.57
CN.2272.T2.ST.1380 | Earned Value Labor Units | 2021-08-21: 58.68
CN.2272.T2.ST.1384 | Earned Value Labor Units | 2021-08-21: 48.94; 2021-08-28: 85.64
CN.2272.T2.ST.1388 | Earned Value Labor Units | 2021-08-28: 19.56; 2021-09-04: 53.79; 2021-09-11: 53.79; 2021-09-18: 53.79
CN.2272.T2.ST.1392 | Earned Value Labor Units | 2021-08-21: 22.2
CN.2272.T2.ST.1396 | Earned Value Labor Units | 2021-08-21: 28.31
CN.2272.T2.ST.1400 | Earned Value Labor Units | 2021-09-04: 0.7; 2021-09-11: 1.92; 2021-09-18: 1.92
CN.2272.T2.ST.1404 | Earned Value Labor Units | 2021-08-21: 3.09; 2021-08-28: 8.49; 2021-09-04: 8.49; 2021-09-11: 8.49; 2021-09-18: 8.49
CN.2272.T2.ST.1408 | Earned Value Labor Units | 2021-08-14: 1.12; 2021-08-21: 6.18; 2021-08-28: 6.18; 2021-09-04: 6.18; 2021-09-11: 6.18; 2021-09-18: 6.18
CN.2272.T2.ST.1430 | Earned Value Labor Units | 2021-07-17: 6.76; 2021-07-24: 18.59; 2021-07-31: 18.59; 2021-08-07: 18.59; 2021-08-14: 18.59; 2021-08-21: 18.59; 2021-08-28: 18.59; 2021-09-04: 18.59; 2021-09-11: 13.52
CN.2272.T2.ST.1461 | Earned Value Labor Units | 2021-07-31: 330.26; 2021-08-07: 41.28
CN.2272.T2.ST.1465 | Earned Value Labor Units | 2021-08-14: 91.81; 2021-08-21: 107.12
CN.2272.T2.ST.1469 | Earned Value Labor Units | 2021-08-21: 43.74; 2021-08-28: 80.19; 2021-09-04: 51.03
CN.2272.T2.ST.1485 | Earned Value Labor Units | 2021-08-28: 49.64; 2021-09-04: 91.01; 2021-09-11: 57.91
CN.2272.T2.ST.1493 | Earned Value Labor Units | 2021-09-04: 13.45; 2021-09-11: 37; 2021-09-18: 37
CN.2272.T2.ST.1497 | Earned Value Labor Units | 2021-09-04: 6.6; 2021-09-11: 18.15; 2021-09-18: 18.15
CN.2272.T2.ST.1501 | Earned Value Labor Units | 2021-09-04: 52.25; 2021-09-11: 95.78; 2021-09-18: 95.78
CN.2272.T2.ST.1505 | Earned Value Labor Units | 2021-09-04: 22.76; 2021-09-11: 62.58; 2021-09-18: 62.58
CN.2272.T2.ST.1513 | Earned Value Labor Units | 2021-09-04: 2.14; 2021-09-11: 5.88; 2021-09-18: 5.88
CN.2272.T2.ST.1598 | Earned Value Labor Units | 2021-09-11: 24.56; 2021-09-18: 85.98
CN.2272.T2.ST.1618 | Earned Value Labor Units | 2021-08-21: 18.36
CN.4242.T2.IN.1665 | Earned Value Labor Units | 2021-09-11: 33.59; 2021-09-18: 33.59
CN.4242.T2.PS.1637 | Earned Value Labor Units | 2021-06-05: 22.11; 2021-06-12: 17.69
CN.4242.T2.PS.1641 | Earned Value Labor Units | 2021-05-29: 27.69; 2021-06-05: 38.08; 2021-06-12: 24.23
CN.4242.T2.PS.1645 | Earned Value Labor Units | 2021-06-05: 53.04; 2021-06-12: 37.12
CN.4242.T2.PS.1649 | Earned Value Labor Units |  |  |  |  | 3 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 4.12 | 2.25
CN.4242.T2.PS.1650 | Earned Value Labor Units | 2021-06-12: 47.32
CN.4242.T2.PS.1653 | Earned Value Labor Units | 2021-09-18: 12.82
CN.4242.T2.PS.1657 | Earned Value Labor Units | 2021-05-29: 7.24; 2021-06-05: 16.3
CN.4242.T2.PS.1661 | Earned Value Labor Units | 2021-06-05: 40.3; 2021-06-12: 20.15
CN.4242.T2.ST.1629 | Earned Value Labor Units | 2021-09-11: 52.13
CN.4242.T2.ST.1633 | Earned Value Labor Units | 2021-09-11: 47.99
CN.4242.T2.WW.1645 | Earned Value Labor Units | 2021-05-29: 5.14; 2021-06-05: 3.67
CN.4242.T2.WW.1653 | Earned Value Labor Units | 2021-06-05: 8.81
CN.4242.T2.WW.1661 | Earned Value Labor Units | 2021-09-18: 8.81
CN.4242.T2.WW.1665 | Earned Value Labor Units | 2021-09-18: 8.81
CN.4242.T2.WW.1669 | Earned Value Labor Units | 2021-05-29: 1.26; 2021-06-05: 6.92; 2021-06-12: 0.63
CN.4242.T2.WW.1673 | Earned Value Labor Units | 2021-06-05: 8.81

## av
Activity ID | Spreadsheet Field | 2021-05-22 | 2021-05-29 | 2021-06-05 | 2021-06-12 | 2021-06-19 | 2021-06-26 | 2021-07-03 | 2021-07-10 | 2021-07-17 | 2021-07-24 | 2021-07-31 | 2021-08-07 | 2021-08-14 | 2021-08-21 | 2021-08-28 | 2021-09-04 | 2021-09-11 | 2021-09-18
2252-1T2.PI.CS-AIN.1055 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2
2252-1T2.PI.CS-GSL.1006 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 36 | 34 | 33 | 60 | 3 | 24
2252-1T2.PI.CS-LPB.1022 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 3 | 3 | 3 | 2 | 5 | 3 | 3 | 2 | 1
2252-1T2.PI.CS-LPB.1029 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 35 | 30 | 70 | 33 | 27 | 31
2252-1T2.PI.CS-LPB.1046 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 19 | 27 | 27 | 17 | 3 | 21
2252-1T2.PI.CS-LPB.1047 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 12 | 2 | 31 | 16 | 21 | 27 | 21 | 13 | 17
2252-1T2.PI.CS-LSH.1048 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 10 | 8 | 8 | 6 | 6 | 9
2252-1T2.PI.CS-WFI.1057 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 4
2252-1T2.PI.HDPE-WRO.1060 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38
2252-1T2.PI.SS-LPB.1019 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 18 | 69 | 8 | 105 | 156 | 188
2252-1T2.PI.SS-LPB.1025 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 12 | 12 | 20 | 14 | 10 | 19 | 13 | 21 | 31 | 10
2252-1T2.PI.SS-LPB.1051 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 60 | 31 | 27 | 35 | 65 | 35 | 45 | 46
2252-1T2.PI.SS-SPB.1034 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 14 | 26
2252-1T2.PI.SS-SPB.1052 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 61 | 27 | 3
2252-1T2.PI.SS-WPO.1060 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17 | 1 | 15 | 1 | 20 | 11
2252-1T2.PI.SS-WRO.1053 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 25 | 45 | 61 | 54 | 34 | 59
2252-1T2.PI.SS-WSC.1021 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 217 | 19 | 94 | 21
2252-1T2.PI.SS-WSC.1026 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 7 | 7 | 8 | 7 | 4 | 7 | 4
2252-1T2.PI.SS-WSC.1054 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 55 | 56 | 82 | 84 | 37 | 57 | 28
2252-2T2.PI.CS-SPB.1047 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 17 | 21 | 24 | 22 | 3 | 14 | 17 | 20
2252-2T2.PI.CS-SPB.1061 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 15 | 11 | 20 | 8 | 9 | 9 | 10 | 14 | 2
2252-2T2.PI.CS-SPB.1069 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 78 | 53 | 92 | 25 | 6 | 37
2252-2T2.PI.SS-LPB.1049 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 94 | 66 | 125 | 61 | 1 | 65
2252-2T2.PI.SS-LPB.1057 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 5 | 5 | 8 | 8 | 9 | 10 | 7 | 8 | 16
2252-2T2.PI.SS-LPB.1063 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 17 | 11 | 23 | 23 | 10 | 18 | 24 | 16 | 19
2252-2T2.PI.SS-LPB.1067 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 4 | 3 | 3 | 2 | 1
2252-2T2.PI.SS-LPB.1071 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 129 | 46 | 74 | 84 | 81 | 39 | 65 | 46 | 106
2252-2T2.PI.SS-WSC.1053 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 8 | 10 | 15 | 2 | 5 | 9
2252-2T2.PI.SS-WSC.1059 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 2 | 1 | 2 | 3 | 4 | 3 | 1
2252-2T2.PI.SS-WSC.1073 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 40 | 75
2252-3 T2.PI.PS .9161 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 4 | 3 | 2 | 4 | 6 | 2 | 4 | 2
2252-3 T2.PI.PS .9163 | Actual Labor Units | 0 | 0 | 0 | 7 | 7 | 11 | 10 | 5 | 6 | 8 | 5 | 9 | 4 | 7 | 6 | 7 | 4 | 10
2252-3 T2.PI.PS .9165 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 1 | 13 | 12 | 6 | 7 | 8 | 9 | 7 | 10 | 9 | 9 | 8 | 8
2252-3 T2.PI.PS .9167 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 4 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 4
2252-3 T2.PI.PS .9169 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
2252-3 T2.PI.PS .9171 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
2252-3 T2.PI.PS .9173 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
2252-3 T2.PI.PS .9175 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
2252-3 T2.PI.SS-GSL. 9162 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 19 | 40 | 34 | 27 | 13
2252-3 T2.PI.SS-LPB. 9167 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 13
2252-3 T2.PI.SS-LPB. 9270 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 21 | 23
2252-3 T2.PI.SS-SPB. 9157 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 32 | 20 | 11 | 32 | 24 | 17
2252-3 T2.PI.SS-WGS. 9159 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 55 | 5 | 25 | 63 | 5 | 55
2252-3 T2.PI.SS-WRO. 9160 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72
2252-3 T2.PI.SS-WSC. 9162 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 56 | 72 | 7 | 38 | 50 | 32
2252-3 T2.PI.SS-WSC. 9178 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 32 | 72
2252-3 T2.PI.SS-WSC. 9180 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 14 | 8
2252-3 T2.PI.SS-WSC. 9276 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 14
2252-4T2.PI.CS-LPB.1081 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 37 | 18 | 18 | 22 | 16 | 2 | 33 | 0
2252-4T2.PI.CS-LPB.1085 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 2
2252-4T2.PI.CS-LPB.1087 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 367
2252-4T2.PI.SS-LPB.1092 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
2252-4T2.PI.SS-WSC.1079 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 70 | 47 | 58 | 30 | 57 | 86 | 65
2252-4T2.PI.SS-WSC.1083 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 6 | 7 | 3 | 7 | 3 | 5
2262-1T2.PI.CS-AIN.9207 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 1 | 2 | 2 | 1 | 2 | 1
2262-1T2.PI.CS-LPB.9235 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 65 | 41
2262-1T2.PI.HDPE-WCW.9239 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 100 | 105 | 89
2262-1T2.PI.HDPE-WCW.9259 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 5 | 7
2262-1T2.PI.HDPE-WRO.9291 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 246
2262-1T2.PI.SS-GVE.9195 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 4 | 4
2262-1T2.PI.SS-LPB.9199 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27 | 31 | 22 | 3 | 36 | 26 | 3 | 16 | 41 | 15
2262-1T2.PI.SS-LPB.9251 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 4 | 11 | 22 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-LPB.9267 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 161 | 250 | 141
2262-1T2.PI.SS-SPB.9207 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 63 | 30 | 58 | 34 | 9 | 6
2262-1T2.PI.SS-SPB.9219 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 124
2262-1T2.PI.SS-SPB.9271 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 3 | 2 | 53 | 42 | 4 | 25 | 56
2262-1T2.PI.SS-WPO.9303 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | 47 | 206 | 276 | 44
2262-1T2.PI.SS-WRO.9295 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
2262-1T2.PI.SS-WRO.9311 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 9 | 10
2262-1T2.PI.SS-WSC.9211 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 77 | 106 | 187 | 10
2262-1T2.PI.SS-WSC.9223 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 38 | 36 | 36 | 41 | 5 | 27
2262-1T2.PI.SS-WSC.9231 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 53 | 49 | 3 | 41 | 57 | 51 | 31 | 39
2262-1T2.PI.SS-WSC.9247 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 208 | 158 | 15 | 85 | 206 | 88 | 22 | 92 | 178
2262-1T2.PI.SS-WSC.9255 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 24 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WSC.9263 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 5 | 5 | 3
2262-1T2.PI.SS-WSC.9275 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 36 | 22 | 37
2262-2 T2.PI.SS-GSL. 9367 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 45
2262-2 T2.PI.SS-GSL. 9368 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 56 | 91
2262-2 T2.PI.SS-GSL. 9369 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 13 | 19 | 16 | 11
2262-2 T2.PI.SS-GVE. 9369 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 62 | 28
2262-2 T2.PI.SS-GVE. 9371 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 16 | 24
2262-2 T2.PI.SS-LPB. 9471 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 16 | 11 | 13 | 11 | 20
2262-2 T2.PI.SS-LPB. 9474 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 20
2262-2 T2.PI.SS-SPB. 9173 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 34 | 40 | 46 | 5 | 33 | 3 | 3
2262-2 T2.PI.SS-WCW. 9375 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 51 | 32 | 47 | 26
2262-2 T2.PI.SS-WCW. 9376 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 0
2262-2 T2.PI.SS-WGS. 9160 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 294 | 133 | 151 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WSC. 9379 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 32 | 68 | 63 | 145 | 202 | 24 | 136
2262-2 T2.PI.SS-WSC. 9380 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 3
2262-2 T2.PI.SS-WSC. 9381 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 25 | 12
2262-2 T2.PI.SS-WSC. 9382 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43
2262-2.T2.PI.HDPE-WCW.80 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 17 | 11 | 15
2262-2.T2.PI.SS-WPO.9650 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 71 | 65
2262-3.T2.PI.CS-GSL.1394 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1
2262-3.T2.PI.CS-GSL.1426 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43
2262-3.T2.PI.CS-GSL.1438 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 39 | 35 | 51 | 71 | 38 | 25 | 5 | 28
2262-3.T2.PI.CS-LPB.1442 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 5
2262-3.T2.PI.HDPE-WR.1440 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36
2262-3.T2.PI.PS.1434 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 9 | 7 | 7 | 11
2262-3.T2.PI.SS-LPB.1430 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9
2262-3.T2.PI.SS-SPB.1458 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 3 | 22 | 17 | 41 | 22 | 32
2262-3.T2.PI.SS-WSC.1422 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 134 | 22
2262-3.T2.PI.SS-WSC.1434 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 12
2272-2.T2.PI.1140 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 4 | 4 | 5 | 3 | 4 | 4 | 7
4242.T2.PI.CS-AIN.1663 | Actual Labor Units | 0 | 0 | 0 | 15 | 38 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1681 | Actual Labor Units | 0 | 0 | 6 | 6 | 10 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1701 | Actual Labor Units | 0 | 0 | 0 | 6 | 15 | 24 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1802 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1820 | Actual Labor Units | 0 | 0 | 0 | 0 | 7 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1842 | Actual Labor Units | 0 | 0 | 0 | 12 | 11 | 25 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GCD.1665 | Actual Labor Units | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GCD.1683 | Actual Labor Units | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GCD.1703 | Actual Labor Units | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1705 | Actual Labor Units | 0 | 0 | 19 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1856 | Actual Labor Units | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1685 | Actual Labor Units | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1707 | Actual Labor Units | 0 | 0 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1804 | Actual Labor Units | 0 | 0 | 0 | 20 | 2 | 22 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1822 | Actual Labor Units | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1709 | Actual Labor Units | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1824 | Actual Labor Units | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1844 | Actual Labor Units | 0 | 0 | 0 | 9 | 7 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-SPB.1711 | Actual Labor Units | 0 | 0 | 0 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-SPB.1808 | Actual Labor Units | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-SPB.1826 | Actual Labor Units | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1667 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 18
4242.T2.PI.FRP-LPA.1687 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
4242.T2.PI.FRP-LPA.1810 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
4242.T2.PI.FRP-LPA.1828 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39
4242.T2.PI.FRP-LPA.1846 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 12
4242.T2.PI.FRP-LSD.1830 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
4242.T2.PI.FRP-LSD.1848 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
4242.T2.PI.HDPE-WCW.1671 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1673 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1812 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1832 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 28 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1850 | Actual Labor Units | 0 | 0 | 0 | 0 | 9 | 49 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRA.1812 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRA.1834 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRA.1852 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1675 | Actual Labor Units | 0 | 0 | 0 | 0 | 14 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1814 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1836 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1677 | Actual Labor Units | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1697 | Actual Labor Units | 0 | 0 | 3 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1718 | Actual Labor Units | 0 | 0 | 0 | 1 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1816 | Actual Labor Units | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1838 | Actual Labor Units | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1679 | Actual Labor Units | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1699 | Actual Labor Units | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1720 | Actual Labor Units | 0 | 0 | 0 | 18 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1818 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1840 | Actual Labor Units | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1854 | Actual Labor Units | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.CV.1000 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 5 | 2 | 3 | 5 | 3 | 3 | 3 | 5 | 4 | 5
CN.2252-1.T2.MC.1000 | Actual Labor Units | 0 | 0 | 0 | 0 | 3 | 3 | 5 | 4 | 4 | 3 | 5 | 9 | 3 | 4 | 6 | 2 | 0 | 0
CN.2252-1.T2.MC.1010 | Actual Labor Units | 0 | 0 | 0 | 3 | 7 | 3 | 4 | 6 | 6 | 5 | 5 | 3 | 3 | 5 | 4 | 4 | 2 | 3
CN.2252-1.T2.MC.1030 | Actual Labor Units | 0 | 0 | 0 | 3 | 6 | 3 | 2 | 3 | 5 | 4 | 6 | 7 | 4 | 3 | 5 | 4 | 2 | 5
CN.2252-1.T2.MC.1040 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 12 | 19 | 20 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1050 | Actual Labor Units | 0 | 0 | 0 | 1 | 3 | 3 | 5 | 7 | 8 | 2 | 4 | 4 | 4 | 6 | 4 | 5 | 2 | 2
CN.2252-1.T2.MC.1060 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1070 | Actual Labor Units | 0 | 0 | 0 | 3 | 5 | 7 | 4 | 7 | 4 | 5 | 3 | 5 | 4 | 4 | 6 | 4 | 4 | 3
CN.2252-1.T2.MC.1090 | Actual Labor Units | 0 | 0 | 0 | 3 | 5 | 2 | 2 | 1 | 2 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 1 | 5
CN.2252-1.T2.MC.1140 | Actual Labor Units | 0 | 0 | 0 | 0 | 13 | 16 | 20 | 1 | 19 | 23 | 24 | 20 | 16 | 19 | 17 | 12 | 17 | 14
CN.2252-1.T2.MC.1150 | Actual Labor Units | 0 | 0 | 0 | 7 | 19 | 19 | 10 | 25 | 26 | 15 | 10 | 19 | 21 | 24 | 26 | 16 | 22 | 1
CN.2252-1.T2.MC.1180 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1190 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 2 | 2 | 1 | 2 | 4 | 3 | 4 | 5 | 1 | 3
CN.2252-1.T2.MC.1210 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1230 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98
CN.2252-1.T2.MC.1260 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 5 | 8 | 8 | 9 | 9 | 4 | 5 | 3 | 3 | 4 | 6
CN.2252-1.T2.MC.1280 | Actual Labor Units | 0 | 0 | 0 | 3 | 6 | 13 | 7 | 9 | 4 | 10 | 9 | 7 | 5 | 9 | 7 | 15 | 10 | 7
CN.2252-1.T2.MC.1295 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57
CN.2252-1.T2.MC.1483 | Actual Labor Units | 0 | 0 | 0 | 0 | 5 | 4 | 6 | 9 | 7 | 5 | 10 | 7 | 11 | 7 | 6 | 9 | 12 | 8
CN.2252-1.T2.MC.1582 | Actual Labor Units | 0 | 0 | 0 | 0 | 9 | 30 | 22 | 31 | 2 | 14 | 1 | 34 | 42 | 18 | 28 | 2 | 27 | 29
CN.2252-1.T2.PL.11102 | Actual Labor Units | 0 | 0 | 0 | 3 | 6 | 3 | 6 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.11106 | Actual Labor Units | 0 | 0 | 0 | 5 | 7 | 17 | 14 | 16 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.11110 | Actual Labor Units | 0 | 0 | 0 | 1 | 4 | 3 | 4 | 2 | 3 | 4 | 6 | 3 | 4 | 3 | 4 | 2 | 3 | 0
CN.2252-1.T2.PL.11114 | Actual Labor Units | 0 | 0 | 0 | 3 | 7 | 6 | 9 | 10 | 8 | 9 | 4 | 7 | 4 | 6 | 8 | 10 | 6 | 0
CN.2252-1.T2.PL.11118 | Actual Labor Units | 0 | 0 | 0 | 5 | 9 | 9 | 6 | 8 | 12 | 9 | 7 | 12 | 7 | 4 | 4 | 7 | 3 | 0
CN.2252-1.T2.PL.11122 | Actual Labor Units | 0 | 0 | 0 | 0 | 3 | 10 | 13 | 6 | 9 | 11 | 10 | 15 | 9 | 6 | 5 | 6 | 4 | 0
CN.2252-1.T2.PL.11126 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.1188 | Actual Labor Units | 0 | 0 | 2 | 6 | 7 | 10 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.1192 | Actual Labor Units | 0 | 0 | 0 | 5 | 4 | 10 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.1196 | Actual Labor Units | 0 | 0 | 0 | 5 | 5 | 2 | 8 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1338 | Actual Labor Units | 0 | 61 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1342 | Actual Labor Units | 0 | 96 | 402 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1346 | Actual Labor Units | 0 | 3 | 103 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1350 | Actual Labor Units | 0 | 7 | 84 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1354 | Actual Labor Units | 0 | 0 | 103 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1358 | Actual Labor Units | 0 | 0 | 307 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1362 | Actual Labor Units | 0 | 0 | 3 | 8 | 7 | 7 | 1 | 8 | 5 | 6 | 16 | 6 | 12 | 10 | 2 | 13 | 7 | 6
CN.2252-1.T2.ST.1366 | Actual Labor Units | 0 | 0 | 109 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1370 | Actual Labor Units | 0 | 0 | 0 | 72 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1374 | Actual Labor Units | 0 | 0 | 0 | 0 | 774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1378 | Actual Labor Units | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1382 | Actual Labor Units | 0 | 0 | 0 | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1386 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1390 | Actual Labor Units | 0 | 0 | 0 | 31 | 69 | 63 | 92 | 111 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1394 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 6 | 32 | 59 | 76 | 77 | 60 | 45 | 50 | 0 | 0 | 0
CN.2252-1.T2.ST.1398 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 57 | 40 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1399 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1402 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1406 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 339 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1410 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0
CN.2252-1.T2.ST.1414 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 165 | 0 | 0 | 0
CN.2252-1.T2.ST.1418 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0
CN.2252-1.T2.ST.1422 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97 | 402 | 0 | 0 | 0
CN.2252-1.T2.ST.1430 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 0 | 0
CN.2252-1.T2.ST.1434 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 0 | 0
CN.2252-1.T2.ST.1438 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 73
CN.2252-1.T2.ST.1442 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 70
CN.2252-1.T2.ST.1446 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 9 | 5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1454 | Actual Labor Units | 0 | 0 | 0 | 0 | 118 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1458 | Actual Labor Units | 0 | 0 | 0 | 0 | 39 | 3 | 65 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1462 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 14 | 30 | 47 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1466 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 21 | 38 | 53 | 76 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1470 | Actual Labor Units | 0 | 0 | 0 | 0 | 24 | 430 | 17 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1474 | Actual Labor Units | 0 | 0 | 0 | 0 | 78 | 134 | 170 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1478 | Actual Labor Units | 0 | 0 | 0 | 0 | 201 | 329 | 21 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1482 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 265 | 248 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1486 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 31 | 100 | 55 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1490 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 19 | 38 | 40 | 22 | 53 | 36
CN.2252-1.T2.ST.1494 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 57 | 46 | 68 | 60
CN.2252-1.T2.ST.1498 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 38 | 71 | 3
CN.2252-1.T2.ST.1502 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 2 | 13 | 22 | 16 | 9 | 15 | 23 | 22 | 20 | 24 | 18 | 24 | 11
CN.2252-1.T2.ST.1506 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 112 | 15 | 23 | 27
CN.2252-1.T2.ST.1510 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 2 | 9 | 8 | 6 | 9 | 6 | 11 | 12 | 6 | 6 | 9 | 6 | 8
CN.2252-2.T2.MC.1000 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 137 | 27 | 14
CN.2252-2.T2.MC.1020 | Actual Labor Units | 0 | 0 | 0 | 0 | 2 | 9 | 9 | 4 | 5 | 10 | 8 | 3 | 7 | 8 | 6 | 9 | 5 | 5
CN.2252-2.T2.MC.1030 | Actual Labor Units | 0 | 0 | 15 | 21 | 22 | 23 | 43 | 41 | 23 | 21 | 35 | 44 | 27 | 21 | 28 | 3 | 32 | 0
CN.2252-2.T2.MC.1040 | Actual Labor Units | 0 | 0 | 0 | 0 | 3 | 4 | 7 | 11 | 9 | 13 | 9 | 8 | 7 | 5 | 7 | 4 | 11 | 3
CN.2252-2.T2.MC.1050 | Actual Labor Units | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 2
CN.2252-2.T2.MC.1053 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1054 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 13 | 21
CN.2252-2.T2.PI.1092 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188
CN.2252-2.T2.ST.1230 | Actual Labor Units | 0 | 0 | 411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1240 | Actual Labor Units | 0 | 0 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1250 | Actual Labor Units | 0 | 0 | 0 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1260 | Actual Labor Units | 0 | 0 | 0 | 61 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1270 | Actual Labor Units | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1280 | Actual Labor Units | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1290 | Actual Labor Units | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1300 | Actual Labor Units | 0 | 0 | 0 | 36 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1310 | Actual Labor Units | 0 | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1324 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1328 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1332 | Actual Labor Units | 0 | 0 | 0 | 9 | 82 | 70 | 82 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1336 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1340 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1344 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1348 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 31 | 83 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1352 | Actual Labor Units | 0 | 0 | 0 | 13 | 8 | 68 | 53 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1356 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1360 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 15 | 13 | 10 | 9 | 15 | 10 | 9 | 0 | 0
CN.2252-2.T2.ST.1364 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 188 | 21 | 15 | 53 | 0
CN.2252-2.T2.ST.1368 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 13 | 15 | 12 | 9 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1372 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 195 | 263 | 27 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1376 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 157 | 133 | 117 | 7 | 110 | 17 | 207 | 145 | 44 | 0 | 0
CN.2252-2.T2.ST.1380 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2
CN.2252-2.T2.ST.1384 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 50 | 58 | 114
CN.2252-2.T2.ST.1388 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 58 | 45 | 88 | 10 | 7 | 61 | 40 | 99
CN.2252-2.T2.ST.1392 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2 | 12 | 12 | 15 | 12
CN.2252-3 T2.Insul.1223 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 115 | 8 | 67 | 25
CN.2252-3 T2.Insul.1294 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 98 | 101 | 126 | 71
CN.2252-3.T2.Insul.1296 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 47 | 0 | 0 | 0
CN.2252-3.T2.Insul.1298 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 0 | 0
CN.2252-3.T2.Insul.1300 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0
CN.2252-3.T2.Insul.1302 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0
CN.2252-3.T2.Insul.1304 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 326 | 289
CN.2252-3.T2.MC.1001 | Actual Labor Units | 0 | 0 | 805 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1200 | Actual Labor Units | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 4 | 4 | 3 | 4 | 3 | 3 | 4 | 3 | 0 | 0 | 0
CN.2252-3.T2.MC.1220 | Actual Labor Units | 0 | 0 | 0 | 1 | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 1 | 1 | 1
CN.2252-3.T2.MC.1272 | Actual Labor Units | 0 | 0 | 0 | 2 | 5 | 7 | 6 | 5 | 4 | 7 | 5 | 7 | 7 | 2 | 6 | 3 | 7 | 5
CN.2252-3.T2.MC.1276 | Actual Labor Units | 0 | 0 | 0 | 0 | 1 | 6 | 2 | 4 | 3 | 4 | 3 | 2 | 6 | 4 | 6 | 5 | 0 | 0
CN.2252-3.T2.MC.1283 | Actual Labor Units | 0 | 0 | 0 | 3 | 6 | 8 | 7 | 6 | 14 | 4 | 11 | 8 | 10 | 8 | 7 | 7 | 9 | 10
CN.2252-3.T2.MC.1285 | Actual Labor Units | 0 | 0 | 0 | 3 | 9 | 1 | 7 | 8 | 8 | 8 | 14 | 6 | 14 | 2 | 6 | 11 | 9 | 20
CN.2252-3.T2.MC.1290 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66
CN.2252-3.T2.MC.1291 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214
CN.2252-3.T2.ST.1180 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1190 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1200 | Actual Labor Units | 0 | 0 | 0 | 0 | 189 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1210 | Actual Labor Units | 0 | 0 | 0 | 49 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1220 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1230 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1250 | Actual Labor Units | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1260 | Actual Labor Units | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1270 | Actual Labor Units | 0 | 0 | 0 | 0 | 273 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1280 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 18 | 13 | 30 | 10 | 26 | 13 | 9 | 10 | 8 | 0
CN.2252-3.T2.ST.1290 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 126 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1300 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 44 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1310 | Actual Labor Units | 0 | 0 | 0 | 113 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1320 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1324 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11 | 12 | 7 | 8 | 9 | 2 | 0 | 0
CN.2252-3.T2.ST.1332 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 58 | 47 | 57 | 24 | 36 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1336 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 0 | 0
CN.2252-3.T2.ST.1344 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 46 | 40 | 24 | 0
CN.2252-3.T2.ST.1348 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0
CN.2252-3.T2.ST.1352 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 1
CN.2252-3.T2.ST.1360 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1364 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 2 | 5 | 3 | 4 | 3 | 5 | 2
CN.2252-3.T2.ST.1372 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 22 | 19 | 18 | 17 | 19 | 17 | 1 | 18 | 15 | 18 | 15
CN.2252-3.T2.ST.1376 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 7 | 9 | 12 | 8 | 12
CN.2252-4.T2.ST.1198 | Actual Labor Units | 0 | 0 | 0 | 0 | 27 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1202 | Actual Labor Units | 0 | 0 | 0 | 14 | 58 | 76 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1206 | Actual Labor Units | 0 | 0 | 0 | 8 | 57 | 39 | 57 | 27 | 21 | 41 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1210 | Actual Labor Units | 0 | 0 | 0 | 0 | 11 | 15 | 28 | 20 | 28 | 28 | 32 | 39 | 17 | 30 | 25 | 23 | 0 | 0
CN.2252-4.T2.ST.1214 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1218 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 3 | 15 | 20 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1222 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1226 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1230 | Actual Labor Units | 0 | 0 | 0 | 8 | 26 | 22 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1234 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 40 | 54 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1238 | Actual Labor Units | 0 | 0 | 0 | 7 | 22 | 37 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1242 | Actual Labor Units | 0 | 0 | 0 | 5 | 31 | 32 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1246 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 2 | 15 | 18 | 13 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1250 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 2 | 25 | 6 | 17 | 10 | 2 | 1 | 7 | 22 | 8 | 0 | 0 | 0
CN.2252-4.T2.ST.1254 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 16 | 30 | 32 | 20 | 18 | 28 | 26 | 2 | 36 | 16 | 0
CN.2252-4.T2.ST.1258 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 5 | 27 | 24 | 36 | 25 | 15 | 27 | 42 | 25 | 26 | 29 | 33 | 16
CN.2252-5.T2.MC.1286 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 4 | 5 | 5 | 3 | 7 | 5 | 5
CN.2252-5.T2.MC.1291 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 2 | 2 | 3 | 1 | 1 | 3 | 2
CN.2252-5.T2.MC.1374 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.MC.1378 | Actual Labor Units | 0 | 0 | 0 | 0 | 6 | 15 | 8 | 14 | 22 | 8 | 10 | 25 | 16 | 12 | 22 | 4 | 0 | 0
CN.2252-5.T2.MC.1381 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
CN.2252-5.T2.MC.1382 | Actual Labor Units | 0 | 0 | 0 | 0 | 3 | 5 | 10 | 9 | 7 | 11 | 6 | 5 | 6 | 7 | 4 | 3 | 0 | 0
CN.2252-5.T2.MC.1386 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 5 | 3 | 6 | 3 | 5 | 7 | 5 | 7 | 3 | 3
CN.2252-6.T2.ST.1380 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 134 | 19 | 66 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-6.T2.ST.1390 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 89
CN.2252-7.T2.ST.1400 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 13 | 7 | 1 | 20 | 26 | 16 | 10 | 20 | 11 | 15 | 1
CN.2262-4.T2.ST.1551 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 39 | 67 | 33
CN.2262-4.T2.ST.1554 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 2
CN.2262.T2.MC.1010 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 2 | 3 | 1 | 4 | 3 | 2 | 1 | 0
CN.2262.T2.MC.1020 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 6 | 5 | 3 | 4 | 5 | 7 | 4 | 0
CN.2262.T2.MC.1030 | Actual Labor Units | 0 | 0 | 3 | 4 | 6 | 5 | 4 | 2 | 4 | 3 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1040 | Actual Labor Units | 0 | 0 | 0 | 0 | 1 | 7 | 2 | 7 | 5 | 5 | 6 | 5 | 6 | 6 | 1 | 0 | 0 | 0
CN.2262.T2.MC.1060 | Actual Labor Units | 0 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1070 | Actual Labor Units | 0 | 0 | 1 | 3 | 2 | 1 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1080 | Actual Labor Units | 0 | 0 | 3 | 79 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1090 | Actual Labor Units | 0 | 0 | 3 | 9 | 6 | 8 | 5 | 9 | 6 | 8 | 9 | 6 | 4 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1100 | Actual Labor Units | 0 | 0 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 2 | 1 | 2 | 3 | 2 | 3 | 1 | 0 | 0
CN.2262.T2.MC.1120 | Actual Labor Units | 0 | 0 | 0 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1160 | Actual Labor Units | 0 | 0 | 0 | 62 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1172 | Actual Labor Units | 0 | 0 | 0 | 0 | 21 | 136 | 138 | 95 | 115 | 223 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1173 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 29 | 22 | 24 | 23 | 27 | 12 | 22 | 23 | 19 | 36
CN.2262.T2.MC.1174 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 3 | 4 | 4 | 3 | 3 | 0 | 0 | 0
CN.2262.T2.MC.1175 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1176 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1177 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1178 | Actual Labor Units | 0 | 0 | 0 | 0 | 3 | 13 | 8 | 9 | 12 | 9 | 7 | 11 | 9 | 5 | 12 | 2 | 0 | 0
CN.2262.T2.MC.1179 | Actual Labor Units | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1180 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1181 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1182 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9 | 14 | 7 | 2 | 12 | 8 | 13 | 7 | 4 | 0 | 0
CN.2262.T2.MC.1183 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 0 | 0
CN.2262.T2.MC.1187 | Actual Labor Units | 0 | 0 | 0 | 0 | 19 | 152 | 148 | 98 | 194 | 253 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1191 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 229 | 248
CN.2262.T2.MC.1199 | Actual Labor Units | 0 | 0 | 16 | 27 | 38 | 2 | 43 | 28 | 27 | 28 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1203 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 6 | 4 | 6 | 5 | 5 | 5
CN.2262.T2.MC.1211 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 5 | 7 | 9 | 2 | 0
CN.2262.T2.MC.1215 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 19 | 11
CN.2262.T2.MC.1219 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 17 | 13
CN.2262.T2.MC.1221 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 75 | 60 | 57 | 68
CN.2262.T2.MC.1225 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 0
CN.2262.T2.MC.1227 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 174 | 120
CN.2262.T2.ST.1304 | Actual Labor Units | 0 | 0 | 0 | 0 | 8 | 48 | 41 | 3 | 31 | 35 | 28 | 21 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1314 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 2 | 20 | 32 | 17 | 32 | 22 | 21 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1324 | Actual Labor Units | 0 | 0 | 0 | 0 | 19 | 32 | 60 | 80 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1334 | Actual Labor Units | 0 | 0 | 0 | 0 | 11 | 17 | 19 | 9 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1344 | Actual Labor Units | 0 | 0 | 0 | 0 | 7 | 23 | 15 | 20 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1354 | Actual Labor Units | 0 | 0 | 0 | 0 | 6 | 17 | 1 | 15 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1364 | Actual Labor Units | 0 | 0 | 0 | 0 | 10 | 16 | 23 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1374 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 19 | 10 | 9 | 2 | 9
CN.2262.T2.ST.1384 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 0 | 1 | 1 | 0 | 2 | 1 | 2
CN.2262.T2.ST.1394 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 20 | 62 | 5 | 56 | 52 | 8 | 32 | 55 | 25 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1404 | Actual Labor Units | 0 | 0 | 0 | 6 | 27 | 19 | 2 | 2 | 16 | 17 | 21 | 17 | 20 | 9 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1424 | Actual Labor Units | 0 | 0 | 0 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1434 | Actual Labor Units | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1444 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1454 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 5 | 20 | 33 | 19 | 27 | 3 | 3 | 35 | 21 | 14 | 13 | 15 | 1
CN.2262.T2.ST.1464 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 106 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1474 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 38 | 33 | 23 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1494 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 7 | 8 | 6 | 7 | 7 | 13 | 8 | 7
CN.2262.T2.ST.1504 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 73 | 99 | 71 | 13 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1514 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 29 | 11 | 19 | 10 | 0 | 0 | 0
CN.2262.T2.ST.1524 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 9 | 15 | 11 | 9 | 5 | 6 | 7 | 0
CN.2262.T2.ST.1534 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 64 | 47 | 8 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1544 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 14 | 9 | 1 | 18 | 13 | 0 | 0
CN.2262.T2.ST.1554 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 6 | 7 | 3 | 3 | 5 | 3 | 9 | 0
CN.2262.T2.ST.1564 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 45 | 83
CN.2262.T2.ST.1574 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 21 | 4 | 62 | 72 | 84 | 101 | 78 | 5 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1594 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295 | 28 | 0
CN.2262.T2.ST.1598 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 26 | 27
CN.2262.T2.ST.1602 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 127
CN.2262.T2.ST.1610 | Actual Labor Units | 0 | 0 | 0 | 0 | 17 | 92 | 58 | 16 | 13 | 65 | 163 | 120 | 7 | 106 | 86 | 59 | 81 | 69
CN.2262.T2.ST.1615 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9
CN.2262.T2.ST.1622 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
CN.2262.T2.ST.1625 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | 8
CN.2262.T2.ST.1634 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 28 | 42
CN.2262.T2.ST.1642 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 20 | 20 | 21 | 3 | 18 | 33 | 31 | 23 | 14
CN.2262.T2.ST.1643 | Actual Labor Units | 0 | 0 | 0 | 0 | 2 | 17 | 9 | 13 | 9 | 20 | 19 | 10 | 19 | 14 | 12 | 18 | 23 | 24
CN.2262.T2.ST.1678 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 438 | 548 | 721 | 494
CN.2272.T2.MC.1000 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1010 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 341 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1020 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1030 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 50 | 40 | 43 | 31
CN.2272.T2.MC.1040 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 0 | 0
CN.2272.T2.MC.1050 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
CN.2272.T2.MC.1080 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 602 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1090 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0
CN.2272.T2.MC.1100 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 53 | 79 | 72 | 68 | 91
CN.2272.T2.MC.1120 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1160 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14 | 7 | 3 | 11 | 7 | 11
CN.2272.T2.MC.1210 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1220 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 405 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1222 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 28 | 33 | 24 | 33 | 3 | 28 | 14 | 12 | 39 | 31 | 38 | 31 | 23
CN.2272.T2.ST.1320 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1330 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1340 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1350 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1360 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1364 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1368 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 57 | 6 | 0 | 0 | 0
CN.2272.T2.ST.1376 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1380 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1384 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 90 | 0 | 0 | 0
CN.2272.T2.ST.1388 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 49 | 4 | 62
CN.2272.T2.ST.1392 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1396 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1400 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3
CN.2272.T2.ST.1404 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 13 | 6 | 5 | 6
CN.2272.T2.ST.1408 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 8 | 12 | 8 | 5
CN.2272.T2.ST.1430 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 26 | 30 | 2 | 1 | 23 | 28 | 27 | 9 | 0
CN.2272.T2.ST.1461 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538 | 36 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1465 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 91 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1469 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 98 | 44 | 0 | 0
CN.2272.T2.ST.1485 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 128 | 91 | 0
CN.2272.T2.ST.1493 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 33 | 37
CN.2272.T2.ST.1497 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 21 | 34
CN.2272.T2.ST.1501 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 111 | 127
CN.2272.T2.ST.1505 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 71 | 99
CN.2272.T2.ST.1513 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 9
CN.2272.T2.ST.1598 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 82
CN.2272.T2.ST.1618 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0
CN.4242.T2.IN.1665 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 39
CN.4242.T2.PS.1637 | Actual Labor Units | 0 | 0 | 17 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1641 | Actual Labor Units | 0 | 32 | 33 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1645 | Actual Labor Units | 0 | 0 | 56 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1649 | Actual Labor Units | 0 | 0 | 0 | 0 | 4 | 3 | 4 | 4 | 5 | 3 | 3 | 3 | 5 | 4 | 4 | 3 | 4 | 5
CN.4242.T2.PS.1650 | Actual Labor Units | 0 | 0 | 0 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1653 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
CN.4242.T2.PS.1657 | Actual Labor Units | 0 | 13 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1661 | Actual Labor Units | 0 | 0 | 32 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.ST.1629 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0
CN.4242.T2.ST.1633 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71 | 0
CN.4242.T2.WW.1645 | Actual Labor Units | 0 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.WW.1653 | Actual Labor Units | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.WW.1661 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
CN.4242.T2.WW.1665 | Actual Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
CN.4242.T2.WW.1669 | Actual Labor Units | 0 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.WW.1673 | Actual Labor Units | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## remaining
Activity ID | Spreadsheet Field | 2021-09-25 | 2021-10-02 | 2021-10-09 | 2021-10-16 | 2021-10-23 | 2021-10-30 | 2021-11-06 | 2021-11-13 | 2021-11-20 | 2021-11-27 | 2021-12-04 | 2021-12-11 | 2021-12-18 | 2021-12-25 | 2022-01-01 | 2022-01-08 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-05 | 2022-02-12 | 2022-02-19 | 2022-02-26
2252-1.T2.PI.1095 | Remaining Labor Units | 2021-11-27: 186.82; 2021-12-04: 182.44; 2021-12-11: 155.9; 2022-01-01: 111.74
2252-1T2.PI.CS-AIN.1000 | Remaining Labor Units | 2021-10-30: 5.38; 2021-11-06: 13.44
2252-1T2.PI.CS-AIN.1032 | Remaining Labor Units | 2021-11-13: 276.12; 2021-11-20: 581.94
2252-1T2.PI.CS-AIN.1055 | Remaining Labor Units | 2021-09-25: 195.35
2252-1T2.PI.CS-AIN.1056 | Remaining Labor Units | 2021-10-23: 15.56; 2021-10-30: 327.65
2252-1T2.PI.CS-AIN.1061 | Remaining Labor Units | 2022-01-22: 69.65; 2022-01-29: 351.59; 2022-02-05: 336.84; 2022-02-12: 327.99; 2022-02-19: 11.5
2252-1T2.PI.CS-GCD.1003 | Remaining Labor Units | 2021-11-20: 45.16; 2021-11-27: 146.6; 2021-12-04: 46.77
2252-1T2.PI.CS-GCD.1045 | Remaining Labor Units | 2021-10-30: 31.6
2252-1T2.PI.CS-GSL.1006 | Remaining Labor Units | 2021-12-04: 134.2; 2021-12-11: 56.99
2252-1T2.PI.CS-GSL.1027 | Remaining Labor Units | 2021-12-11: 79.39
2252-1T2.PI.CS-GVE.1028 | Remaining Labor Units | 2021-10-30: 8.41
2252-1T2.PI.CS-GVE.1041 | Remaining Labor Units | 2021-10-02: 4.46; 2021-10-09: 31.65
2252-1T2.PI.CS-GVE.1042 | Remaining Labor Units | 2021-10-30: 58.53
2252-1T2.PI.CS-LPB.1022 | Remaining Labor Units
2252-1T2.PI.CS-LPB.1029 | Remaining Labor Units | 2021-10-30: 49.61; 2021-11-06: 152.71; 2021-11-13: 6.32
2252-1T2.PI.CS-LPB.1046 | Remaining Labor Units | 2021-11-06: 6.91; 2021-11-13: 5
2252-1T2.PI.CS-LPB.1047 | Remaining Labor Units | 2021-11-13: 128.44; 2021-11-20: 21.97
2252-1T2.PI.CS-LPN.1047 | Remaining Labor Units | 2021-11-13: 249.27; 2021-11-20: 48.65
2252-1T2.PI.CS-LSH.1048 | Remaining Labor Units | 2021-11-20: 58.2
2252-1T2.PI.CS-LSH.1049 | Remaining Labor Units | 2021-12-04: 46.35; 2021-12-11: 24.57
2252-1T2.PI.CS-SPB.1042 | Remaining Labor Units | 2021-10-09: 182.93; 2021-10-16: 44.49
2252-1T2.PI.CS-SPB.1043 | Remaining Labor Units | 2021-12-04: 48.88; 2021-12-11: 27.6
2252-1T2.PI.CS-WFI.1057 | Remaining Labor Units | 2021-09-25: 37.94; 2021-10-02: 16.55
2252-1T2.PI.CS-WFI.1058 | Remaining Labor Units | 2021-10-02: 198.15
2252-1T2.PI.FRP-LPA.1012 | Remaining Labor Units | 2021-11-13: 89.76; 2021-11-20: 82.14
2252-1T2.PI.FRP-LPA.1024 | Remaining Labor Units | 2022-02-19: 58.11; 2022-02-26: 23.23
2252-1T2.PI.HDPE-WCW.1015 | Remaining Labor Units | 2021-11-06: 215.48; 2021-11-13: 198.64
2252-1T2.PI.HDPE-WFI.1016 | Remaining Labor Units | 2022-01-29: 16.54
2252-1T2.PI.HDPE-WPO.1058 | Remaining Labor Units | 2021-09-25: 929.34
2252-1T2.PI.HDPE-WRO.1059 | Remaining Labor Units | 2021-10-02: 13.28
2252-1T2.PI.HDPE-WRO.1060 | Remaining Labor Units | 2021-11-13: 18.86; 2021-11-20: 13
2252-1T2.PI.SS-GVE.1018 | Remaining Labor Units | 2021-12-11: 49.15
2252-1T2.PI.SS-GVE.1030 | Remaining Labor Units | 2021-10-30: 16.53; 2021-11-06: 39.84; 2021-11-13: 14.86
2252-1T2.PI.SS-GVE.1036 | Remaining Labor Units | 2022-01-01: 44.95; 2022-01-08: 68.9
2252-1T2.PI.SS-GVE.1044 | Remaining Labor Units | 2021-10-16: 31.23
2252-1T2.PI.SS-LPB.1019 | Remaining Labor Units | 2021-11-27: 147.31; 2021-12-04: 144.4; 2021-12-11: 126.33; 2022-01-01: 118.25; 2022-01-08: 17.4
2252-1T2.PI.SS-LPB.1025 | Remaining Labor Units
2252-1T2.PI.SS-LPB.1051 | Remaining Labor Units | 2021-12-11: 26.38; 2022-01-01: 13.95
2252-1T2.PI.SS-SPB.1031 | Remaining Labor Units | 2021-10-30: 183.71; 2021-11-06: 229.24; 2021-11-13: 99.11
2252-1T2.PI.SS-SPB.1034 | Remaining Labor Units | 2021-10-16: 56.73; 2021-10-23: 336.96; 2021-10-30: 48.14
2252-1T2.PI.SS-SPB.1037 | Remaining Labor Units | 2021-10-30: 226.12; 2021-11-06: 29.15; 2021-11-13: 21.86; 2021-11-20: 199.25; 2021-11-27: 197; 2021-12-04: 157.21
2252-1T2.PI.SS-SPB.1039 | Remaining Labor Units | 2021-11-20: 35.47; 2021-11-27: 141.62; 2021-12-04: 155; 2021-12-11: 188.7; 2022-01-01: 12.98
2252-1T2.PI.SS-SPB.1052 | Remaining Labor Units | 2021-10-16: 13.62
2252-1T2.PI.SS-WCW.1020 | Remaining Labor Units | 2021-11-27: 7.2
2252-1T2.PI.SS-WPO.1060 | Remaining Labor Units | 2022-01-22: 7.92; 2022-01-29: 42.51; 2022-02-05: 385.6; 2022-02-12: 315.2
2252-1T2.PI.SS-WRO.1053 | Remaining Labor Units | 2021-10-23: 14.6; 2021-10-30: 89.66; 2021-11-06: 96.73; 2021-11-13: 75.69
2252-1T2.PI.SS-WRO.1059 | Remaining Labor Units | 2021-12-11: 83.78; 2022-01-01: 34.51; 2022-01-08: 234.28; 2022-01-15: 263.8; 2022-01-22: 152.47
2252-1T2.PI.SS-WRO.1060 | Remaining Labor Units | 2022-01-15: 4.44; 2022-01-22: 85.8; 2022-01-29: 21.28
2252-1T2.PI.SS-WSC.1021 | Remaining Labor Units | 2021-10-02: 12.62; 2021-10-09: 24.13; 2021-10-16: 199.31; 2021-10-23: 15.73; 2021-10-30: 183.6; 2021-11-06: 6.7
2252-1T2.PI.SS-WSC.1026 | Remaining Labor Units | 2021-11-13: 7.69
2252-1T2.PI.SS-WSC.1038 | Remaining Labor Units | 2021-12-04: 46.18; 2021-12-11: 128.6; 2022-01-01: 97.7
2252-1T2.PI.SS-WSC.1040 | Remaining Labor Units | 2022-01-01: 13.34; 2022-01-08: 23.43
2252-1T2.PI.SS-WSC.1054 | Remaining Labor Units | 2021-11-27: 225.48; 2021-12-04: 6.55
2252-2T2.PI.CS-AIN.1055 | Remaining Labor Units | 2021-11-20: 88.81; 2021-11-27: 5.69
2252-2T2.PI.CS-AIN.1075 | Remaining Labor Units | 2021-09-25: 89.28; 2021-10-02: 365.98
2252-2T2.PI.CS-AIN.1083 | Remaining Labor Units | 2021-12-04: 151.7; 2021-12-11: 121.64
2252-2T2.PI.CS-SPB.1047 | Remaining Labor Units | 2021-09-25: 22.6
2252-2T2.PI.CS-SPB.1061 | Remaining Labor Units
2252-2T2.PI.CS-SPB.1069 | Remaining Labor Units
2252-2T2.PI.CS-WFI.1077 | Remaining Labor Units | 2021-11-27: 15.46
2252-2T2.PI.CS-WFI.1081 | Remaining Labor Units | 2021-11-27: 37.34; 2021-12-04: 34.48
2252-2T2.PI.HDPE-WRO.10 | Remaining Labor Units | 2021-11-27: 15.59
2252-2T2.PI.SS-LPB.1049 | Remaining Labor Units
2252-2T2.PI.SS-LPB.1051 | Remaining Labor Units | 2021-11-27: 98.94; 2021-12-04: 16.68; 2021-12-11: 16.68; 2022-01-01: 35.96
2252-2T2.PI.SS-LPB.1057 | Remaining Labor Units | 2021-10-30: 3.75; 2021-11-06: 152.66; 2021-11-13: 118.61; 2021-11-20: 91.37; 2021-11-27: 2.15
2252-2T2.PI.SS-LPB.1063 | Remaining Labor Units | 2021-09-25: 8.26
2252-2T2.PI.SS-LPB.1067 | Remaining Labor Units
2252-2T2.PI.SS-LPB.1071 | Remaining Labor Units | 2021-09-25: 66.76; 2021-10-02: 44.4; 2021-10-09: 6.16; 2021-10-16: 6.39
2252-2T2.PI.SS-WPO.1085 | Remaining Labor Units | 2021-12-04: 142.45; 2021-12-11: 19.89; 2022-01-01: 148.86; 2022-01-08: 9.38
2252-2T2.PI.SS-WRO.1079 | Remaining Labor Units | 2022-01-08: 176.92; 2022-01-15: 27.19; 2022-01-22: 276.25; 2022-01-29: 6.28
2252-2T2.PI.SS-WSC.1053 | Remaining Labor Units | 2021-10-30: 176.49
2252-2T2.PI.SS-WSC.1059 | Remaining Labor Units | 2021-10-30: 1.79; 2021-11-06: 84.86
2252-2T2.PI.SS-WSC.1065 | Remaining Labor Units | 2021-09-25: 34.81
2252-2T2.PI.SS-WSC.1073 | Remaining Labor Units | 2021-10-02: 21.1; 2021-10-09: 235.16; 2021-10-16: 17.38
2252-3 T2.Flush. 9176 | Remaining Labor Units | 2021-10-30: 184.71; 2021-11-06: 362.36; 2021-11-13: 491.79; 2021-11-20: 44.42
2252-3 T2.Flush. 9178 | Remaining Labor Units | 2022-02-12: 141.12; 2022-02-19: 483.44
2252-3 T2.Flush. 9180 | Remaining Labor Units | 2022-01-08: 264.54
2252-3 T2.HYDRO. 9168 | Remaining Labor Units | 2021-10-09: 12.77; 2021-10-16: 183.11; 2021-10-23: 235.51; 2021-10-30: 83.17
2252-3 T2.HYDRO. 9170 | Remaining Labor Units | 2022-02-05: 79.37; 2022-02-12: 114.51
2252-3 T2.HYDRO. 9172 | Remaining Labor Units | 2022-01-15: 2.92; 2022-01-22: 121.81; 2022-01-29: 87.79
2252-3 T2.Insul. 9182 | Remaining Labor Units | 2022-01-29: 134.37; 2022-02-05: 197.55; 2022-02-12: 3.7
2252-3 T2.Insul. 9184 | Remaining Labor Units | 2021-11-20: 79.26; 2021-11-27: 57
2252-3 T2.Insul. 9186 | Remaining Labor Units | 2022-02-05: 63.39; 2022-02-12: 193.53; 2022-02-19: 125.68
2252-3 T2.Insul. 9188 | Remaining Labor Units | 2022-01-08: 3.61; 2022-01-15: 149.79; 2022-01-22: 152.73; 2022-01-29: 113.34; 2022-02-05: 135.4; 2022-02-12: 89.28; 2022-02-19: 13.46; 2022-02-26: 54.65
2252-3 T2.Insul. 9190 | Remaining Labor Units | 2022-02-05: 81.17; 2022-02-12: 172.55; 2022-02-19: 79.2
2252-3 T2.PI.CS-AIN. 9160 | Remaining Labor Units | 2021-10-30: 145.44
2252-3 T2.PI.CS-AIN. 9688 | Remaining Labor Units | 2021-10-30: 3.91; 2021-11-06: 18.83
2252-3 T2.PI.CS-GSL. 9153 | Remaining Labor Units | 2021-12-11: 16.32; 2022-01-01: 35.52; 2022-01-08: 3.14
2252-3 T2.PI.CS-GSL. 9164 | Remaining Labor Units | 2021-12-11: 174.37
2252-3 T2.PI.CS-LPB. 9372 | Remaining Labor Units | 2021-12-11: 245.24
2252-3 T2.PI.CS-LPB. 9374 | Remaining Labor Units | 2022-01-01: 143.81; 2022-01-08: 2.37
2252-3 T2.PI.CS-WFI. 9692 | Remaining Labor Units | 2021-11-13: 14.6; 2021-11-20: 15.24
2252-3 T2.PI.HDPE-WRO. 94 | Remaining Labor Units | 2021-10-02: 16.3; 2021-10-09: 76.78
2252-3 T2.PI.PS .9161 | Remaining Labor Units | 2021-10-16: 0.52; 2021-10-23: 3.82; 2021-10-30: 2.54; 2021-11-06: 3.93; 2021-11-13: 0.29
2252-3 T2.PI.PS .9163 | Remaining Labor Units | 2021-10-16: 1.98; 2021-10-23: 12.36; 2021-10-30: 7.75
2252-3 T2.PI.PS .9165 | Remaining Labor Units | 2021-10-16: 1.4; 2021-10-23: 5.98; 2021-10-30: 4.53; 2021-11-06: 5.45; 2021-11-13: 5.27; 2021-11-20: 3.86; 2021-11-27: 1.5
2252-3 T2.PI.PS .9167 | Remaining Labor Units | 2021-10-16: 1.39; 2021-10-23: 5.92; 2021-10-30: 7.59; 2021-11-06: 6.13; 2021-11-13: 8.11; 2021-11-20: 6.7; 2021-11-27: 7.66; 2021-12-04: 4.93
2252-3 T2.PI.PS .9169 | Remaining Labor Units | 2021-10-16: 5.24; 2021-10-23: 22.17
2252-3 T2.PI.PS .9171 | Remaining Labor Units | 2021-10-16: 1.21; 2021-10-23: 6.44
2252-3 T2.PI.PS .9173 | Remaining Labor Units | 2021-10-16: 2.65; 2021-10-23: 14
2252-3 T2.PI.PS .9175 | Remaining Labor Units | 2021-10-16: 5.6; 2021-10-23: 12.95
2252-3 T2.PI.SS-GSL. 9162 | Remaining Labor Units | 2022-01-08: 23.95; 2022-01-15: 174.37
2252-3 T2.PI.SS-GSL. 9164 | Remaining Labor Units | 2022-01-15: 12.13; 2022-01-22: 74.94; 2022-01-29: 44.82; 2022-02-05: 53.23; 2022-02-12: 25.77
2252-3 T2.PI.SS-GSL. 9366 | Remaining Labor Units | 2022-01-15: 24.86
2252-3 T2.PI.SS-GVE. 9154 | Remaining Labor Units | 2021-11-20: 7.1
2252-3 T2.PI.SS-GVE. 9164 | Remaining Labor Units | 2022-01-15: 45.14; 2022-01-22: 168.87
2252-3 T2.PI.SS-GVE. 9165 | Remaining Labor Units | 2021-11-27: 146.33; 2021-12-04: 51.16
2252-3 T2.PI.SS-GVE. 9166 | Remaining Labor Units | 2021-11-20: 73.22
2252-3 T2.PI.SS-GVE. 9368 | Remaining Labor Units | 2022-01-22: 17.6; 2022-01-29: 26.87
2252-3 T2.PI.SS-LPB. 9167 | Remaining Labor Units | 2022-01-08: 57.34; 2022-01-15: 141.15
2252-3 T2.PI.SS-LPB. 9170 | Remaining Labor Units | 2022-01-08: 162.82
2252-3 T2.PI.SS-LPB. 9270 | Remaining Labor Units | 2022-01-15: 13.83; 2022-01-22: 68.32; 2022-01-29: 46.85; 2022-02-05: 19.92
2252-3 T2.PI.SS-LPB. 9271 | Remaining Labor Units | 2022-02-05: 42.54
2252-3 T2.PI.SS-SPB. 9157 | Remaining Labor Units | 2021-09-25: 41.78; 2021-10-02: 88.81; 2021-10-09: 64.5
2252-3 T2.PI.SS-WCW. 9158 | Remaining Labor Units | 2021-11-13: 116.56; 2021-11-20: 53.58
2252-3 T2.PI.SS-WCW. 9172 | Remaining Labor Units | 2022-01-08: 65.12
2252-3 T2.PI.SS-WCW. 9174 | Remaining Labor Units | 2022-01-01: 223.99; 2022-01-08: 256.2
2252-3 T2.PI.SS-WCW. 9374 | Remaining Labor Units | 2022-01-08: 11.75; 2022-01-15: 1.15
2252-3 T2.PI.SS-WGS. 9159 | Remaining Labor Units | 2021-09-25: 76.83; 2021-10-02: 216.91; 2021-10-09: 16.36; 2021-10-16: 14.64
2252-3 T2.PI.SS-WPO. 9694 | Remaining Labor Units | 2021-09-25: 38.91; 2021-10-02: 117.59
2252-3 T2.PI.SS-WPR. 9176 | Remaining Labor Units | 2022-01-08: 28.9
2252-3 T2.PI.SS-WRO. 9160 | Remaining Labor Units | 2021-10-09: 42.29
2252-3 T2.PI.SS-WRO. 9690 | Remaining Labor Units | 2021-10-09: 216.36; 2021-10-16: 42.32
2252-3 T2.PI.SS-WRO. 9691 | Remaining Labor Units | 2021-10-09: 41.41; 2021-10-16: 47.61
2252-3 T2.PI.SS-WSC. 9162 | Remaining Labor Units | 2021-11-06: 1.21; 2021-11-13: 128.5; 2021-11-20: 17.79
2252-3 T2.PI.SS-WSC. 9178 | Remaining Labor Units | 2021-11-20: 31.52; 2021-11-27: 13.96
2252-3 T2.PI.SS-WSC. 9180 | Remaining Labor Units | 2021-11-27: 99.16; 2021-12-04: 5.72
2252-3 T2.PI.SS-WSC. 9276 | Remaining Labor Units | 2021-12-04: 13.32; 2021-12-11: 86.23
2252-3 T2.PI.SS-WSC. 9368 | Remaining Labor Units | 2022-01-01: 121.67; 2022-01-08: 91.23
2252-3 T2.PI.SS-WSC. 9370 | Remaining Labor Units | 2022-01-01: 19.64
2252-3 T2.PI.SS-WSC. 9376 | Remaining Labor Units | 2021-12-11: 142.44
2252-3 T2.PI.SS-WSC. 9378 | Remaining Labor Units | 2021-12-11: 2.97; 2022-01-01: 2.49
2252-4T2.PI.CS-AIN.1100 | Remaining Labor Units | 2021-12-11: 214.12; 2022-01-01: 16.32
2252-4T2.PI.CS-LPB.1081 | Remaining Labor Units
2252-4T2.PI.CS-LPB.1085 | Remaining Labor Units | 2022-01-01: 14.2; 2022-01-08: 12.5
2252-4T2.PI.CS-LPB.1087 | Remaining Labor Units
2252-4T2.PI.HDPE-WRO.89 | Remaining Labor Units | 2021-10-02: 55.86
2252-4T2.PI.HDPE-WRO.96 | Remaining Labor Units | 2021-12-04: 49.27; 2021-12-11: 4.27
2252-4T2.PI.SS-LPB.1075 | Remaining Labor Units | 2021-09-25: 243.79
2252-4T2.PI.SS-LPB.1092 | Remaining Labor Units | 2021-10-02: 15.88; 2021-10-09: 226.76; 2021-10-16: 145.7
2252-4T2.PI.SS-SPB.1077 | Remaining Labor Units | 2021-09-25: 188.31
2252-4T2.PI.SS-WPO.1102 | Remaining Labor Units | 2021-12-11: 77.74; 2022-01-01: 19
2252-4T2.PI.SS-WRO.1098 | Remaining Labor Units | 2021-12-11: 31.59
2252-4T2.PI.SS-WSC.1079 | Remaining Labor Units | 2021-09-25: 35.8; 2021-10-02: 85.2
2252-4T2.PI.SS-WSC.1083 | Remaining Labor Units | 2021-09-25: 8.71
2252-4T2.PI.SS-WSC.1094 | Remaining Labor Units | 2021-11-27: 53.87; 2021-12-04: 312.32; 2021-12-11: 266.9; 2022-01-01: 112.44
2252-5T2.PI.CS-AIN.1094 | Remaining Labor Units | 2021-10-30: 13.16; 2021-11-06: 81.48
2252-5T2.PI.SS-WPO.1098 | Remaining Labor Units | 2021-11-06: 11.75
2252-5T2.PI.SS-WRO.1096 | Remaining Labor Units | 2021-11-06: 12.76
2262-1T2.PI.9277 | Remaining Labor Units | 2021-10-30: 71.87; 2021-11-06: 71.62; 2021-11-13: 114.5; 2021-11-20: 77
2262-1T2.PI.CS-AIN.9203 | Remaining Labor Units | 2021-09-25: 345.82; 2021-10-02: 35.75; 2021-10-09: 55.26
2262-1T2.PI.CS-AIN.9207 | Remaining Labor Units | 2021-12-11: 131.26
2262-1T2.PI.CS-AIN.9279 | Remaining Labor Units | 2021-10-02: 179.42; 2021-10-09: 27.58; 2021-10-16: 374.11; 2021-10-23: 147.98
2262-1T2.PI.CS-AIN.9315 | Remaining Labor Units | 2021-11-27: 46.54; 2021-12-04: 231.75; 2021-12-11: 65.63
2262-1T2.PI.CS-LPB.9235 | Remaining Labor Units | 2021-10-30: 28.54
2262-1T2.PI.CS-WFI.9283 | Remaining Labor Units | 2021-10-09: 547.1
2262-1T2.PI.CS-WFI.9299 | Remaining Labor Units | 2021-10-09: 17.51
2262-1T2.PI.HDPE-WCW.9239 | Remaining Labor Units | 2021-11-06: 188.9
2262-1T2.PI.HDPE-WCW.9259 | Remaining Labor Units | 2021-11-13: 14.3
2262-1T2.PI.HDPE-WRO.9291 | Remaining Labor Units | 2021-10-23: 21.5; 2021-10-30: 16.74
2262-1T2.PI.SS-GVE.9195 | Remaining Labor Units | 2021-10-30: 14.42; 2021-11-06: 1.87
2262-1T2.PI.SS-GVE.9215 | Remaining Labor Units | 2021-10-16: 9.32
2262-1T2.PI.SS-GVE.9243 | Remaining Labor Units | 2021-09-25: 36.96
2262-1T2.PI.SS-LPB.9199 | Remaining Labor Units | 2021-11-13: 21.23
2262-1T2.PI.SS-LPB.9251 | Remaining Labor Units
2262-1T2.PI.SS-LPB.9267 | Remaining Labor Units | 2021-11-06: 0.5; 2021-11-13: 35.27
2262-1T2.PI.SS-SPB.9207 | Remaining Labor Units | 2021-12-11: 24.6
2262-1T2.PI.SS-SPB.9219 | Remaining Labor Units | 2021-10-16: 24.7; 2021-10-23: 262.62; 2021-10-30: 63.77
2262-1T2.PI.SS-SPB.9227 | Remaining Labor Units | 2021-11-20: 157.12
2262-1T2.PI.SS-SPB.9271 | Remaining Labor Units | 2021-11-13: 8.91; 2021-11-20: 7.5
2262-1T2.PI.SS-WPO.9303 | Remaining Labor Units | 2021-09-25: 171.7; 2021-10-02: 61.57
2262-1T2.PI.SS-WRO.9295 | Remaining Labor Units
2262-1T2.PI.SS-WRO.9311 | Remaining Labor Units | 2021-11-06: 0.7; 2021-11-13: 7.3
2262-1T2.PI.SS-WRO.9312 | Remaining Labor Units | 2021-11-13: 12.87; 2021-11-20: 126.27; 2021-11-27: 151.73; 2021-12-04: 124.96
2262-1T2.PI.SS-WSC.9211 | Remaining Labor Units | 2021-12-11: 6.32; 2022-01-01: 56.31; 2022-01-08: 7.77; 2022-01-15: 86; 2022-01-22: 48.25
2262-1T2.PI.SS-WSC.9223 | Remaining Labor Units | 2021-11-06: 375.9; 2021-11-13: 33.98
2262-1T2.PI.SS-WSC.9231 | Remaining Labor Units | 2021-11-13: 123.16
2262-1T2.PI.SS-WSC.9247 | Remaining Labor Units | 2021-09-25: 297.19; 2021-10-02: 1.2
2262-1T2.PI.SS-WSC.9255 | Remaining Labor Units
2262-1T2.PI.SS-WSC.9263 | Remaining Labor Units | 2021-11-06: 0.16; 2021-11-13: 1.83
2262-1T2.PI.SS-WSC.9275 | Remaining Labor Units | 2021-11-13: 27.98
2262-2 T2.Flush. 9181 | Remaining Labor Units | 2021-11-20: 12.35; 2021-11-27: 43.9
2262-2 T2.Flush. 9182 | Remaining Labor Units | 2021-10-30: 32.6; 2021-11-06: 184.65; 2021-11-13: 157.7; 2021-11-20: 52.6
2262-2 T2.Flush. 9183 | Remaining Labor Units | 2021-10-09: 199.44
2262-2 T2.Flush. 9184 | Remaining Labor Units | 2021-11-06: 27.55; 2021-11-13: 923.42
2262-2 T2.HYDRO. 9173 | Remaining Labor Units | 2021-10-09: 4.96; 2021-10-16: 239.4; 2021-10-23: 214.44; 2021-10-30: 162.4
2262-2 T2.HYDRO. 9174 | Remaining Labor Units | 2021-09-25: 185.3; 2021-10-02: 27.54; 2021-10-09: 46.46
2262-2 T2.HYDRO. 9175 | Remaining Labor Units | 2021-11-13: 21.45; 2021-11-20: 48.59
2262-2 T2.Insul. 9191 | Remaining Labor Units | 2021-10-23: 4.29; 2021-10-30: 223.85; 2021-11-06: 159.26; 2021-11-13: 29.86; 2021-11-20: 241.25; 2021-11-27: 147.23; 2021-12-04: 166.75; 2021-12-11: 184.8; 2022-01-01: 155.81
2262-2 T2.Insul. 9192 | Remaining Labor Units | 2021-11-20: 22.25; 2021-11-27: 264.41; 2021-12-04: 214.95; 2021-12-11: 257.8; 2022-01-01: 239.44
2262-2 T2.Insul. 9193 | Remaining Labor Units | 2021-10-02: 234.4; 2021-10-09: 177.2; 2021-10-16: 4.37
2262-2 T2.Insul. 9194 | Remaining Labor Units | 2021-11-13: 138.36; 2021-11-20: 589.38; 2021-11-27: 353.23; 2021-12-04: 55.59; 2021-12-11: 424.6
2262-2 T2.Insul. 9195 | Remaining Labor Units | 2021-11-27: 133.63; 2021-12-04: 22.22; 2021-12-11: 228; 2022-01-01: 113.73
2262-2 T2.PI.SS-GSL. 9367 | Remaining Labor Units | 2021-10-16: 59.1
2262-2 T2.PI.SS-GSL. 9368 | Remaining Labor Units | 2021-10-16: 9.45; 2021-10-23: 11.71
2262-2 T2.PI.SS-GSL. 9369 | Remaining Labor Units | 2021-10-23: 1.92; 2021-10-30: 26.35; 2021-11-06: 34.95; 2021-11-13: 13.5
2262-2 T2.PI.SS-GSL. 9372 | Remaining Labor Units | 2021-10-23: 15.81
2262-2 T2.PI.SS-GVE. 9369 | Remaining Labor Units | 2021-09-25: 9.52
2262-2 T2.PI.SS-GVE. 9371 | Remaining Labor Units | 2021-09-25: 8.21; 2021-10-02: 26.43; 2021-10-09: 0.45
2262-2 T2.PI.SS-GVE. 9372 | Remaining Labor Units | 2021-10-16: 72.9; 2021-10-23: 3.86
2262-2 T2.PI.SS-GVE. 9373 | Remaining Labor Units | 2021-10-23: 126.75
2262-2 T2.PI.SS-GVE. 9697 | Remaining Labor Units | 2021-10-23: 0.71; 2021-10-30: 18.77
2262-2 T2.PI.SS-LPB. 9471 | Remaining Labor Units | 2021-10-02: 52.5
2262-2 T2.PI.SS-LPB. 9473 | Remaining Labor Units | 2021-10-02: 166.6; 2021-10-09: 25.89
2262-2 T2.PI.SS-LPB. 9474 | Remaining Labor Units | 2021-10-09: 37.52; 2021-10-16: 71.73; 2021-10-23: 6.55; 2021-10-30: 57.62; 2021-11-06: 84.58; 2021-11-13: 3.31
2262-2 T2.PI.SS-LPB. 9475 | Remaining Labor Units | 2021-11-13: 9.43; 2021-11-20: 6.79
2262-2 T2.PI.SS-SPB. 9173 | Remaining Labor Units | 2021-10-09: 72.6
2262-2 T2.PI.SS-SPB. 9390 | Remaining Labor Units | 2021-11-27: 6.69; 2021-12-04: 43.41; 2021-12-11: 36.1; 2022-01-01: 1.1
2262-2 T2.PI.SS-SPB. 9391 | Remaining Labor Units | 2022-01-01: 52.6; 2022-01-08: 1.66
2262-2 T2.PI.SS-WCW. 9375 | Remaining Labor Units | 2021-11-06: 1.18; 2021-11-13: 212.98; 2021-11-20: 62.59
2262-2 T2.PI.SS-WCW. 9376 | Remaining Labor Units
2262-2 T2.PI.SS-WCW. 9377 | Remaining Labor Units | 2021-11-20: 36.23; 2021-11-27: 1.51
2262-2 T2.PI.SS-WCW. 9378 | Remaining Labor Units | 2021-11-27: 358.17
2262-2 T2.PI.SS-WGS. 9160 | Remaining Labor Units
2262-2 T2.PI.SS-WGS. 9705 | Remaining Labor Units | 2021-12-11: 8.73
2262-2 T2.PI.SS-WGS. 9707 | Remaining Labor Units | 2021-12-11: 95.58
2262-2 T2.PI.SS-WPR. 9177 | Remaining Labor Units | 2021-11-27: 25.96
2262-2 T2.PI.SS-WSC. 9379 | Remaining Labor Units | 2021-09-25: 98.85
2262-2 T2.PI.SS-WSC. 9380 | Remaining Labor Units | 2021-10-09: 2.36
2262-2 T2.PI.SS-WSC. 9381 | Remaining Labor Units | 2021-10-09: 3.31; 2021-10-16: 74.65
2262-2 T2.PI.SS-WSC. 9382 | Remaining Labor Units | 2021-10-16: 132.64; 2021-10-23: 184.18; 2021-10-30: 141.52
2262-2 T2.PI.SS-WSC. 9384 | Remaining Labor Units | 2021-10-30: 12.51
2262-2 T2.PI.SS-WSC. 9385 | Remaining Labor Units | 2021-10-30: 5.2; 2021-11-06: 67.84
2262-2 T2.PI.SS-WSC. 9386 | Remaining Labor Units | 2021-11-06: 132.54
2262-2 T2.PI.SS-WWW. 9709 | Remaining Labor Units | 2021-09-25: 41.31
2262-2.T2.PI.CS-GSL.9203 | Remaining Labor Units | 2021-10-09: 3.18; 2021-10-16: 73.98
2262-2.T2.PI.CS-GVE.9190 | Remaining Labor Units | 2021-10-30: 51.22
2262-2.T2.PI.CS-LPB.9189 | Remaining Labor Units | 2021-09-25: 16.52; 2021-10-02: 12.14
2262-2.T2.PI.CS-LPN.9179 | Remaining Labor Units | 2021-09-25: 55.66
2262-2.T2.PI.CS-WFI.9646 | Remaining Labor Units | 2021-12-04: 27.88
2262-2.T2.PI.HDPE-WCW.80 | Remaining Labor Units | 2021-10-02: 43.64
2262-2.T2.PI.HDPE-WRO.92 | Remaining Labor Units | 2021-12-04: 111.76; 2021-12-11: 13.26
2262-2.T2.PI.SS-LPB.9181 | Remaining Labor Units | 2021-09-25: 344.31
2262-2.T2.PI.SS-SPB.9223 | Remaining Labor Units | 2021-10-09: 467.64
2262-2.T2.PI.SS-WPO.9650 | Remaining Labor Units | 2021-11-27: 37.72; 2021-12-04: 238.1
2262-2.T2.PI.SS-WRO.9654 | Remaining Labor Units | 2021-12-11: 39.86
2262-2.T2.PI.SS-WSC.9239 | Remaining Labor Units | 2021-11-20: 96.96; 2021-11-27: 158.81
2262-3.T2.PI.1435 | Remaining Labor Units | 2021-10-09: 13.79; 2021-10-16: 24.27
2262-3.T2.PI.CS-GSL.1394 | Remaining Labor Units | 2021-09-25: 5.28
2262-3.T2.PI.CS-GSL.1426 | Remaining Labor Units | 2021-09-25: 27.4
2262-3.T2.PI.CS-GSL.1438 | Remaining Labor Units | 2021-09-25: 13.18; 2021-10-02: 125.9
2262-3.T2.PI.CS-LPB.1442 | Remaining Labor Units | 2021-09-25: 6.57
2262-3.T2.PI.CS-LPN.1446 | Remaining Labor Units | 2021-09-25: 33.19; 2021-10-02: 164.1; 2021-10-09: 194.45; 2021-10-16: 157.72; 2021-10-23: 11.25
2262-3.T2.PI.CS-WRA.1439 | Remaining Labor Units | 2021-10-16: 18.12
2262-3.T2.PI.HDPE-WR.1440 | Remaining Labor Units | 2021-10-16: 29.44
2262-3.T2.PI.PS.1434 | Remaining Labor Units | 2021-10-16: 1.66; 2021-10-23: 59.7
2262-3.T2.PI.SS-LPB.1430 | Remaining Labor Units
2262-3.T2.PI.SS-SPB.1454 | Remaining Labor Units | 2021-09-25: 86.59
2262-3.T2.PI.SS-SPB.1458 | Remaining Labor Units | 2021-10-02: 8.88; 2021-10-09: 41.77; 2021-10-16: 9.36
2262-3.T2.PI.SS-WSC.1422 | Remaining Labor Units | 2021-09-25: 14.98
2262-3.T2.PI.SS-WSC.1434 | Remaining Labor Units | 2021-09-25: 2.18
2272-1.T2.PI.1224 | Remaining Labor Units | 2021-10-16: 38.15; 2021-10-23: 158.5; 2021-10-30: 122.11
2272-1.T2.PI.1225 | Remaining Labor Units | 2021-10-30: 63.29; 2021-11-06: 179.75; 2021-11-13: 218.29; 2021-11-20: 217.8
2272-1.T2.PI.1228 | Remaining Labor Units | 2021-11-20: 6.59; 2021-11-27: 153.42; 2021-12-04: 22.63; 2021-12-11: 18.23
2272-1.T2.PI.1229 | Remaining Labor Units | 2021-12-11: 8.11; 2022-01-01: 273.44; 2022-01-08: 333.26; 2022-01-15: 357.46
2272-1.T2.PI.1230 | Remaining Labor Units | 2022-01-01: 123.11
2272-1.T2.PI.1232 | Remaining Labor Units | 2022-01-01: 1.99; 2022-01-08: 221.31; 2022-01-15: 77.71
2272-1.T2.PI.1233 | Remaining Labor Units | 2022-01-15: 277.62; 2022-01-22: 141.17
2272-1.T2.PI.1234 | Remaining Labor Units | 2022-01-22: 191.96; 2022-01-29: 358.1
2272-1.T2.PI.1235 | Remaining Labor Units | 2022-01-29: 7.15; 2022-02-05: 116.53; 2022-02-12: 113.57; 2022-02-19: 64.92
2272-1.T2.PI.1236 | Remaining Labor Units | 2022-01-29: 58.61; 2022-02-05: 21.42; 2022-02-12: 218.91; 2022-02-19: 93.19
2272-1.T2.PI.1238 | Remaining Labor Units | 2022-01-29: 17.83; 2022-02-05: 192.26; 2022-02-12: 242.51; 2022-02-19: 69.85
2272-2.T2.HY.1164 | Remaining Labor Units | 2022-01-22: 6.51; 2022-01-29: 284.43; 2022-02-05: 139.74
2272-2.T2.IN.1168 | Remaining Labor Units | 2022-01-29: 1.58; 2022-02-05: 259.7; 2022-02-12: 287.23; 2022-02-19: 186.21
2272-2.T2.PI.1140 | Remaining Labor Units | 2021-11-20: 27.75; 2021-11-27: 82.82; 2021-12-04: 1.92
2272-2.T2.PI.1144 | Remaining Labor Units | 2021-12-04: 345.6
2272-2.T2.PI.1146 | Remaining Labor Units | 2021-12-04: 23.89; 2021-12-11: 254.24
2272-2.T2.PI.1148 | Remaining Labor Units | 2021-12-11: 16.69; 2022-01-01: 38.57
2272-2.T2.PI.1150 | Remaining Labor Units | 2022-01-01: 135.83; 2022-01-08: 5.34
2272-2.T2.PI.1152 | Remaining Labor Units | 2022-01-01: 48.3; 2022-01-08: 115.96
2272-2.T2.PI.1154 | Remaining Labor Units | 2022-01-08: 14.96; 2022-01-15: 139.2; 2022-01-22: 4.71
2272-2.T2.PI.1156 | Remaining Labor Units | 2022-01-08: 14.97; 2022-01-15: 125.54; 2022-01-22: 54.58
2272-2.T2.PI.1158 | Remaining Labor Units | 2022-01-22: 7.12
2272-2.T2.PI.1162 | Remaining Labor Units | 2022-01-08: 48.24; 2022-01-15: 253.95; 2022-01-22: 215.92
2272-2.T2.PI.1166 | Remaining Labor Units | 2022-01-15: 98.47; 2022-01-22: 235.67
4242.T2.PI.CS-AIN.1663 | Remaining Labor Units
4242.T2.PI.CS-AIN.1681 | Remaining Labor Units
4242.T2.PI.CS-AIN.1701 | Remaining Labor Units
4242.T2.PI.CS-AIN.1722 | Remaining Labor Units | 2021-12-04: 29.45
4242.T2.PI.CS-AIN.1746 | Remaining Labor Units | 2021-11-13: 39.4
4242.T2.PI.CS-AIN.1774 | Remaining Labor Units | 2021-09-25: 29.41; 2021-10-02: 28.29
4242.T2.PI.CS-AIN.1802 | Remaining Labor Units
4242.T2.PI.CS-AIN.1820 | Remaining Labor Units
4242.T2.PI.CS-AIN.1842 | Remaining Labor Units
4242.T2.PI.CS-GCD.1665 | Remaining Labor Units
4242.T2.PI.CS-GCD.1683 | Remaining Labor Units
4242.T2.PI.CS-GCD.1703 | Remaining Labor Units
4242.T2.PI.CS-GSL.1705 | Remaining Labor Units
4242.T2.PI.CS-GSL.1724 | Remaining Labor Units | 2021-12-04: 4.5
4242.T2.PI.CS-GSL.1748 | Remaining Labor Units | 2021-11-13: 54.54
4242.T2.PI.CS-GSL.1776 | Remaining Labor Units | 2021-10-02: 53.15
4242.T2.PI.CS-GSL.1856 | Remaining Labor Units
4242.T2.PI.CS-GSL.1858 | Remaining Labor Units | 2022-01-01: 14.58; 2022-01-08: 136.78
4242.T2.PI.CS-GSL.1860 | Remaining Labor Units | 2022-01-08: 86.35; 2022-01-15: 134.34
4242.T2.PI.CS-GSL.1862 | Remaining Labor Units | 2022-01-15: 13.84; 2022-01-22: 62.58; 2022-01-29: 65.63; 2022-02-05: 23.98
4242.T2.PI.CS-LCC.1750 | Remaining Labor Units | 2021-11-20: 48.55
4242.T2.PI.CS-LCC.1778 | Remaining Labor Units | 2021-10-02: 23.97; 2021-10-09: 3.81
4242.T2.PI.CS-LPB.1685 | Remaining Labor Units
4242.T2.PI.CS-LPB.1707 | Remaining Labor Units
4242.T2.PI.CS-LPB.1726 | Remaining Labor Units | 2021-12-04: 18.99; 2021-12-11: 43.96
4242.T2.PI.CS-LPB.1752 | Remaining Labor Units | 2021-11-20: 55.16; 2021-11-27: 38.33
4242.T2.PI.CS-LPB.1780 | Remaining Labor Units | 2021-10-09: 78.22
4242.T2.PI.CS-LPB.1804 | Remaining Labor Units
4242.T2.PI.CS-LPB.1822 | Remaining Labor Units
4242.T2.PI.CS-LSH.1709 | Remaining Labor Units
4242.T2.PI.CS-LSH.1728 | Remaining Labor Units | 2021-12-11: 18.64
4242.T2.PI.CS-LSH.1754 | Remaining Labor Units | 2021-11-27: 16.89
4242.T2.PI.CS-LSH.1782 | Remaining Labor Units | 2021-10-09: 2.29; 2021-10-16: 6.6
4242.T2.PI.CS-LSH.1806 | Remaining Labor Units | 2021-09-25: 13.48
4242.T2.PI.CS-LSH.1824 | Remaining Labor Units
4242.T2.PI.CS-LSH.1844 | Remaining Labor Units
4242.T2.PI.CS-SPB.1711 | Remaining Labor Units
4242.T2.PI.CS-SPB.1730 | Remaining Labor Units | 2021-12-11: 2.83
4242.T2.PI.CS-SPB.1756 | Remaining Labor Units | 2021-11-27: 24.59
4242.T2.PI.CS-SPB.1784 | Remaining Labor Units | 2021-10-30: 34.35
4242.T2.PI.CS-SPB.1808 | Remaining Labor Units
4242.T2.PI.CS-SPB.1826 | Remaining Labor Units
4242.T2.PI.FRP-LPA.1667 | Remaining Labor Units
4242.T2.PI.FRP-LPA.1687 | Remaining Labor Units
4242.T2.PI.FRP-LPA.1712 | Remaining Labor Units | 2021-10-09: 2.72; 2021-10-16: 69.97
4242.T2.PI.FRP-LPA.1732 | Remaining Labor Units | 2021-11-20: 23.9
4242.T2.PI.FRP-LPA.1758 | Remaining Labor Units | 2021-11-06: 19.89; 2021-11-13: 11.79
4242.T2.PI.FRP-LPA.1786 | Remaining Labor Units | 2021-10-02: 16.14
4242.T2.PI.FRP-LPA.1810 | Remaining Labor Units
4242.T2.PI.FRP-LPA.1828 | Remaining Labor Units
4242.T2.PI.FRP-LPA.1846 | Remaining Labor Units
4242.T2.PI.FRP-LSD.1713 | Remaining Labor Units | 2021-10-16: 37.47
4242.T2.PI.FRP-LSD.1734 | Remaining Labor Units | 2021-11-20: 35.7
4242.T2.PI.FRP-LSD.1788 | Remaining Labor Units | 2021-10-02: 52.6
4242.T2.PI.FRP-LSD.1830 | Remaining Labor Units
4242.T2.PI.FRP-LSD.1848 | Remaining Labor Units
4242.T2.PI.FRP-WCW.1669 | Remaining Labor Units | 2021-09-25: 181.46; 2021-10-02: 54.78
4242.T2.PI.FRP-WCW.1689 | Remaining Labor Units | 2021-10-02: 12.74; 2021-10-09: 33.24
4242.T2.PI.FRP-WCW.1714 | Remaining Labor Units | 2021-10-16: 17.21; 2021-10-23: 79.87; 2021-10-30: 45.59
4242.T2.PI.FRP-WCW.1736 | Remaining Labor Units | 2021-11-20: 52.86; 2021-11-27: 18.49
4242.T2.PI.FRP-WCW.1760 | Remaining Labor Units | 2021-11-13: 71.16
4242.T2.PI.FRP-WCW.1790 | Remaining Labor Units | 2021-10-02: 33.49; 2021-10-09: 35.79
4242.T2.PI.HDPE-WCW.1671 | Remaining Labor Units
4242.T2.PI.HDPE-WCW.1691 | Remaining Labor Units | 2021-10-02: 16.9
4242.T2.PI.HDPE-WCW.1715 | Remaining Labor Units | 2021-10-09: 18.98
4242.T2.PI.HDPE-WCW.1738 | Remaining Labor Units | 2021-11-13: 21.11
4242.T2.PI.HDPE-WCW.1762 | Remaining Labor Units | 2021-10-09: 32.13
4242.T2.PI.HDPE-WPO.1673 | Remaining Labor Units
4242.T2.PI.HDPE-WPO.1693 | Remaining Labor Units | 2021-10-02: 49.54
4242.T2.PI.HDPE-WPO.1716 | Remaining Labor Units | 2021-10-09: 2.74
4242.T2.PI.HDPE-WPO.1764 | Remaining Labor Units | 2021-10-09: 41.29
4242.T2.PI.HDPE-WPO.1792 | Remaining Labor Units | 2021-09-25: 41.16
4242.T2.PI.HDPE-WPO.1812 | Remaining Labor Units
4242.T2.PI.HDPE-WPO.1832 | Remaining Labor Units
4242.T2.PI.HDPE-WPO.1850 | Remaining Labor Units
4242.T2.PI.HDPE-WRA.1766 | Remaining Labor Units | 2021-10-09: 16.3
4242.T2.PI.HDPE-WRA.1794 | Remaining Labor Units | 2021-09-25: 8.32
4242.T2.PI.HDPE-WRA.1812 | Remaining Labor Units
4242.T2.PI.HDPE-WRA.1834 | Remaining Labor Units
4242.T2.PI.HDPE-WRA.1852 | Remaining Labor Units
4242.T2.PI.HDPE-WRO.1675 | Remaining Labor Units
4242.T2.PI.HDPE-WRO.1695 | Remaining Labor Units | 2021-10-02: 32.9
4242.T2.PI.HDPE-WRO.1717 | Remaining Labor Units | 2021-10-09: 47.45
4242.T2.PI.HDPE-WRO.1740 | Remaining Labor Units | 2021-11-13: 49.72; 2021-11-20: 3.93
4242.T2.PI.HDPE-WRO.1768 | Remaining Labor Units | 2021-11-06: 41.97
4242.T2.PI.HDPE-WRO.1796 | Remaining Labor Units | 2021-09-25: 31.3; 2021-10-02: 6.44
4242.T2.PI.HDPE-WRO.1814 | Remaining Labor Units
4242.T2.PI.HDPE-WRO.1836 | Remaining Labor Units
4242.T2.PI.INS.1792 | Remaining Labor Units | 2021-10-02: 7.14
4242.T2.PI.INS.1794 | Remaining Labor Units | 2021-10-02: 9.44; 2021-10-09: 1.93
4242.T2.PI.INS.1796 | Remaining Labor Units | 2021-10-16: 12.7; 2021-10-23: 18.79; 2021-10-30: 12.37
4242.T2.PI.INS.1798 | Remaining Labor Units | 2021-12-11: 15.89; 2022-01-01: 23.41
4242.T2.PI.INS.1800 | Remaining Labor Units | 2021-11-27: 22.46; 2021-12-04: 22.68
4242.T2.PI.INS.1802 | Remaining Labor Units | 2021-10-23: 17.8; 2021-10-30: 15.88; 2021-11-06: 23.25; 2021-11-13: 4.96
4242.T2.PI.INS.1804 | Remaining Labor Units | 2021-09-25: 9.16
4242.T2.PI.INS.1806 | Remaining Labor Units | 2021-09-25: 13.8
4242.T2.PI.INS.1808 | Remaining Labor Units | 2021-09-25: 6.83
4242.T2.PI.INS.1810 | Remaining Labor Units | 2021-09-25: 2.66; 2021-10-02: 0.58
4242.T2.PI.INS.1812 | Remaining Labor Units | 2022-01-01: 0.11; 2022-01-08: 0.14
4242.T2.PI.INS.1814 | Remaining Labor Units | 2022-01-01: 0.7; 2022-01-08: 0.7; 2022-01-15: 0.9
4242.T2.PI.INS.1816 | Remaining Labor Units | 2022-01-29: 4.38; 2022-02-05: 2.8
4242.T2.PI.SS-LPB.1677 | Remaining Labor Units
4242.T2.PI.SS-LPB.1697 | Remaining Labor Units
4242.T2.PI.SS-LPB.1718 | Remaining Labor Units
4242.T2.PI.SS-LPB.1742 | Remaining Labor Units | 2021-12-11: 31.11; 2022-01-01: 8.28
4242.T2.PI.SS-LPB.1770 | Remaining Labor Units | 2021-11-27: 43.23; 2021-12-04: 7.24
4242.T2.PI.SS-LPB.1798 | Remaining Labor Units | 2021-11-06: 43.88
4242.T2.PI.SS-LPB.1816 | Remaining Labor Units
4242.T2.PI.SS-LPB.1838 | Remaining Labor Units
4242.T2.PI.SS-WSC.1679 | Remaining Labor Units
4242.T2.PI.SS-WSC.1699 | Remaining Labor Units
4242.T2.PI.SS-WSC.1720 | Remaining Labor Units
4242.T2.PI.SS-WSC.1744 | Remaining Labor Units | 2022-01-01: 69.57
4242.T2.PI.SS-WSC.1772 | Remaining Labor Units | 2021-12-04: 46.18
4242.T2.PI.SS-WSC.1800 | Remaining Labor Units | 2021-11-06: 16.95; 2021-11-13: 31.43
4242.T2.PI.SS-WSC.1818 | Remaining Labor Units
4242.T2.PI.SS-WSC.1840 | Remaining Labor Units
4242.T2.PI.SS-WSC.1854 | Remaining Labor Units
CN.2252-1.T2.CV.1000 | Remaining Labor Units | 2021-11-13: 38.81
CN.2252-1.T2.MC.1000 | Remaining Labor Units
CN.2252-1.T2.MC.1010 | Remaining Labor Units | 2021-09-25: 29.8
CN.2252-1.T2.MC.1030 | Remaining Labor Units | 2021-09-25: 33.66
CN.2252-1.T2.MC.1040 | Remaining Labor Units
CN.2252-1.T2.MC.1050 | Remaining Labor Units | 2021-10-02: 2.7; 2021-10-09: 16.56
CN.2252-1.T2.MC.1060 | Remaining Labor Units
CN.2252-1.T2.MC.1070 | Remaining Labor Units | 2021-09-25: 7.4; 2021-10-02: 32.16
CN.2252-1.T2.MC.1090 | Remaining Labor Units | 2021-09-25: 28.63
CN.2252-1.T2.MC.1140 | Remaining Labor Units | 2021-10-23: 2.61
CN.2252-1.T2.MC.1150 | Remaining Labor Units | 2021-10-09: 95.64
CN.2252-1.T2.MC.1170 | Remaining Labor Units | 2021-10-09: 32.42; 2021-10-16: 446.43
CN.2252-1.T2.MC.1180 | Remaining Labor Units
CN.2252-1.T2.MC.1190 | Remaining Labor Units | 2021-11-13: 29.76; 2021-11-20: 7.35
CN.2252-1.T2.MC.1210 | Remaining Labor Units
CN.2252-1.T2.MC.1230 | Remaining Labor Units | 2021-10-16: 71.32; 2021-10-23: 256.94
CN.2252-1.T2.MC.1260 | Remaining Labor Units | 2021-11-20: 1.21
CN.2252-1.T2.MC.1280 | Remaining Labor Units | 2021-10-02: 57.23
CN.2252-1.T2.MC.1295 | Remaining Labor Units | 2021-11-06: 92.69; 2021-11-13: 193.8; 2021-11-20: 42.47
CN.2252-1.T2.MC.1483 | Remaining Labor Units | 2021-10-30: 3.69; 2021-11-06: 112.23; 2021-11-13: 4.72
CN.2252-1.T2.MC.1582 | Remaining Labor Units | 2021-10-23: 19.63; 2021-10-30: 147.29
CN.2252-1.T2.PI.1080 | Remaining Labor Units | 2021-10-09: 12.39; 2021-10-16: 198.68; 2021-10-23: 169.74; 2021-10-30: 268.1; 2021-11-06: 177.51; 2021-11-13: 191.5
CN.2252-1.T2.PI.1090 | Remaining Labor Units | 2022-01-01: 2.3; 2022-01-08: 123.75; 2022-01-15: 2.83; 2022-01-22: 158.6; 2022-01-29: 145.1; 2022-02-05: 144.13; 2022-02-12: 147.9
CN.2252-1.T2.PI.1094 | Remaining Labor Units | 2022-01-01: 98.44; 2022-01-08: 113.55; 2022-01-15: 113.28
CN.2252-1.T2.PL.11102 | Remaining Labor Units
CN.2252-1.T2.PL.11106 | Remaining Labor Units
CN.2252-1.T2.PL.11110 | Remaining Labor Units
CN.2252-1.T2.PL.11114 | Remaining Labor Units
CN.2252-1.T2.PL.11118 | Remaining Labor Units
CN.2252-1.T2.PL.11122 | Remaining Labor Units
CN.2252-1.T2.PL.11126 | Remaining Labor Units
CN.2252-1.T2.PL.1188 | Remaining Labor Units
CN.2252-1.T2.PL.1192 | Remaining Labor Units
CN.2252-1.T2.PL.1196 | Remaining Labor Units
CN.2252-1.T2.ST.1338 | Remaining Labor Units
CN.2252-1.T2.ST.1342 | Remaining Labor Units
CN.2252-1.T2.ST.1346 | Remaining Labor Units
CN.2252-1.T2.ST.1350 | Remaining Labor Units
CN.2252-1.T2.ST.1354 | Remaining Labor Units
CN.2252-1.T2.ST.1358 | Remaining Labor Units
CN.2252-1.T2.ST.1362 | Remaining Labor Units | 2021-09-25: 1.59
CN.2252-1.T2.ST.1366 | Remaining Labor Units
CN.2252-1.T2.ST.1370 | Remaining Labor Units
CN.2252-1.T2.ST.1374 | Remaining Labor Units
CN.2252-1.T2.ST.1378 | Remaining Labor Units
CN.2252-1.T2.ST.1382 | Remaining Labor Units
CN.2252-1.T2.ST.1386 | Remaining Labor Units
CN.2252-1.T2.ST.1390 | Remaining Labor Units
CN.2252-1.T2.ST.1394 | Remaining Labor Units
CN.2252-1.T2.ST.1398 | Remaining Labor Units
CN.2252-1.T2.ST.1399 | Remaining Labor Units
CN.2252-1.T2.ST.1402 | Remaining Labor Units
CN.2252-1.T2.ST.1406 | Remaining Labor Units
CN.2252-1.T2.ST.1410 | Remaining Labor Units
CN.2252-1.T2.ST.1414 | Remaining Labor Units
CN.2252-1.T2.ST.1418 | Remaining Labor Units
CN.2252-1.T2.ST.1422 | Remaining Labor Units
CN.2252-1.T2.ST.1430 | Remaining Labor Units
CN.2252-1.T2.ST.1434 | Remaining Labor Units
CN.2252-1.T2.ST.1438 | Remaining Labor Units
CN.2252-1.T2.ST.1442 | Remaining Labor Units
CN.2252-1.T2.ST.1446 | Remaining Labor Units
CN.2252-1.T2.ST.1454 | Remaining Labor Units
CN.2252-1.T2.ST.1458 | Remaining Labor Units
CN.2252-1.T2.ST.1462 | Remaining Labor Units
CN.2252-1.T2.ST.1466 | Remaining Labor Units
CN.2252-1.T2.ST.1470 | Remaining Labor Units
CN.2252-1.T2.ST.1474 | Remaining Labor Units
CN.2252-1.T2.ST.1478 | Remaining Labor Units
CN.2252-1.T2.ST.1482 | Remaining Labor Units
CN.2252-1.T2.ST.1486 | Remaining Labor Units
CN.2252-1.T2.ST.1490 | Remaining Labor Units | 2021-09-25: 31.27
CN.2252-1.T2.ST.1494 | Remaining Labor Units | 2021-09-25: 15.84
CN.2252-1.T2.ST.1498 | Remaining Labor Units | 2021-09-25: 22.54
CN.2252-1.T2.ST.1502 | Remaining Labor Units | 2021-09-25: 2.3; 2021-10-02: 27.63; 2021-10-09: 1.35
CN.2252-1.T2.ST.1506 | Remaining Labor Units | 2021-09-25: 113.78; 2021-10-02: 117; 2021-10-09: 93.75; 2021-10-16: 153.28; 2021-10-23: 121.1; 2021-10-30: 91.71; 2021-11-06: 69.31
CN.2252-1.T2.ST.1510 | Remaining Labor Units | 2021-10-23: 121.72; 2021-10-30: 117.6; 2021-11-06: 61.4
CN.2252-2.T2.MC.1000 | Remaining Labor Units | 2021-10-09: 169.65; 2021-10-16: 259.86; 2021-10-23: 214.34; 2021-10-30: 26.87; 2021-11-06: 93.88
CN.2252-2.T2.MC.1020 | Remaining Labor Units | 2021-09-25: 73.23
CN.2252-2.T2.MC.1030 | Remaining Labor Units
CN.2252-2.T2.MC.1040 | Remaining Labor Units
CN.2252-2.T2.MC.1050 | Remaining Labor Units | 2021-09-25: 3.21
CN.2252-2.T2.MC.1051 | Remaining Labor Units | 2021-09-25: 5.89; 2021-10-02: 94.89; 2021-10-09: 3.26
CN.2252-2.T2.MC.1052 | Remaining Labor Units | 2021-09-25: 13.5
CN.2252-2.T2.MC.1053 | Remaining Labor Units
CN.2252-2.T2.MC.1054 | Remaining Labor Units | 2021-11-20: 32.42; 2021-11-27: 6.97
CN.2252-2.T2.PI.1092 | Remaining Labor Units | 2021-12-11: 183.74; 2022-01-01: 289.91; 2022-01-08: 249.99; 2022-01-15: 15.77
CN.2252-2.T2.ST.1230 | Remaining Labor Units
CN.2252-2.T2.ST.1240 | Remaining Labor Units
CN.2252-2.T2.ST.1250 | Remaining Labor Units
CN.2252-2.T2.ST.1260 | Remaining Labor Units
CN.2252-2.T2.ST.1270 | Remaining Labor Units
CN.2252-2.T2.ST.1280 | Remaining Labor Units
CN.2252-2.T2.ST.1290 | Remaining Labor Units
CN.2252-2.T2.ST.1300 | Remaining Labor Units
CN.2252-2.T2.ST.1310 | Remaining Labor Units
CN.2252-2.T2.ST.1324 | Remaining Labor Units
CN.2252-2.T2.ST.1328 | Remaining Labor Units
CN.2252-2.T2.ST.1332 | Remaining Labor Units
CN.2252-2.T2.ST.1336 | Remaining Labor Units
CN.2252-2.T2.ST.1340 | Remaining Labor Units
CN.2252-2.T2.ST.1344 | Remaining Labor Units
CN.2252-2.T2.ST.1348 | Remaining Labor Units
CN.2252-2.T2.ST.1352 | Remaining Labor Units
CN.2252-2.T2.ST.1356 | Remaining Labor Units
CN.2252-2.T2.ST.1360 | Remaining Labor Units
CN.2252-2.T2.ST.1364 | Remaining Labor Units
CN.2252-2.T2.ST.1368 | Remaining Labor Units
CN.2252-2.T2.ST.1372 | Remaining Labor Units
CN.2252-2.T2.ST.1376 | Remaining Labor Units
CN.2252-2.T2.ST.1380 | Remaining Labor Units | 2021-09-25: 3.44; 2021-10-02: 1.1
CN.2252-2.T2.ST.1384 | Remaining Labor Units | 2021-10-02: 11.45; 2021-10-09: 5.51
CN.2252-2.T2.ST.1388 | Remaining Labor Units | 2021-09-25: 75.87; 2021-10-02: 75.65; 2021-10-09: 49.32; 2021-10-16: 44.19; 2021-10-23: 38.85
CN.2252-2.T2.ST.1392 | Remaining Labor Units | 2021-10-23: 21.77; 2021-10-30: 52.45; 2021-11-06: 55.57
CN.2252-3 T2.Insul.1223 | Remaining Labor Units | 2021-11-20: 37.36; 2021-11-27: 77.66; 2021-12-04: 44.32
CN.2252-3 T2.Insul.1294 | Remaining Labor Units | 2021-11-06: 34.68; 2021-11-13: 57.37; 2021-11-20: 14.98
CN.2252-3.T2.Insul.1296 | Remaining Labor Units
CN.2252-3.T2.Insul.1298 | Remaining Labor Units
CN.2252-3.T2.Insul.1300 | Remaining Labor Units
CN.2252-3.T2.Insul.1302 | Remaining Labor Units
CN.2252-3.T2.Insul.1304 | Remaining Labor Units | 2021-12-04: 55.84; 2021-12-11: 13.87; 2022-01-01: 73.65; 2022-01-08: 1.32; 2022-01-15: 111.6; 2022-01-22: 79.81; 2022-01-29: 124.82; 2022-02-05: 67.76
CN.2252-3.T2.MC.1001 | Remaining Labor Units
CN.2252-3.T2.MC.1200 | Remaining Labor Units
CN.2252-3.T2.MC.1220 | Remaining Labor Units | 2021-09-25: 6.53
CN.2252-3.T2.MC.1272 | Remaining Labor Units | 2021-09-25: 23.14
CN.2252-3.T2.MC.1276 | Remaining Labor Units
CN.2252-3.T2.MC.1283 | Remaining Labor Units | 2021-09-25: 31.72
CN.2252-3.T2.MC.1285 | Remaining Labor Units | 2021-09-25: 61.51
CN.2252-3.T2.MC.1290 | Remaining Labor Units
CN.2252-3.T2.MC.1291 | Remaining Labor Units
CN.2252-3.T2.ST.1180 | Remaining Labor Units
CN.2252-3.T2.ST.1190 | Remaining Labor Units
CN.2252-3.T2.ST.1200 | Remaining Labor Units
CN.2252-3.T2.ST.1210 | Remaining Labor Units
CN.2252-3.T2.ST.1220 | Remaining Labor Units
CN.2252-3.T2.ST.1230 | Remaining Labor Units
CN.2252-3.T2.ST.1250 | Remaining Labor Units
CN.2252-3.T2.ST.1260 | Remaining Labor Units
CN.2252-3.T2.ST.1270 | Remaining Labor Units
CN.2252-3.T2.ST.1280 | Remaining Labor Units
CN.2252-3.T2.ST.1290 | Remaining Labor Units
CN.2252-3.T2.ST.1300 | Remaining Labor Units
CN.2252-3.T2.ST.1310 | Remaining Labor Units
CN.2252-3.T2.ST.1320 | Remaining Labor Units
CN.2252-3.T2.ST.1324 | Remaining Labor Units
CN.2252-3.T2.ST.1332 | Remaining Labor Units
CN.2252-3.T2.ST.1336 | Remaining Labor Units
CN.2252-3.T2.ST.1344 | Remaining Labor Units
CN.2252-3.T2.ST.1348 | Remaining Labor Units
CN.2252-3.T2.ST.1352 | Remaining Labor Units
CN.2252-3.T2.ST.1360 | Remaining Labor Units
CN.2252-3.T2.ST.1364 | Remaining Labor Units
CN.2252-3.T2.ST.1368 | Remaining Labor Units | 2021-09-25: 185.29
CN.2252-3.T2.ST.1372 | Remaining Labor Units | 2021-09-25: 92.69; 2021-10-02: 188.22; 2021-10-09: 122.23; 2021-10-16: 51.69
CN.2252-3.T2.ST.1376 | Remaining Labor Units | 2021-10-09: 25.4; 2021-10-16: 34.73
CN.2252-4.T2.PI.1094 | Remaining Labor Units | 2022-01-01: 12.48; 2022-01-08: 222.64; 2022-01-15: 265.74; 2022-01-22: 23.48
CN.2252-4.T2.PI.1096 | Remaining Labor Units | 2022-01-08: 165.96; 2022-01-15: 356.4; 2022-01-22: 277.96
CN.2252-4.T2.ST.1198 | Remaining Labor Units
CN.2252-4.T2.ST.1202 | Remaining Labor Units
CN.2252-4.T2.ST.1206 | Remaining Labor Units
CN.2252-4.T2.ST.1210 | Remaining Labor Units
CN.2252-4.T2.ST.1214 | Remaining Labor Units
CN.2252-4.T2.ST.1218 | Remaining Labor Units
CN.2252-4.T2.ST.1222 | Remaining Labor Units
CN.2252-4.T2.ST.1226 | Remaining Labor Units
CN.2252-4.T2.ST.1230 | Remaining Labor Units
CN.2252-4.T2.ST.1234 | Remaining Labor Units
CN.2252-4.T2.ST.1238 | Remaining Labor Units
CN.2252-4.T2.ST.1242 | Remaining Labor Units
CN.2252-4.T2.ST.1246 | Remaining Labor Units
CN.2252-4.T2.ST.1250 | Remaining Labor Units
CN.2252-4.T2.ST.1254 | Remaining Labor Units
CN.2252-4.T2.ST.1258 | Remaining Labor Units | 2021-09-25: 46.67
CN.2252-5.T2.MC.1286 | Remaining Labor Units | 2021-09-25: 22.79; 2021-10-02: 35.19
CN.2252-5.T2.MC.1288 | Remaining Labor Units | 2021-10-16: 129.38; 2021-10-23: 339.42; 2021-10-30: 235.53
CN.2252-5.T2.MC.1291 | Remaining Labor Units | 2021-10-02: 42.19
CN.2252-5.T2.MC.1374 | Remaining Labor Units
CN.2252-5.T2.MC.1378 | Remaining Labor Units
CN.2252-5.T2.MC.1381 | Remaining Labor Units | 2021-10-02: 5.49; 2021-10-09: 6.76
CN.2252-5.T2.MC.1382 | Remaining Labor Units
CN.2252-5.T2.MC.1386 | Remaining Labor Units | 2021-09-25: 7.38
CN.2252-5.T2.PI.1098 | Remaining Labor Units | 2021-11-06: 4.77; 2021-11-13: 158.8; 2021-11-20: 167.95; 2021-11-27: 163.25; 2021-12-04: 114.83; 2021-12-11: 145.46; 2022-01-01: 18.69
CN.2252-5.T2.PI.1100 | Remaining Labor Units | 2021-11-27: 3.8; 2021-12-04: 5.54; 2021-12-11: 5.58; 2022-01-01: 3.46; 2022-01-08: 0.7
CN.2252-6.T2.ST.1380 | Remaining Labor Units
CN.2252-6.T2.ST.1390 | Remaining Labor Units | 2021-09-25: 14.63
CN.2252-7.T2.ST.1400 | Remaining Labor Units | 2021-09-25: 62.37
CN.2252-7.T2.ST.1410 | Remaining Labor Units | 2021-09-25: 24.94; 2021-10-02: 1.44; 2021-10-09: 3.97
CN.2252-7.T2.ST.1412 | Remaining Labor Units | 2021-10-09: 33.62; 2021-10-16: 9.11
CN.2262-4.T2.ST.1551 | Remaining Labor Units | 2021-11-27: 19.47; 2021-12-04: 16.8; 2021-12-11: 75.64; 2022-01-01: 5.5
CN.2262-4.T2.ST.1554 | Remaining Labor Units | 2022-01-01: 6.24
CN.2262.T2.MC.1010 | Remaining Labor Units
CN.2262.T2.MC.1020 | Remaining Labor Units
CN.2262.T2.MC.1030 | Remaining Labor Units
CN.2262.T2.MC.1040 | Remaining Labor Units
CN.2262.T2.MC.1060 | Remaining Labor Units
CN.2262.T2.MC.1070 | Remaining Labor Units
CN.2262.T2.MC.1080 | Remaining Labor Units
CN.2262.T2.MC.1090 | Remaining Labor Units
CN.2262.T2.MC.1100 | Remaining Labor Units
CN.2262.T2.MC.1120 | Remaining Labor Units
CN.2262.T2.MC.1160 | Remaining Labor Units
CN.2262.T2.MC.1172 | Remaining Labor Units
CN.2262.T2.MC.1173 | Remaining Labor Units | 2021-09-25: 19.31
CN.2262.T2.MC.1174 | Remaining Labor Units
CN.2262.T2.MC.1175 | Remaining Labor Units
CN.2262.T2.MC.1176 | Remaining Labor Units
CN.2262.T2.MC.1177 | Remaining Labor Units
CN.2262.T2.MC.1178 | Remaining Labor Units
CN.2262.T2.MC.1179 | Remaining Labor Units
CN.2262.T2.MC.1180 | Remaining Labor Units
CN.2262.T2.MC.1181 | Remaining Labor Units
CN.2262.T2.MC.1182 | Remaining Labor Units
CN.2262.T2.MC.1183 | Remaining Labor Units
CN.2262.T2.MC.1187 | Remaining Labor Units
CN.2262.T2.MC.1191 | Remaining Labor Units | 2021-09-25: 54.49; 2021-10-02: 76.74; 2021-10-09: 65.22; 2021-10-16: 18.21
CN.2262.T2.MC.1195 | Remaining Labor Units | 2021-10-16: 341.83; 2021-10-23: 31.3
CN.2262.T2.MC.1199 | Remaining Labor Units
CN.2262.T2.MC.1203 | Remaining Labor Units | 2021-10-23: 163.58
CN.2262.T2.MC.1211 | Remaining Labor Units
CN.2262.T2.MC.1215 | Remaining Labor Units
CN.2262.T2.MC.1219 | Remaining Labor Units
CN.2262.T2.MC.1221 | Remaining Labor Units | 2021-11-20: 33.62
CN.2262.T2.MC.1225 | Remaining Labor Units
CN.2262.T2.MC.1227 | Remaining Labor Units | 2021-11-20: 38.88; 2021-11-27: 149.99; 2021-12-04: 111.5; 2021-12-11: 45.81
CN.2262.T2.ST.1304 | Remaining Labor Units
CN.2262.T2.ST.1314 | Remaining Labor Units
CN.2262.T2.ST.1324 | Remaining Labor Units
CN.2262.T2.ST.1334 | Remaining Labor Units
CN.2262.T2.ST.1344 | Remaining Labor Units
CN.2262.T2.ST.1354 | Remaining Labor Units
CN.2262.T2.ST.1364 | Remaining Labor Units
CN.2262.T2.ST.1374 | Remaining Labor Units | 2021-09-25: 1.5
CN.2262.T2.ST.1384 | Remaining Labor Units | 2021-09-25: 1.2
CN.2262.T2.ST.1394 | Remaining Labor Units
CN.2262.T2.ST.1404 | Remaining Labor Units
CN.2262.T2.ST.1424 | Remaining Labor Units
CN.2262.T2.ST.1434 | Remaining Labor Units
CN.2262.T2.ST.1444 | Remaining Labor Units
CN.2262.T2.ST.1454 | Remaining Labor Units | 2021-09-25: 12.19
CN.2262.T2.ST.1464 | Remaining Labor Units
CN.2262.T2.ST.1474 | Remaining Labor Units
CN.2262.T2.ST.1494 | Remaining Labor Units | 2021-09-25: 8.41
CN.2262.T2.ST.1504 | Remaining Labor Units
CN.2262.T2.ST.1514 | Remaining Labor Units
CN.2262.T2.ST.1524 | Remaining Labor Units
CN.2262.T2.ST.1534 | Remaining Labor Units
CN.2262.T2.ST.1544 | Remaining Labor Units
CN.2262.T2.ST.1554 | Remaining Labor Units
CN.2262.T2.ST.1564 | Remaining Labor Units | 2021-09-25: 17.97
CN.2262.T2.ST.1574 | Remaining Labor Units
CN.2262.T2.ST.1594 | Remaining Labor Units
CN.2262.T2.ST.1598 | Remaining Labor Units | 2021-09-25: 73.78
CN.2262.T2.ST.1602 | Remaining Labor Units | 2021-09-25: 63.3; 2021-10-02: 82.25
CN.2262.T2.ST.1610 | Remaining Labor Units | 2021-09-25: 17.67; 2021-10-02: 123.48; 2021-10-09: 66.94
CN.2262.T2.ST.1614 | Remaining Labor Units | 2021-10-30: 273.71; 2021-11-06: 341.39; 2021-11-13: 361.29; 2021-11-20: 295.71; 2021-11-27: 18.32
CN.2262.T2.ST.1615 | Remaining Labor Units | 2021-09-25: 1.72; 2021-10-02: 1.31
CN.2262.T2.ST.1618 | Remaining Labor Units | 2021-10-09: 34.21; 2021-10-16: 18.19
CN.2262.T2.ST.1622 | Remaining Labor Units | 2021-09-25: 63.94; 2021-10-02: 61.64; 2021-10-09: 52.67; 2021-10-16: 74.32; 2021-10-23: 13.15
CN.2262.T2.ST.1625 | Remaining Labor Units | 2021-10-02: 9.56
CN.2262.T2.ST.1634 | Remaining Labor Units | 2021-10-02: 29
CN.2262.T2.ST.1638 | Remaining Labor Units | 2021-10-02: 37.53; 2021-10-09: 167.1; 2021-10-16: 199.62; 2021-10-23: 149.48; 2021-10-30: 142.13
CN.2262.T2.ST.1642 | Remaining Labor Units | 2021-10-30: 24.22
CN.2262.T2.ST.1643 | Remaining Labor Units | 2021-10-16: 0.7; 2021-10-23: 9.3; 2021-10-30: 7.89; 2021-11-06: 7.5; 2021-11-13: 1.69
CN.2262.T2.ST.1644 | Remaining Labor Units | 2021-10-30: 11.1; 2021-11-06: 152.68; 2021-11-13: 24.58
CN.2262.T2.ST.1678 | Remaining Labor Units | 2021-10-23: 86.69; 2021-10-30: 112.39; 2021-11-06: 73.84; 2021-11-13: 7.64; 2021-11-20: 119.45; 2021-11-27: 6.35
CN.2272.T2.MC.1000 | Remaining Labor Units
CN.2272.T2.MC.1010 | Remaining Labor Units
CN.2272.T2.MC.1020 | Remaining Labor Units
CN.2272.T2.MC.1030 | Remaining Labor Units | 2021-10-23: 16.26; 2021-10-30: 12.65
CN.2272.T2.MC.1040 | Remaining Labor Units
CN.2272.T2.MC.1050 | Remaining Labor Units | 2021-10-16: 161.73; 2021-10-23: 192.4; 2021-10-30: 147.2; 2021-11-06: 12.7
CN.2272.T2.MC.1070 | Remaining Labor Units | 2021-11-06: 66.5; 2021-11-13: 12.41; 2021-11-20: 69.78
CN.2272.T2.MC.1080 | Remaining Labor Units
CN.2272.T2.MC.1090 | Remaining Labor Units
CN.2272.T2.MC.1100 | Remaining Labor Units | 2021-10-09: 21.86; 2021-10-16: 5.25; 2021-10-23: 11.48
CN.2272.T2.MC.1120 | Remaining Labor Units
CN.2272.T2.MC.1160 | Remaining Labor Units | 2021-10-16: 123.25; 2021-10-23: 412.61
CN.2272.T2.MC.1180 | Remaining Labor Units | 2021-10-23: 17.62; 2021-10-30: 276.21; 2021-11-06: 351.2; 2021-11-13: 11.12
CN.2272.T2.MC.1191 | Remaining Labor Units | 2021-11-13: 243.1; 2021-11-20: 279.49; 2021-11-27: 233.3
CN.2272.T2.MC.1210 | Remaining Labor Units
CN.2272.T2.MC.1211 | Remaining Labor Units | 2021-11-27: 361.28; 2021-12-04: 1336.65
CN.2272.T2.MC.1220 | Remaining Labor Units
CN.2272.T2.MC.1221 | Remaining Labor Units | 2021-10-30: 69.63
CN.2272.T2.MC.1222 | Remaining Labor Units | 2021-10-30: 7.21; 2021-11-06: 17.34; 2021-11-13: 132.77; 2021-11-20: 67.38
CN.2272.T2.MC.1224 | Remaining Labor Units | 2022-02-05: 124.8; 2022-02-12: 23.48; 2022-02-19: 68.78
CN.2272.T2.ST.1320 | Remaining Labor Units
CN.2272.T2.ST.1330 | Remaining Labor Units
CN.2272.T2.ST.1340 | Remaining Labor Units
CN.2272.T2.ST.1350 | Remaining Labor Units
CN.2272.T2.ST.1360 | Remaining Labor Units
CN.2272.T2.ST.1364 | Remaining Labor Units
CN.2272.T2.ST.1368 | Remaining Labor Units
CN.2272.T2.ST.1376 | Remaining Labor Units
CN.2272.T2.ST.1380 | Remaining Labor Units
CN.2272.T2.ST.1381 | Remaining Labor Units | 2021-10-16: 389.45; 2021-10-23: 288.47; 2021-10-30: 263.62; 2021-11-06: 435.38; 2021-11-13: 257.1; 2021-11-20: 57.66
CN.2272.T2.ST.1384 | Remaining Labor Units
CN.2272.T2.ST.1388 | Remaining Labor Units | 2021-09-25: 8.93
CN.2272.T2.ST.1392 | Remaining Labor Units
CN.2272.T2.ST.1396 | Remaining Labor Units
CN.2272.T2.ST.1400 | Remaining Labor Units | 2021-10-02: 3.94; 2021-10-09: 0.94
CN.2272.T2.ST.1401 | Remaining Labor Units | 2021-11-27: 88.94; 2021-12-04: 147.59; 2021-12-11: 142.94
CN.2272.T2.ST.1404 | Remaining Labor Units | 2021-10-09: 167.92
CN.2272.T2.ST.1408 | Remaining Labor Units | 2021-10-30: 1.33; 2021-11-06: 3.18; 2021-11-13: 4.39; 2021-11-20: 2.27
CN.2272.T2.ST.1430 | Remaining Labor Units
CN.2272.T2.ST.1461 | Remaining Labor Units
CN.2272.T2.ST.1465 | Remaining Labor Units
CN.2272.T2.ST.1469 | Remaining Labor Units
CN.2272.T2.ST.1485 | Remaining Labor Units
CN.2272.T2.ST.1489 | Remaining Labor Units | 2021-09-25: 11.45
CN.2272.T2.ST.1493 | Remaining Labor Units | 2021-09-25: 74.7
CN.2272.T2.ST.1497 | Remaining Labor Units | 2021-09-25: 2.31
CN.2272.T2.ST.1501 | Remaining Labor Units | 2021-09-25: 1.1; 2021-10-02: 78.2
CN.2272.T2.ST.1505 | Remaining Labor Units | 2021-10-02: 19.85; 2021-10-09: 5.25
CN.2272.T2.ST.1509 | Remaining Labor Units | 2021-10-09: 391.4
CN.2272.T2.ST.1513 | Remaining Labor Units | 2021-10-09: 8.55
CN.2272.T2.ST.1533 | Remaining Labor Units | 2021-10-16: 73.45; 2021-10-23: 14.42
CN.2272.T2.ST.1537 | Remaining Labor Units | 2021-10-23: 133.55
CN.2272.T2.ST.1541 | Remaining Labor Units | 2021-10-23: 2.44
CN.2272.T2.ST.1545 | Remaining Labor Units | 2021-10-23: 56.67; 2021-10-30: 33.69
CN.2272.T2.ST.1549 | Remaining Labor Units | 2021-10-30: 7.93
CN.2272.T2.ST.1553 | Remaining Labor Units | 2021-10-30: 17.39
CN.2272.T2.ST.1565 | Remaining Labor Units | 2021-11-06: 124.46
CN.2272.T2.ST.1573 | Remaining Labor Units | 2021-11-06: 56.33
CN.2272.T2.ST.1577 | Remaining Labor Units | 2021-11-06: 122.31
CN.2272.T2.ST.1581 | Remaining Labor Units | 2021-12-11: 675.83; 2022-01-01: 189.33; 2022-01-08: 1646.19
CN.2272.T2.ST.1593 | Remaining Labor Units | 2022-01-22: 287.77; 2022-01-29: 237.4
CN.2272.T2.ST.1598 | Remaining Labor Units | 2021-11-13: 35.85; 2021-11-20: 29.88; 2021-11-27: 36.56; 2021-12-04: 13.69
CN.2272.T2.ST.1606 | Remaining Labor Units | 2021-09-25: 22.76
CN.2272.T2.ST.1618 | Remaining Labor Units
CN.2272.T2.ST.1622 | Remaining Labor Units | 2021-10-02: 254.9
CN.2272.T2.ST.1626 | Remaining Labor Units | 2021-10-09: 31.64; 2021-10-16: 268.53; 2021-10-23: 328.32; 2021-10-30: 281.81; 2021-11-06: 327.49; 2021-11-13: 234.62
CN.2272.T2.ST.1672 | Remaining Labor Units | 2021-10-23: 18.68; 2021-10-30: 72.7
CN.2272.T2.ST.1674 | Remaining Labor Units | 2021-10-30: 32.89; 2021-11-06: 16.52
CN.2272.T2.ST.1676 | Remaining Labor Units | 2021-12-11: 199.4; 2022-01-01: 222.49
CN.4242.T2.IN.1665 | Remaining Labor Units
CN.4242.T2.PS.1637 | Remaining Labor Units
CN.4242.T2.PS.1641 | Remaining Labor Units
CN.4242.T2.PS.1645 | Remaining Labor Units
CN.4242.T2.PS.1649 | Remaining Labor Units
CN.4242.T2.PS.1650 | Remaining Labor Units
CN.4242.T2.PS.1653 | Remaining Labor Units | 2021-09-25: 52.78
CN.4242.T2.PS.1657 | Remaining Labor Units
CN.4242.T2.PS.1658 | Remaining Labor Units | 2021-09-25: 99.17
CN.4242.T2.PS.1661 | Remaining Labor Units
CN.4242.T2.PS.1663 | Remaining Labor Units | 2021-09-25: 58.23
CN.4242.T2.ST.1629 | Remaining Labor Units
CN.4242.T2.ST.1633 | Remaining Labor Units
CN.4242.T2.WW.1645 | Remaining Labor Units
CN.4242.T2.WW.1653 | Remaining Labor Units
CN.4242.T2.WW.1661 | Remaining Labor Units
CN.4242.T2.WW.1665 | Remaining Labor Units
CN.4242.T2.WW.1669 | Remaining Labor Units
CN.4242.T2.WW.1673 | Remaining Labor Units

## baseline_1
Activity ID | Activity Name | Activity % Complete | Start | Finish | Budgeted Labor Units | Spreadsheet Field | time axis 2021-05-29 to 2022-03-19
2252-1.T2.PI.1095 | 2252-1 Tank Trim | 0% | 2022-02-04 | 2022-03-02 | 585.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9533 | 166.4677 | 166.4677 | 166.4677 | 81.6636 | 0 | 0 | 0
2252-1T2.PI.CS-AIN.1000 | 2252-1 Install-Piping & It's Components [CS-AIN] | 0% | 2021-09-17 | 2021-09-18 | 52.42 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.6966 | 15.7234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-AIN.1032 | 2252-1 Install-Piping & It's Components [CS-AIN] | 0% | 2021-11-12 | 2021-11-19 | 708.92 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472.0712 | 236.8488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-AIN.1055 | 2252-1 Install-Piping & It's Components [CS-AIN] | 10% | 29-Jul-21 A | 2021-08-13 | 147.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 97.5762 | 49.6738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-AIN.1056 | 2252-1 Install-Piping & It's Components [CS-AIN] | 0% | 2021-09-08 | 2021-09-16 | 477.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404.2632 | 73.1168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-AIN.1061 | 2252-1 Install-Piping & It's Components [CS-AIN] | 0% | 2022-01-24 | 2022-02-18 | 894.07 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.7497 | 245.8645 | 245.8645 | 214.5914 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-GCD.1003 | 2252-1 Install-Piping & It's Components [CS-GCD] | 0% | 2021-10-06 | 2021-10-19 | 199.83 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.3135 | 113.3337 | 41.1828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-GCD.1045 | 2252-1 Install-Piping & It's Components [CS-GCD] | 0% | 2021-09-16 | 2021-09-17 | 28.47 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-GSL.1006 | 2252-1 Install-Piping & It's Components [CS-GSL] | 0% | 2021-10-19 | 2021-11-02 | 337.75 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.5168 | 59.9818 | 216.2514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-GSL.1027 | 2252-1 Install-Piping & It's Components [CS-GSL] | 0% | 2021-11-03 | 2021-11-05 | 91.36 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-GVE.1028 | 2252-1 Install-Piping & It's Components [CS-GVE] | 0% | 2022-01-15 | 2022-01-19 | 5.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-GVE.1041 | 2252-1 Install-Piping & It's Components [CS-GVE] | 0% | 2021-08-20 | 2021-08-25 | 28.03 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8077 | 23.2223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-GVE.1042 | 2252-1 Install-Piping & It's Components [CS-GVE] | 0% | 2022-01-15 | 2022-01-20 | 57.05 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-LPB.1022 | 2252-1 Install-Piping & It's Components [CS-LPB] | 75% | 15-Jul-21 A | 2021-08-10 | 24.52 | Budgeted Labor Units | 0 | 0 | 0 | 24.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-LPB.1029 | 2252-1 Install-Piping & It's Components [CS-LPB] | 0% | 2022-01-19 | 2022-02-01 | 472.43 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.1694 | 259.7943 | 94.4663 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-LPB.1046 | 2252-1 Install-Piping & It's Components [CS-LPB] | 0% | 2021-09-18 | 2021-09-24 | 133.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-LPB.1047 | 2252-1 Install-Piping & It's Components [CS-LPB] | 10% | 22-Jul-21 A | 2022-02-10 | 484.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.914 | 335.5163 | 108.3597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-LPN.1047 | 2252-1 Install-Piping & It's Components [CS-LPN] | 0% | 2021-09-24 | 2021-10-02 | 290.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.3722 | 257.6154 | 23.3924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-LSH.1048 | 2252-1 Install-Piping & It's Components [CS-LSH] | 20% | 29-Jul-21 A | 2021-10-06 | 114.54 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-LSH.1049 | 2252-1 Install-Piping & It's Components [FRP-LSD] | 0% | 2022-01-06 | 2022-01-12 | 73.47 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.3415 | 51.1285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-SPB.1042 | 2252-1 Install-Piping & It's Components [CS-SPB] | 0% | 2021-08-25 | 2021-08-30 | 185.73 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.2164 | 49.5136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-SPB.1043 | 2252-1 Install-Piping & It's Components [FRP-GVE] | 0% | 2021-10-19 | 2021-10-27 | 66.7 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.35 | 33.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-WFI.1057 | 2252-1 Install-Piping & It's Components [CS-WFI] | 0% | 2021-08-13 | 2021-08-16 | 163.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.5263 | 118.4237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.CS-WFI.1058 | 2252-1 Install-Piping & It's Components [CS-WFI] | 0% | 2021-08-18 | 2021-08-20 | 164.58 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.FRP-LPA.1012 | 2252-1 Install-Piping & It's Components [FRP-LPA] | 0% | 2022-03-03 | 2022-03-09 | 169.13 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126.4882 | 42.6418 | 0 | 0
2252-1T2.PI.FRP-LPA.1024 | 2252-1 Install-Piping & It's Components [FRP-LPA] | 0% | 2022-02-18 | 2022-02-24 | 61.18 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5666 | 52.6134 | 0 | 0 | 0 | 0
2252-1T2.PI.HDPE-WCW.1015 | 2252-1 Install-Piping & It's Components [HDPE-WCW] | 0% | 2022-02-24 | 2022-03-03 | 384.28 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.6919 | 262.5881 | 0 | 0 | 0
2252-1T2.PI.HDPE-WFI.1016 | 2252-1 Install-Piping & It's Components [HDPE-WFI] | 0% | 2022-03-09 | 2022-03-10 | 11.61 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.61 | 0 | 0
2252-1T2.PI.HDPE-WPO.1058 | 2252-1 Install-Piping & It's Components [HDPE-WPO] | 0% | 2021-08-07 | 2021-08-11 | 775.74 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.HDPE-WRO.1059 | 2252-1 Install-Piping & It's Components [HDPE-WRO] | 0% | 2021-08-16 | 2021-08-18 | 14.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.HDPE-WRO.1060 | 2252-1 Install-Piping & It's Components [HDPE-WRO] | 0% | 2022-03-03 | 2022-03-09 | 61.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.8262 | 9.9638 | 0 | 0
2252-1T2.PI.SS-GVE.1018 | 2252-1 Install-Piping & It's Components [SS-GVE] | 0% | 2021-11-02 | 2021-11-03 | 39.73 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-GVE.1030 | 2252-1 Install-Piping & It's Components [SS-GVE] | 0% | 2022-01-26 | 2022-02-05 | 60.6 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1688 | 52.6791 | 4.7521 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-GVE.1036 | 2252-1 Install-Piping & It's Components [SS-GVE] | 0% | 2022-01-24 | 2022-01-31 | 80.33 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.4777 | 12.8523 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-GVE.1044 | 2252-1 Install-Piping & It's Components [SS-GVE] | 0% | 2021-08-30 | 2021-09-02 | 33.87 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-LPB.1019 | 2252-1 Install-Piping & It's Components [SS-LPB] | 0% | 2021-12-14 | 2022-01-25 | 1147.06 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262.9316 | 0 | 0 | 38.4435 | 413.2184 | 413.2184 | 19.248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-LPB.1025 | 2252-1 Install-Piping & It's Components [SS-LPB] | 75% | 14-Jul-21 A | 2021-08-19 | 161.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 148.3133 | 13.4767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-LPB.1051 | 2252-1 Install-Piping & It's Components [SS-LPB] | 50% | 29-Jul-21 A | 2021-10-29 | 328.22 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138.7354 | 189.4846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-SPB.1031 | 2252-1 Install-Piping & It's Components [SS-SPB] | 0% | 2022-02-01 | 2022-02-16 | 519.93 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151.6369 | 238.3173 | 129.9759 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-SPB.1034 | 2252-1 Install-Piping & It's Components [SS-SPB] | 0% | 2022-01-06 | 2022-01-14 | 550.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.9713 | 432.2787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-SPB.1037 | 2252-1 Install-Piping & It's Components [SS-SPB] | 0% | 2022-01-24 | 2022-02-16 | 1039.9 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.6329 | 317.7516 | 317.7516 | 161.7639 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-SPB.1039 | 2252-1 Install-Piping & It's Components [SS-SPB] | 0% | 2022-01-15 | 2022-01-24 | 498.15 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.7318 | 343.4182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-SPB.1052 | 2252-1 Install-Piping & It's Components [SS-SPB] | 0% | 2021-10-30 | 2021-11-04 | 240.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-WCW.1020 | 2252-1 Install-Piping & It's Components [SS-WCW] | 0% | 2022-01-26 | 2022-01-27 | 6.89 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-WPO.1060 | 2252-1 Install-Piping & It's Components [SS-WPO] | 0% | 2021-12-14 | 2022-01-06 | 953.57 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.785 | 0 | 0 | 476.785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-WRO.1053 | 2252-1 Install-Piping & It's Components [SS-WRO] | 0% | 2021-11-05 | 2021-11-11 | 567.29 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518.6314 | 48.6586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-WRO.1059 | 2252-1 Install-Piping & It's Components [SS-WRO] | 0% | 2021-11-12 | 2021-12-14 | 985.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.4211 | 216.8566 | 216.8566 | 216.8566 | 216.8566 | 78.8423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-WRO.1060 | 2252-1 Install-Piping & It's Components [SS-WRO] | 0% | 2021-12-14 | 2022-01-06 | 90.77 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.385 | 0 | 0 | 45.385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-WSC.1021 | 2252-1 Install-Piping & It's Components [SS-WSC] | 0% | 2022-01-27 | 2022-02-24 | 1462.39 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.3541 | 396.7727 | 396.7727 | 396.7727 | 259.7176 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-WSC.1026 | 2252-1 Install-Piping & It's Components [SS-WSC] | 80% | 29-Jul-21 A | 2021-09-28 | 61.8 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-WSC.1038 | 2252-1 Install-Piping & It's Components [SS-WSC] | 0% | 2022-02-16 | 2022-03-02 | 221.36 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180.1545 | 38.8184 | 2.3872 | 0 | 0 | 0
2252-1T2.PI.SS-WSC.1040 | 2252-1 Install-Piping & It's Components [SS-WSC] | 0% | 2022-01-24 | 2022-01-31 | 264.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222.2212 | 42.1588 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-1T2.PI.SS-WSC.1054 | 2252-1 Install-Piping & It's Components [SS-WSC] | 30% | 02-Aug-21 A | 2022-01-06 | 565.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.6859 | 444.6317 | 56.6323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.CS-AIN.1055 | 2252-2 Install-Piping & It's Components [CS-AIN] | 0% | 2021-10-14 | 2021-10-18 | 72.23 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.9173 | 34.3127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.CS-AIN.1075 | 2252-2 Install-Piping & It's Components [CS-AIN] | 0% | 2021-09-13 | 2021-09-21 | 381.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259.1313 | 122.5587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.CS-AIN.1083 | 2252-2 Install-Piping & It's Components [CS-AIN] | 0% | 2021-11-09 | 2021-11-12 | 222 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.CS-SPB.1047 | 2252-2 Install-Piping & It's Components [CS-SPB] | 60% | 29-Jul-21 A | 2021-09-08 | 198.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 86.6156 | 111.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.CS-SPB.1061 | 2252-2 Install-Piping & It's Components [CS-SPB] | 90% | 15-Jul-21 A | 2021-08-26 | 97.59 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 57.9435 | 39.6465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.CS-SPB.1069 | 2252-2 Install-Piping & It's Components [CS-SPB] | 0% | 2021-08-13 | 2021-08-25 | 290.48 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.5421 | 231.1206 | 16.8173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.CS-WFI.1077 | 2252-2 Install-Piping & It's Components [CS-WFI] | 0% | 2021-10-18 | 2021-10-20 | 168.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.CS-WFI.1081 | 2252-2 Install-Piping & It's Components [CS-WFI] | 0% | 2021-11-01 | 2021-11-09 | 62.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.9733 | 48.2767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.HDPE-WRO.10 | 2252-2 Install-Piping & It's Components [HDPE-WRO] | 0% | 2021-10-20 | 2021-10-22 | 175.51 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-LPB.1049 | 2252-2 Install-Piping & It's Components [SS-LPB] | 0% | 2021-09-08 | 2021-09-13 | 654.4 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489.1424 | 165.2576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-LPB.1051 | 2252-2 Install-Piping & It's Components [SS-LPB] | 0% | 2021-10-18 | 2021-11-10 | 265.62 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.6775 | 18.3974 | 18.3974 | 84.1478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-LPB.1057 | 2252-2 Install-Piping & It's Components [SS-LPB] | 20% | 15-Jul-21 A | 2021-10-18 | 400.07 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.3992 | 326.3243 | 59.3464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-LPB.1063 | 2252-2 Install-Piping & It's Components [SS-LPB] | 80% | 21-Jul-21 A | 2021-09-01 | 178.85 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 3.6332 | 175.2168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-LPB.1067 | 2252-2 Install-Piping & It's Components [SS-LPB] | 0% | 2021-08-26 | 2021-08-27 | 15.76 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-LPB.1071 | 2252-2 Install-Piping & It's Components [SS-LPB] | 40% | 21-Jul-21 A | 2021-09-01 | 756.48 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 56.6676 | 416.4479 | 283.3646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-WPO.1085 | 2252-2 Install-Piping & It's Components [SS-WPO] | 0% | 2021-11-12 | 2021-12-07 | 467.44 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5714 | 135.6671 | 135.6671 | 135.6671 | 46.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-WRO.1079 | 2252-2 Install-Piping & It's Components [SS-WRO] | 0% | 2021-10-22 | 2021-11-01 | 500.23 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.2496 | 393.1942 | 67.7862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-WSC.1053 | 2252-2 Install-Piping & It's Components [SS-WSC] | 20% | 30-Aug-21 A | 2021-10-06 | 230.27 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-WSC.1059 | 2252-2 Install-Piping & It's Components [SS-WSC] | 20% | 21-Jul-21 A | 2021-10-18 | 95.39 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.7967 | 63.5933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-WSC.1065 | 2252-2 Install-Piping & It's Components [SS-WSC] | 0% | 2021-09-01 | 2021-09-03 | 32.93 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-2T2.PI.SS-WSC.1073 | 2252-2 Install-Piping & It's Components [SS-WSC] | 0% | 2021-09-21 | 2021-10-04 | 488.27 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.5741 | 268.3618 | 61.3341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.Flush. 9176 | 2252-3 SPB System Flush | 0% | 2021-11-05 | 2021-11-10 | 861.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.8382 | 813.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.Flush. 9178 | 2252-3 LPB System Flush | 0% | 2022-03-15 | 2022-03-19 | 553.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 538.1236 | 15.3764
2252-3 T2.Flush. 9180 | 2252-3 WSC System Flush | 0% | 2022-01-20 | 2022-01-25 | 199.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83.1253 | 116.3747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.HYDRO. 9168 | 2252-3 SPB System Hydrotest | 0% | 2021-10-18 | 2021-11-05 | 430.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.7208 | 150.8664 | 162.9128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.HYDRO. 9170 | 2252-3 LPB System Hydrotest | 0% | 2022-02-24 | 2022-03-15 | 231.73 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5146 | 88.527 | 88.527 | 32.1615 | 0
2252-3 T2.HYDRO. 9172 | 2252-3 GSL System Hydrotest | 0% | 2021-11-30 | 2021-12-13 | 170.24 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.9279 | 85.0775 | 23.2346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.Insul. 9182 | 2252-3 GVE System Insulation | 0% | 2021-12-09 | 2022-01-05 | 1780.15 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 356.1974 | 978.9626 | 0 | 0 | 444.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.Insul. 9184 | 2252-3 SPB System Insulation | 0% | 2021-11-10 | 2021-11-20 | 139.83 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.5116 | 96.3726 | 6.9458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.Insul. 9186 | 2252-3 LPB System Insulation | 0% | 2022-03-07 | 2022-03-22 | 296.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.9748 | 195.7168 | 74.2584
2252-3 T2.Insul. 9188 | 2252-3 WSC System Insulation | 0% | 2022-01-25 | 2022-02-21 | 676.08 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7658 | 25.556 | 25.556 | 25.556 | 576.6463 | 0 | 0 | 0 | 0
2252-3 T2.Insul. 9190 | 2252-3 GSL System Insulation | 0% | 2021-12-16 | 2022-01-17 | 302.78 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2732 | 0 | 0 | 258.4278 | 29.6314 | 7.4477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.CS-AIN. 9160 | 2252-3 RL2 Install-Piping & It's Components [CS-AIN] | 0% | 2021-09-16 | 2021-09-17 | 109.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.CS-AIN. 9688 | 2252-3 Install-Piping & It's Components [CS-AIN] | 0% | 2021-09-17 | 2021-09-24 | 26.49 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8568 | 22.6332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.CS-GSL. 9153 | 2252-3 RL1 Install-Piping & It's Components [CS-GSL] | 0% | 2021-11-03 | 2021-11-13 | 44.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.3943 | 29.4274 | 1.6783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.CS-GSL. 9164 | 2252-3 RL2 Install-Piping & It's Components [CS-GSL] | 0% | 2021-11-02 | 2021-11-03 | 118.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.CS-LPB. 9372 | 2252-3 RL5 Install-Piping & It's Components [CS-LPB] | 0% | 2021-11-02 | 2021-11-03 | 211.78 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.CS-LPB. 9374 | 2252-3 RL5 Install-Piping & It's Components [CS-LPB] | 0% | 2021-11-08 | 2021-11-15 | 122.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.7979 | 73.5021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.CS-WFI. 9692 | 2252-3 Install-Piping & It's Components [CS-WFI] | 0% | 2022-03-04 | 2022-03-09 | 22.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3855 | 19.4245 | 0 | 0
2252-3 T2.PI.HDPE-WRO. 94 | 2252-3 Install-Piping & It's Components [HDPE-WRO] | 0% | 2021-08-18 | 2021-08-23 | 281.28 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.8624 | 91.4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-GSL. 9162 | 2252-3 RL2 Install-Piping & It's Components [SS-GSL] | 0% | 2021-11-15 | 2021-11-29 | 450.73 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2698 | 436.6863 | 9.774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-GSL. 9164 | 2252-3 RL3 Install-Piping & It's Components [SS-GSL] | 0% | 2021-11-29 | 2022-01-07 | 183.13 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89.8708 | 1.6942 | 1.6942 | 0 | 0 | 89.8708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-GSL. 9366 | 2252-3 RL7 Install-Piping & It's Components [SS-GSL] | 0% | 2021-11-29 | 2021-11-29 | 24.52 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-GVE. 9154 | 2252-3 RL1 Install-Piping & It's Components [SS-GVE] | 0% | 2021-10-18 | 2021-10-19 | 66.17 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-GVE. 9164 | 2252-3 RL5 Install-Piping & It's Components [SS-GVE] | 0% | 2021-11-29 | 2021-12-06 | 149.64 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112.2277 | 37.4123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-GVE. 9165 | 2252-3 RL3 Install-Piping & It's Components [SS-GVE] | 0% | 2021-10-28 | 2021-11-05 | 177.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.2226 | 134.7574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-GVE. 9166 | 2252-3 RL2 Install-Piping & It's Components [SS-GVE] | 0% | 2021-10-19 | 2021-10-20 | 58.2 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-GVE. 9368 | 2252-3 RL7 Install-Piping & It's Components [SS-GVE] | 0% | 2021-12-07 | 2021-12-08 | 39.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-LPB. 9167 | 2252-3 RL3 Install-Piping & It's Components [SS-LPB] | 0% | 2022-01-29 | 2022-02-05 | 198.73 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195.1737 | 3.5563 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-LPB. 9170 | 2252-3 RL2 Install-Piping & It's Components [SS-LPB] | 0% | 2022-01-26 | 2022-01-28 | 160.89 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-LPB. 9270 | 2252-3 RL4 Install-Piping & It's Components [SS-LPB] | 0% | 2022-02-05 | 2022-02-24 | 456.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164.5162 | 167.518 | 124.9458 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-LPB. 9271 | 2252-3 RL4 Install-Piping & It's Components [SS-LPB] | 0% | 2022-02-24 | 2022-02-28 | 30.28 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6211 | 23.6589 | 0 | 0 | 0
2252-3 T2.PI.SS-SPB. 9157 | 2252-3 RL1 Install-Piping & It's Components [SS-SPB] | 0% | 2021-08-17 | 2021-09-02 | 280.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.3382 | 29.7393 | 229.7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WCW. 9158 | 2252-3 RL1 Install-Piping & It's Components [SS-WCW] | 0% | 2022-03-03 | 2022-03-09 | 143.17 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4195 | 135.7505 | 0 | 0
2252-3 T2.PI.SS-WCW. 9172 | 2252-3 RL3 Install-Piping & It's Components [SS-WCW] | 0% | 2022-03-12 | 2022-03-15 | 52.52 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.52 | 0
2252-3 T2.PI.SS-WCW. 9174 | 2252-3 RL2 Install-Piping & It's Components [SS-WCW] | 0% | 2022-03-07 | 2022-03-12 | 431.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423.3441 | 8.6359 | 0
2252-3 T2.PI.SS-WCW. 9374 | 2252-3 RL5 Install-Piping & It's Components [SS-WCW] | 0% | 2022-03-15 | 2022-03-18 | 198.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.66 | 0
2252-3 T2.PI.SS-WGS. 9159 | 2252-3 RL1 Install-Piping & It's Components [SS-WGS] | 0% | 2021-08-12 | 2021-08-27 | 806.58 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.8837 | 81.4272 | 676.2691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WPO. 9694 | 2252-3 Install-Piping & It's Components [SS-WPO] | 0% | 2021-08-12 | 2021-08-20 | 169.2 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133.6476 | 35.5524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WPR. 9176 | 2252-3 RL3 Install-Piping & It's Components [SS-WPR] | 0% | 2022-03-15 | 2022-03-16 | 24.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.01 | 0
2252-3 T2.PI.SS-WRO. 9160 | 2252-3 RL1 Install-Piping & It's Components [SS-WRO] | 0% | 2021-08-23 | 2021-08-25 | 144.86 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WRO. 9690 | 2252-3 Install-Piping & It's Components [SS-WRO] | 0% | 2021-08-23 | 2021-08-30 | 219.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.6169 | 35.1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WRO. 9691 | 2252-3 RL1 Install-Piping & It's Components [SS-WRO] | 0% | 2021-08-25 | 2021-08-31 | 88.59 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48.7167 | 39.8733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WSC. 9162 | 2252-3 RL1 Install-Piping & It's Components [SS-WSC] | 0% | 2021-09-24 | 2021-10-18 | 515.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7317 | 157.4964 | 157.4964 | 157.4964 | 37.2292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WSC. 9178 | 2252-3 RL2 Install-Piping & It's Components [SS-WSC] | 0% | 2021-10-18 | 2021-10-28 | 377.9 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.3642 | 179.5358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WSC. 9180 | 2252-3 RL3 Install-Piping & It's Components [SS-WSC] | 0% | 2021-12-07 | 2021-12-17 | 168.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.7262 | 93.3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WSC. 9276 | 2252-3 RL4 Install-Piping & It's Components [SS-WSC] | 0% | 2021-12-17 | 2022-01-08 | 196.43 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.3733 | 0 | 0 | 163.6834 | 16.3733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WSC. 9368 | 2252-3 RL8 Install-Piping & It's Components [SS-WSC] | 0% | 2022-01-15 | 2022-01-20 | 216.93 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WSC. 9370 | 2252-3 RL7 Install-Piping & It's Components [SS-WSC] | 0% | 2022-01-13 | 2022-01-14 | 17.35 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WSC. 9376 | 2252-3 RL5 Install-Piping & It's Components [SS-WSC] | 0% | 2022-01-10 | 2022-01-11 | 175.64 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-3 T2.PI.SS-WSC. 9378 | 2252-3 RL6 Install-Piping & It's Components [SS-WSC] | 0% | 2022-01-11 | 2022-01-12 | 6.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.CS-AIN.1100 | 2252-4 Install-Piping & It's Components [CS-AIN] | 0% | 2021-10-12 | 2021-10-13 | 189.37 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.CS-LPB.1081 | 2252-4 Install-Piping & It's Components [CS-LPB] | 70% | 30-Jul-21 A | 2021-08-17 | 171.24 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.8827 | 36.3573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.CS-LPB.1085 | 2252-4 Install-Piping & It's Components [CS-LPB] | 0% | 2021-10-15 | 2021-10-25 | 31.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6546 | 24.4282 | 4.3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.CS-LPB.1087 | 2252-4 Install-Piping & It's Components [CS-LPB] | 0% | 2021-09-09 | 2021-09-21 | 296.61 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.4374 | 181.2562 | 65.9165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.HDPE-WRO.89 | 2252-4 Install-Piping & It's Components [HDPE-WRO] | 0% | 2021-09-21 | 2021-09-22 | 37.67 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.HDPE-WRO.96 | 2252-4 Install-Piping & It's Components [HDPE-WRO] | 0% | 2021-10-04 | 2021-10-06 | 56.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.SS-LPB.1075 | 2252-4 Install-Piping & It's Components [SS-LPB] | 0% | 2021-08-19 | 2021-08-20 | 242.34 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.SS-LPB.1092 | 2252-4 Install-Piping & It's Components [SS-LPB] | 0% | 2021-09-22 | 2021-10-07 | 492.24 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.1713 | 434.5162 | 33.5525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.SS-SPB.1077 | 2252-4 Install-Piping & It's Components [SS-SPB] | 0% | 2021-08-21 | 2021-08-25 | 134.7 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.SS-WPO.1102 | 2252-4 Install-Piping & It's Components [SS-WPO] | 0% | 2021-10-13 | 2021-10-16 | 147.34 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122.7811 | 24.5589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.SS-WRO.1098 | 2252-4 Install-Piping & It's Components [SS-WRO] | 0% | 2021-10-06 | 2021-10-11 | 218.88 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.3256 | 82.5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.SS-WSC.1079 | 2252-4 Install-Piping & It's Components [SS-WSC] | 20% | 03-Aug-21 A | 2021-09-09 | 452.33 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313.2586 | 45.3459 | 93.7255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.SS-WSC.1083 | 2252-4 Install-Piping & It's Components [SS-WSC] | 80% | 30-Jul-21 A | 2021-08-19 | 46.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-4T2.PI.SS-WSC.1094 | 2252-4 Install-Piping & It's Components [SS-WSC] | 0% | 2021-09-28 | 2021-10-15 | 672.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.7915 | 256.8392 | 228.8194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-5T2.PI.CS-AIN.1094 | 2252-5 Install-Piping & It's Components [CS-AIN] | 0% | 2021-09-06 | 2021-09-07 | 110.23 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-5T2.PI.SS-WPO.1098 | 2252-5 Install-Piping & It's Components [SS-WPO] | 0% | 2021-09-08 | 2021-09-11 | 124.72 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.1247 | 18.5953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252-5T2.PI.SS-WRO.1096 | 2252-5 Install-Piping & It's Components [SS-WRO] | 0% | 2021-09-07 | 2021-09-08 | 118.28 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.9277 | 2262-1 Tank Trim | 0% | 2021-11-22 | 2021-12-17 | 295.6 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.2636 | 81.2519 | 81.2519 | 67.8326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.CS-AIN.9203 | 2262-1 Install-Piping & It's Components (CS-AIN) | 0% | 2021-08-09 | 2021-08-24 | 567.73 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.2642 | 59.7178 | 22.748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.CS-AIN.9207 | 2262-1 Install-Piping & It's Components (SS-SPB) | 10% | 03-Aug-21 A | 2022-02-15 | 109.97 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.1458 | 65.8242 | 0 | 0
2262-1T2.PI.CS-AIN.9279 | 2262-1 Install-Piping & It's Components (CS-AIN) | 0% | 2021-09-01 | 2021-09-22 | 769.76 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.2922 | 256.5867 | 256.5867 | 135.2945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.CS-AIN.9315 | 2262-1 Install-Piping & It's Components (CS-AIN) | 0% | 2022-01-20 | 2022-01-31 | 269.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.8872 | 174.3786 | 41.2343 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.CS-LPB.9235 | 2262-1 Install-Piping & It's Components (CS-LPB) | 0% | 2021-09-29 | 2021-10-01 | 203.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.CS-WFI.9283 | 2262-1 Install-Piping & It's Components (CS-WFI) | 0% | 2021-09-25 | 2021-09-28 | 430.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 430.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.CS-WFI.9299 | 2262-1 Install-Piping & It's Components (CS-WFI) | 0% | 2021-09-28 | 2021-09-30 | 94.89 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.HDPE-WCW.9239 | 2262-1 Install-Piping & It's Components (HDPE-WCW) | 0% | 2021-10-09 | 2021-10-18 | 583.46 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484.7112 | 98.7488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.HDPE-WCW.9259 | 2262-1 Install-Piping & It's Components (HDPE-WCW) | 0% | 2021-10-20 | 2021-10-21 | 38.19 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.HDPE-WRO.9291 | 2262-1 Install-Piping & It's Components (HDPE-WRO) | 0% | 2021-09-22 | 2021-09-29 | 345.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.5456 | 181.4644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-GVE.9195 | 2262-1 Install-Piping & It's Components (SS-GVE) | 0% | 2021-10-01 | 2021-10-09 | 98.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.1128 | 53.1429 | 9.6943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-GVE.9215 | 2262-1 Install-Piping & It's Components (SS-GVE) | 0% | 2021-09-30 | 2021-10-02 | 76.09 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.7222 | 19.3678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-GVE.9243 | 2262-1 Install-Piping & It's Components (SS-GVE) | 0% | 2021-08-18 | 2021-08-18 | 42.43 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-LPB.9199 | 2262-1 Install-Piping & It's Components (SS-LPB) | 90% | 14-Jul-21 A | 2021-10-20 | 297.72 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.5289 | 233.1911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-LPB.9251 | 2262-1 Install-Piping & It's Components (SS-LPB) | 100% | 01-Jul-21 A | 22-Jul-21 A | 44.85 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.9641 | 4.8859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-LPB.9267 | 2262-1 Install-Piping & It's Components (SS-LPB) | 90% | 01-Jul-21 A | 2021-10-19 | 525.23 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 445.8378 | 79.3922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-SPB.9207 | 2262-1 Install-Piping & It's Components (SS-SPB) | 0% | 2022-01-31 | 2022-02-12 | 390.12 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.8272 | 214.5477 | 11.7451 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-SPB.9219 | 2262-1 Install-Piping & It's Components (SS-SPB) | 0% | 2021-11-09 | 2021-11-22 | 840.06 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285.4681 | 462.2388 | 92.3531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-SPB.9227 | 2262-1 Install-Piping & It's Components (SS-SPB) | 0% | 2021-12-08 | 2021-12-10 | 170.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-SPB.9271 | 2262-1 Install-Piping & It's Components (SS-SPB) | 10% | 03-Aug-21 A | 2021-12-08 | 292.17 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1354 | 0 | 0 | 272.1264 | 16.9082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WPO.9303 | 2262-1 Install-Piping & It's Components (SS-WPO) | 0% | 2021-10-20 | 2021-10-29 | 1249.73 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399.9352 | 849.7948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WRO.9295 | 2262-1 Install-Piping & It's Components (SS-WRO) | 0% | 2021-10-18 | 2021-10-19 | 14.82 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WRO.9311 | 2262-1 Install-Piping & It's Components (SS-WRO) | 0% | 2021-10-29 | 2021-11-09 | 29.87 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7643 | 6.3667 | 19.7389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WRO.9312 | 2262-1 Install-Piping & It's Components (SS-WRO) | 0% | 2021-11-29 | 2022-01-03 | 425.65 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125.2557 | 146.2122 | 146.2122 | 0 | 0 | 7.9698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WSC.9211 | 2262-1 Install-Piping & It's Components (SS-WSC) | 0% | 2022-02-12 | 2022-03-12 | 728.76 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172.2468 | 182.1923 | 182.1923 | 182.1923 | 9.9362 | 0
2262-1T2.PI.SS-WSC.9223 | 2262-1 Install-Piping & It's Components (SS-WSC) | 0% | 2021-11-22 | 2021-12-02 | 525.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.1179 | 236.5421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WSC.9231 | 2262-1 Install-Piping & It's Components (SS-WSC) | 35% | 29-Jul-21 A | 2021-11-29 | 414.71 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145.1586 | 269.5514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WSC.9247 | 2262-1 Install-Piping & It's Components (SS-WSC) | 20% | 19-Jul-21 A | 2021-09-01 | 1473 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.8369 | 9.1495 | 9.1495 | 9.1495 | 1362.7147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WSC.9255 | 2262-1 Install-Piping & It's Components (SS-WSC) | 100% | 01-Jul-21 A | 22-Jul-21 A | 92.42 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WSC.9263 | 2262-1 Install-Piping & It's Components (SS-WSC) | 0% | 2021-10-18 | 2021-10-19 | 14.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-1T2.PI.SS-WSC.9275 | 2262-1 Install-Piping & It's Components (SS-WSC) | 0% | 2021-10-19 | 2021-10-20 | 94.39 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.Flush. 9181 | 2262-2 GSL System Flush | 0% | 2022-01-31 | 2022-02-02 | 61.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.Flush. 9182 | 2262-2 SPB System Flush | 0% | 2021-12-04 | 2021-12-09 | 368.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.Flush. 9183 | 2262-2 LPB System Flush | 0% | 2022-02-15 | 2022-02-18 | 184.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.5 | 0 | 0 | 0 | 0 | 0
2262-2 T2.Flush. 9184 | 2262-2 WSC System Flush | 0% | 2022-02-07 | 2022-02-11 | 676.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 676.5 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.HYDRO. 9173 | 2262-2 SPB System Hydrotest | 0% | 2021-11-16 | 2021-12-04 | 676.51 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 173.5825 | 244.7874 | 244.7874 | 13.3526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.HYDRO. 9174 | 2262-2 LPB System Hydrotest | 0% | 2022-01-21 | 2022-02-15 | 369 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.7741 | 73.4778 | 73.4778 | 73.4778 | 118.7925 | 0 | 0 | 0 | 0 | 0
2262-2 T2.HYDRO. 9175 | 2262-2 GSL System Hydrotest | 0% | 2022-01-20 | 2022-01-31 | 61.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.8373 | 42.2813 | 5.3814 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.Insul. 9191 | 2262-2 GVE System Insulation | 0% | 2022-02-04 | 2022-03-02 | 1268.91 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.2861 | 392.8818 | 392.8818 | 392.8818 | 25.9784 | 0 | 0 | 0
2262-2 T2.Insul. 9192 | 2262-2 SPB System Insulation | 0% | 2021-12-09 | 2022-01-25 | 932.62 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.2322 | 141.8235 | 0 | 0 | 1.7641 | 141.8235 | 141.8235 | 468.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.Insul. 9193 | 2262-2 LPB System Insulation | 0% | 2022-01-31 | 2022-02-22 | 449.1 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.5923 | 145.2946 | 145.2946 | 44.9184 | 0 | 0 | 0 | 0
2262-2 T2.Insul. 9194 | 2262-2 WSC System Insulation | 0% | 2022-02-11 | 2022-03-14 | 1749.56 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616.226 | 52.2481 | 52.2481 | 52.2481 | 52.2481 | 924.3415 | 0
2262-2 T2.Insul. 9195 | 2262-2 GSL System Insulation | 0% | 2022-02-02 | 2022-02-25 | 541.9 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.227 | 165.5804 | 165.5804 | 147.5122 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-GSL. 9367 | 2262-2 RL1 Install-Piping & It's Components [SS-GSL] | 0% | 2021-09-29 | 2021-09-30 | 104.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-GSL. 9368 | 2262-2 RL2 Install-Piping & It's Components [SS-GSL] | 0% | 2021-10-28 | 2021-11-06 | 204.94 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.369 | 195.0392 | 3.5318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-GSL. 9369 | 2262-2 RL3 Install-Piping & It's Components [SS-GSL] | 0% | 2021-11-23 | 2021-12-15 | 161.8 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.36 | 52.3466 | 52.3466 | 24.7468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-GSL. 9372 | 2262-2 RL8 Install-Piping & It's Components [SS-GSL] | 0% | 2022-01-18 | 2022-01-20 | 19.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-GVE. 9369 | 2262-2 RL1 Install-Piping & It's Components [SS-GVE] | 0% | 2021-10-26 | 2021-10-27 | 82.18 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-GVE. 9371 | 2262-2 RL3 Install-Piping & It's Components [SS-GVE] | 0% | 2022-01-12 | 2022-01-24 | 72.21 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.2562 | 44.1283 | 8.8255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-GVE. 9372 | 2262-2 RL4 Install-Piping & It's Components [SS-GVE] | 0% | 2022-01-24 | 2022-01-31 | 91.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.1676 | 17.2824 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-GVE. 9373 | 2262-2 RL5 Install-Piping & It's Components [SS-GVE] | 0% | 2022-01-31 | 2022-02-04 | 98.33 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-GVE. 9697 | 2262-2 RL6 Install-Piping & It's Components [SS-GVE] | 0% | 2022-02-04 | 2022-02-08 | 16.31 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.8942 | 11.4158 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-LPB. 9471 | 2262-2 RL1 Install-Piping & It's Components [SS-LPB] | 0% | 2021-09-15 | 2021-09-17 | 105.83 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-LPB. 9473 | 2262-2 RL3 Install-Piping & It's Components [SS-LPB] | 0% | 2021-09-17 | 2021-09-23 | 372.63 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.5189 | 298.1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-LPB. 9474 | 2262-2 RL4 Install-Piping & It's Components [SS-LPB] | 0% | 2021-10-26 | 2021-12-01 | 395.06 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.9781 | 77.612 | 77.612 | 77.612 | 77.612 | 36.6339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-LPB. 9475 | 2262-2 RL5 Install-Piping & It's Components [SS-LPB] | 0% | 2022-01-18 | 2022-01-24 | 12.77 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.3377 | 3.4323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-SPB. 9173 | 2262-2 RL1 Install-Piping & It's Components [SS-SPB] | 5% | 04-Aug-21 A | 2021-11-16 | 257.48 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.3554 | 121.1246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-SPB. 9390 | 2262-2 RL4 Install-Piping & It's Components [SS-SPB] | 0% | 2022-01-18 | 2022-02-02 | 65.92 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7265 | 9.1071 | 50.0864 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-SPB. 9391 | 2262-2 RL5 Install-Piping & It's Components [SS-SPB] | 0% | 2022-02-02 | 2022-02-09 | 48.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.4585 | 24.6515 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WCW. 9375 | 2262-2 RL1 Install-Piping & It's Components [SS-WCW] | 0% | 2021-10-26 | 2021-11-10 | 338.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95.9616 | 155.2325 | 87.4959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WCW. 9376 | 2262-2 RL2 Install-Piping & It's Components [SS-WCW] | 0% | 2021-10-26 | 2021-10-28 | 39.44 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WCW. 9377 | 2262-2 RL3 Install-Piping & It's Components [SS-WCW] | 0% | 2021-10-28 | 2021-11-03 | 30.37 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2165 | 28.1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WCW. 9378 | 2262-2 RL4 Install-Piping & It's Components [SS-WCW] | 0% | 2022-01-12 | 2022-01-18 | 255.47 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.2212 | 119.2488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WGS. 9160 | 2262-2 RL1 Install-Piping & It's Components [SS-WGS] | 5% | 03-Aug-21 A | 2021-09-03 | 696.26 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388.7712 | 55.7672 | 55.7672 | 195.9544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WGS. 9705 | 2262-2 RL3 Install-Piping & It's Components [SS-WGS] | 0% | 2021-12-15 | 2021-12-16 | 8.74 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WGS. 9707 | 2262-2 RL4 Install-Piping & It's Components [SS-WGS] | 0% | 2022-01-18 | 2022-01-20 | 118.15 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WPR. 9177 | 2262-2 RL3 Install-Piping & It's Components [SS-WPR] | 0% | 2021-11-03 | 2021-11-05 | 17.88 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WSC. 9379 | 2262-2 RL1 Install-Piping & It's Components [SS-WSC] | 5% | 05-Aug-21 A | 2021-10-26 | 798.54 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262.1482 | 55.8129 | 55.8129 | 55.8129 | 368.9532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WSC. 9380 | 2262-2 RL2 Install-Piping & It's Components [SS-WSC] | 0% | 2021-11-16 | 2021-11-23 | 12.84 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3458 | 4.4942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WSC. 9381 | 2262-2 RL3 Install-Piping & It's Components [SS-WSC] | 0% | 2021-12-16 | 2022-01-12 | 384.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72.8189 | 0 | 0 | 191.9494 | 119.2717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WSC. 9382 | 2262-2 RL4 Install-Piping & It's Components [SS-WSC] | 0% | 2022-01-12 | 2022-01-28 | 367.29 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.548 | 155.4163 | 144.3258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WSC. 9384 | 2262-2 RL6 Install-Piping & It's Components [SS-WSC] | 0% | 2022-01-28 | 2022-01-31 | 13.48 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5934 | 9.8866 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WSC. 9385 | 2262-2 RL7 Install-Piping & It's Components [SS-WSC] | 0% | 2022-01-31 | 2022-02-02 | 70.22 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WSC. 9386 | 2262-2 RL8 Install-Piping & It's Components [SS-WSC] | 0% | 2022-02-02 | 2022-02-07 | 114.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.2768 | 35.8832 | 0 | 0 | 0 | 0 | 0 | 0
2262-2 T2.PI.SS-WWW. 9709 | 2262-2 RL3 Install-Piping & It's Components [SS-WWW] | 0% | 2021-09-06 | 2021-09-08 | 38.86 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.CS-GSL.9203 | 2262-2 Install-Piping & It's Components (CS-GSL) | 0% | 2021-09-27 | 2021-09-29 | 57.09 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.CS-GVE.9190 | 2262-2 Install-Piping & It's Components (CS-GVE) | 0% | 2022-02-08 | 2022-02-09 | 58.94 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.94 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.CS-LPB.9189 | 2262-2 Install-Piping & It's Components (CS-LPB) | 0% | 2021-09-09 | 2021-09-10 | 128.22 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.CS-LPN.9179 | 2262-2 Install-Piping & It's Components (CS-LPN) | 0% | 2021-09-08 | 2021-09-09 | 56.51 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.CS-WFI.9646 | 2262-2 Install-Piping & It's Components (CS-WFI) | 0% | 2021-11-26 | 2021-11-29 | 23.85 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5376 | 14.3124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.HDPE-WCW.80 | 2262-2 Install-Piping & It's Components (HDPE-WCW) | 0% | 2021-09-10 | 2021-09-15 | 106.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.1429 | 91.8971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.HDPE-WRO.92 | 2262-2 Install-Piping & It's Components (HDPE-WRO) | 0% | 2021-12-01 | 2021-12-06 | 88.65 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.2712 | 24.3788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.SS-LPB.9181 | 2262-2 Install-Piping & It's Components (SS-LPB) | 0% | 2021-09-03 | 2021-09-06 | 244.54 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.9117 | 176.6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.SS-SPB.9223 | 2262-2 Install-Piping & It's Components (SS-SPB) | 0% | 2021-09-23 | 2021-09-27 | 413.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261.6241 | 151.4859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.SS-WPO.9650 | 2262-2 Install-Piping & It's Components (SS-WPO) | 0% | 2021-11-22 | 2021-11-26 | 328.74 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.SS-WRO.9654 | 2262-2 Install-Piping & It's Components (SS-WRO) | 0% | 2021-12-06 | 2021-12-10 | 307.28 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-2.T2.PI.SS-WSC.9239 | 2262-2 Install-Piping & It's Components (CS-AIN) | 0% | 2021-11-10 | 2021-11-22 | 190.72 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9237 | 177.6041 | 4.1922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.1435 | 2262-3 Tank Trim | 0% | 2021-09-28 | 2021-10-11 | 33.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5523 | 18.6918 | 3.7358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.CS-GSL.1394 | 2262-3 Install-Piping & It's Components (CS-GSL) | 0% | 2021-08-11 | 2021-08-12 | 7.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.CS-GSL.1426 | 2262-3 Install-Piping & It's Components (CS-GSL) | 0% | 2021-08-12 | 2021-08-13 | 65.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.CS-GSL.1438 | 2262-3 Install-Piping & It's Components (CS-GSL) | 25% | 28-Jul-21 A | 2021-09-22 | 429.19 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123.7527 | 151.3414 | 151.3414 | 2.7546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.CS-LPB.1442 | 2262-3 Install-Piping & It's Components (CS-LPB) | 0% | 2021-08-12 | 2021-08-14 | 54.59 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.1104 | 13.4796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.CS-LPN.1446 | 2262-3 Install-Piping & It's Components (CS-LPN) | 0% | 2021-09-02 | 2021-10-06 | 685.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.2278 | 12.6452 | 12.6452 | 12.6452 | 12.6452 | 587.4914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.CS-WRA.1439 | 2262-3 Install-Piping & It's Components (CS-WRA) | 0% | 2021-10-06 | 2021-10-07 | 20.09 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.HDPE-WR.1440 | 2262-3 Install-Piping & It's Components (HDPE-WRO) | 0% | 2021-10-07 | 2021-10-11 | 51.24 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.4523 | 18.7877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.PS.1434 | 2262-3 Install Pipe Supports and Miscellaneous Steel | 0% | 2022-01-12 | 2022-01-20 | 103.33 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.6623 | 63.6677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.SS-LPB.1430 | 2262-3 Install-Piping & It's Components (SS-LPB) | 0% | 2021-08-11 | 2021-08-12 | 26.84 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.SS-SPB.1454 | 2262-3 Install-Piping & It's Components (SS-SPB) | 0% | 2021-08-14 | 2021-08-16 | 89.36 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.SS-SPB.1458 | 2262-3 Install-Piping & It's Components (SS-WSC) | 0% | 2021-09-22 | 2021-10-06 | 222.19 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.5563 | 111.1349 | 52.4988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.SS-WSC.1422 | 2262-3 Install-Piping & It's Components (SS-WSC) | 0% | 2021-08-11 | 2021-09-01 | 295.26 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.1008 | 116.9263 | 116.9263 | 8.3065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262-3.T2.PI.SS-WSC.1434 | 2262-3 Install-Piping & It's Components (SS-WSC) | 0% | 2021-08-10 | 2021-08-11 | 27.07 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1224 | 2272-1 Run and align 2272-80-PLH-2002-S2l1 LINE FROM HP 1012 (Drying area) to HP 018 (Packaging area) | 0% | 2021-10-07 | 2021-10-19 | 265.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.1726 | 145.719 | 66.2184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1225 | 2272-1 Run and align 2272-80-PLH-2004-S2l1 LINE FROM HP 1013 (Drying area) to HP 021 (Packaging area) | 0% | 2021-10-20 | 2021-11-11 | 525.53 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86.1584 | 157.9446 | 157.9446 | 123.4825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1228 | 2272-1 Run and align screw feeder (FE 011 and 012) interconnection lines to Manetic screens 003 and 004 | 0% | 2021-11-11 | 2021-12-02 | 487.05 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.4232 | 162.35 | 162.35 | 126.9268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1229 | 2272-1 Run and align screw feeder (FE 013 and 014) interconnection lines to Manetic screens 001 and 002 | 0% | 2021-12-02 | 2022-01-06 | 753.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5554 | 264.1597 | 264.1597 | 0 | 0 | 167.9351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1230 | 2272-1 Run and align Magnetic screen discharge piping from MS 003 and 004 - Intermediate hoppers HP 016 and 017 | 0% | 2022-01-06 | 2022-01-07 | 97.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1232 | 2272-1 Run and align piping from Hoppers 016 and 017 - Hopper 23 including diversion line | 0% | 2022-01-07 | 2022-01-17 | 282.52 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6951 | 274.4321 | 5.3928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1233 | 2272-1 Run and align piping from Hoppers 014 and 015 - Hopper 22 including diversion line | 0% | 2022-01-17 | 2022-01-25 | 319.1 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.6622 | 261.4378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1234 | 2272-1 Run and align Vacuum pump (PP 024 - 027) to Transfer Reciever Vessel Piping | 0% | 2022-01-26 | 2022-02-04 | 383.53 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143.8176 | 239.7124 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1235 | 2272-1 Run and align Vacuum pump (PP 024 - 027) vents | 0% | 2022-02-04 | 2022-02-11 | 346.71 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8925 | 317.8175 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1236 | 2272-1 Site run and fit all instrucmnt air pipe, manifolds and tubing | 0% | 2022-02-03 | 2022-02-11 | 649.17 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 473.9468 | 175.2232 | 0 | 0 | 0 | 0 | 0 | 0
2272-1.T2.PI.1238 | 2272-1 Assemble and Install 11 Safety Showers | 0% | 2022-02-02 | 2022-02-11 | 445.71 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 353.3114 | 92.3986 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.HY.1164 | 2272-2 Hydrotesting | 0% | 2022-01-24 | 2022-02-03 | 430.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236.7745 | 193.7255 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.IN.1168 | 2272-2 Piping insulation | 0% | 2022-01-27 | 2022-02-18 | 697.4 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.4322 | 225.6267 | 225.6267 | 188.7144 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1140 | 2272-2 Run and align off gas ducting from Dryers 001 and 002 back to Vent Scrubber 001 | 20% | 28-Jul-21 A | 2021-11-29 | 154.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.8152 | 99.4848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1144 | 2272-2 Run and align Steam Condensate Lines from Dryer Hot Water Tank 2272-TK-001 to Dryers 1 and 2 | 0% | 2021-11-29 | 2021-12-06 | 268.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.4289 | 183.5211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1146 | 2272-2 Run and align Steam Condensate Lines from Dryers 1 and 2 - Dryer Hot Water Tank 2272-TK-001 | 0% | 2021-12-06 | 2021-12-11 | 240.93 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221.6556 | 19.2744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1148 | 2272-2 Run and align Steam Condensate Lines from 2260-PP-002 to Dryer Hot Water Tank 2272-TK-001 | 0% | 2021-12-10 | 2021-12-17 | 43.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.369 | 39.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1150 | 2272-2 Cooling water supply and return lines for Dryer 1 | 0% | 2021-12-14 | 2022-01-03 | 166.65 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129.1537 | 0 | 0 | 37.4962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1152 | 2272-2 Cooling water supply and return lines for Dryer 2 | 0% | 2021-12-17 | 2022-01-06 | 150.23 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7558 | 0 | 0 | 146.4743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1154 | 2272-2 Cooling water supply and return lines for Dryer 3 | 0% | 2022-01-05 | 2022-01-21 | 214.44 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.5625 | 145.5437 | 13.3338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1156 | 2272-2 Cooling water supply and return lines for Dryer 4 | 0% | 2022-01-10 | 2022-01-24 | 221.83 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.3149 | 31.8554 | 36.6596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1158 | 2272-2 Run and align sump pump discharge line back to 2262-SU-001 (Area 2262 Sump) | 0% | 2022-01-24 | 2022-01-27 | 5.2 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1162 | 2272-2 Site run and install Instrument air piping | 0% | 2022-01-11 | 2022-01-27 | 413.53 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5396 | 235.6724 | 175.318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272-2.T2.PI.1166 | 2272-2 Installation and chem anchoring of ground pipe supports | 0% | 2021-12-17 | 2022-01-27 | 270.84 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.9425 | 0 | 0 | 3.0119 | 26.4185 | 26.4185 | 176.0486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1663 | 4242-SP1-100 Install-Piping & It's Components (CS-AIN) | 100% | 14-Jun-21 A | 29-Jun-21 A | 42.83 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1681 | 4242-SP1-200 Install-Piping & It's Components (CS-AIN) | 100% | 08-Jun-21 A | 02-Jul-21 A | 24.82 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1701 | 4242-SP1-300 Install-Piping & It's Components (CS-AIN) | 100% | 17-Jun-21 A | 05-Jul-21 A | 43.35 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.1046 | 4.2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1722 | 4242-SP1-400 Install-Piping & It's Components (CS-AIN) | 0% | 2021-11-02 | 2021-11-02 | 32.22 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1746 | 4242-SP1-500 Install-Piping & It's Components (CS-AIN) | 0% | 2021-10-09 | 2021-10-12 | 47.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1774 | 4242-SP1-600 Install-Piping & It's Components (CS-AIN) | 0% | 2021-09-10 | 2021-09-14 | 40.75 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2789 | 33.4711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1802 | 4242-SP1-700 Install-Piping & It's Components (CS-AIN) | 100% | 17-Jul-21 A | 17-Jul-21 A | 14.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1820 | 4242-SP1-800 Install-Piping & It's Components (CS-AIN) | 100% | 23-Jun-21 A | 07-Jul-21 A | 37.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.8286 | 12.2114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-AIN.1842 | 4242-SP1-900 Install-Piping & It's Components (CS-AIN) | 100% | 16-Jun-21 A | 05-Jul-21 A | 35.43 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GCD.1665 | 4242-SP1-100 Install-Piping & It's Components (CS-GCD) | 100% | 15-Jun-21 A | 16-Jun-21 A | 31.51 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.93 | 1.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GCD.1683 | 4242-SP1-200 Install-Piping & It's Components (CS-GCD) | 100% | 09-Jun-21 A | 10-Jun-21 A | 22.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GCD.1703 | 4242-SP1-300 Install-Piping & It's Components (CS-GCD) | 100% | 17-Jun-21 A | 17-Jun-21 A | 19.31 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1705 | 4242-SP1-300 Install-Piping & It's Components (CS-GSL) | 100% | 08-Jun-21 A | 24-Jun-21 A | 56.49 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1724 | 4242-SP1-400 Install-Piping & It's Components (CS-GSL) | 0% | 2021-11-03 | 2021-11-03 | 33.22 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1748 | 4242-SP1-500 Install-Piping & It's Components (CS-GSL) | 0% | 2021-10-12 | 2021-10-14 | 39.07 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1776 | 4242-SP1-600 Install-Piping & It's Components (CS-GSL) | 0% | 2021-09-14 | 2021-09-17 | 46.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1856 | 4242-TR-100 Install-Piping & It's Components (CS-GSL) | 100% | 21-Jun-21 A | 24-Jun-21 A | 197.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.1165 | 186.3335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1858 | 4242-TR-400 Install-Piping & It's Components (CS-GSL) | 0% | 2021-11-15 | 2021-11-23 | 197.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.2789 | 158.1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1860 | 4242-TR-500 Install-Piping & It's Components (CS-GSL) | 0% | 2021-11-23 | 2021-11-30 | 197.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.83 | 79.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-GSL.1862 | 4242-TR-600 Install-Piping & It's Components (CS-GSL) | 0% | 2021-12-01 | 2021-12-17 | 197.46 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.6512 | 78.1244 | 76.6844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LCC.1750 | 4242-SP1-500 Install-Piping & It's Components (CS-LCC) | 0% | 2021-10-14 | 2021-10-18 | 56.58 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2218 | 31.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LCC.1778 | 4242-SP1-600 Install-Piping & It's Components (CS-LCC) | 0% | 2021-09-17 | 2021-09-21 | 46.58 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.65 | 39.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1685 | 4242-SP1-200 Install-Piping & It's Components (CS-LPB) | 100% | 08-Jun-21 A | 09-Jun-21 A | 33.29 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6673 | 26.6227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1707 | 4242-SP1-300 Install-Piping & It's Components (CS-LPB) | 100% | 10-Jun-21 A | 17-Jun-21 A | 74.57 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.2227 | 27.3473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1726 | 4242-SP1-400 Install-Piping & It's Components (CS-LPB) | 0% | 2021-11-04 | 2021-11-08 | 59.75 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.2618 | 17.4882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1752 | 4242-SP1-500 Install-Piping & It's Components (CS-LPB) | 0% | 2021-10-19 | 2021-10-22 | 96.8 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1780 | 4242-SP1-600 Install-Piping & It's Components (CS-LPB) | 0% | 2021-09-21 | 2021-09-27 | 85.21 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.51 | 15.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1804 | 4242-SP1-700 Install-Piping & It's Components (CS-LPB) | 100% | 15-Jun-21 A | 08-Jul-21 A | 57.15 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LPB.1822 | 4242-SP1-800 Install-Piping & It's Components (CS-LPB) | 100% | 15-Jun-21 A | 17-Jun-21 A | 62.47 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1709 | 4242-SP1-300 Install-Piping & It's Components (CS-LSH) | 100% | 17-Jun-21 A | 17-Jun-21 A | 19.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1728 | 4242-SP1-400 Install-Piping & It's Components (CS-LSH) | 0% | 2021-11-08 | 2021-11-09 | 19.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1754 | 4242-SP1-500 Install-Piping & It's Components (CS-LSH) | 0% | 2021-10-22 | 2021-10-25 | 19.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8122 | 15.2278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1782 | 4242-SP1-600 Install-Piping & It's Components (CS-LSH) | 0% | 2021-09-27 | 2021-09-28 | 9.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1806 | 4242-SP1-700 Install-Piping & It's Components (CS-LSH) | 0% | 2021-08-06 | 2021-08-06 | 9.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1824 | 4242-SP1-800 Install-Piping & It's Components (CS-LSH) | 100% | 15-Jun-21 A | 17-Jun-21 A | 37.08 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.8 | 25.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-LSH.1844 | 4242-SP1-900 Install-Piping & It's Components (CS-LSH) | 100% | 16-Jun-21 A | 05-Jul-21 A | 37.07 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-SPB.1711 | 4242-SP1-300 Install-Piping & It's Components (CS-SPB) | 100% | 17-Jun-21 A | 24-Jun-21 A | 19.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-SPB.1730 | 4242-SP1-400 Install-Piping & It's Components (CS-SPB) | 0% | 2021-11-09 | 2021-11-10 | 19.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-SPB.1756 | 4242-SP1-500 Install-Piping & It's Components (CS-SPB) | 0% | 2021-10-25 | 2021-10-26 | 24.86 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-SPB.1784 | 4242-SP1-600 Install-Piping & It's Components (CS-SPB) | 0% | 2021-09-28 | 2021-09-30 | 31.03 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-SPB.1808 | 4242-SP1-700 Install-Piping & It's Components (CS-SPB) | 100% | 22-Jun-21 A | 24-Jun-21 A | 35.55 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.42 | 34.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.CS-SPB.1826 | 4242-SP1-800 Install-Piping & It's Components (CS-SPB) | 100% | 21-Jun-21 A | 22-Jun-21 A | 18.08 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1667 | 4242-SP1-100 Install-Piping & It's Components (FRP-LPA) | 0% | 2021-08-12 | 2021-08-16 | 41.62 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.73 | 11.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1687 | 4242-SP1-200 Install-Piping & It's Components (FRP-LPA) | 0% | 2021-08-28 | 2021-08-30 | 30.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1712 | 4242-SP1-300 Install-Piping & It's Components (FRP-LPA) | 0% | 2021-09-06 | 2021-09-10 | 91.92 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1732 | 4242-SP1-400 Install-Piping & It's Components (FRP-LPA) | 0% | 2021-10-14 | 2021-10-16 | 29.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.6333 | 7.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1758 | 4242-SP1-500 Install-Piping & It's Components (FRP-LPA) | 0% | 2021-10-06 | 2021-10-08 | 29.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1786 | 4242-SP1-600 Install-Piping & It's Components (FRP-LPA) | 0% | 2021-09-14 | 2021-09-14 | 19.75 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1810 | 4242-SP1-700 Install-Piping & It's Components (FRP-LPA) | 0% | 2021-08-14 | 2021-08-16 | 19.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1828 | 4242-SP1-800 Install-Piping & It's Components (FRP-LPA) | 0% | 2021-08-10 | 2021-08-11 | 19.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LPA.1846 | 4242-SP1-900 Install-Piping & It's Components (FRP-LPA) | 0% | 2021-08-06 | 2021-08-09 | 19.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.19 | 7.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LSD.1713 | 4242-SP1-300 Install-Piping & It's Components (FRP-LSD) | 0% | 2021-09-10 | 2021-09-11 | 29.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.7 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LSD.1734 | 4242-SP1-400 Install-Piping & It's Components (FRP-LSD) | 0% | 2021-10-16 | 2021-10-19 | 29.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LSD.1788 | 4242-SP1-600 Install-Piping & It's Components (FRP-LSD) | 0% | 2021-09-15 | 2021-09-17 | 38.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LSD.1830 | 4242-SP1-800 Install-Piping & It's Components (FRP-LSD) | 0% | 2021-08-11 | 2021-08-14 | 38.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.6 | 3.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-LSD.1848 | 4242-SP1-900 Install-Piping & It's Components (FRP-LSD) | 0% | 2021-08-09 | 2021-08-10 | 12.18 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-WCW.1669 | 4242-SP1-100 Install-Piping & It's Components (FRP-WCW) | 0% | 2021-08-16 | 2021-08-25 | 208.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122.2246 | 86.4354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-WCW.1689 | 4242-SP1-200 Install-Piping & It's Components (FRP-WCW) | 0% | 2021-08-30 | 2021-09-01 | 47.51 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-WCW.1714 | 4242-SP1-300 Install-Piping & It's Components (FRP-WCW) | 0% | 2021-09-11 | 2021-09-24 | 131.29 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.6312 | 63.6588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-WCW.1736 | 4242-SP1-400 Install-Piping & It's Components (FRP-WCW) | 0% | 2021-10-19 | 2021-10-22 | 85.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-WCW.1760 | 4242-SP1-500 Install-Piping & It's Components (FRP-WCW) | 0% | 2021-10-08 | 2021-10-12 | 85.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.4884 | 59.5316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.FRP-WCW.1790 | 4242-SP1-600 Install-Piping & It's Components (FRP-WCW) | 0% | 2021-09-17 | 2021-09-21 | 55.4 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.2317 | 46.1683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WCW.1671 | 4242-SP1-100 Install-Piping & It's Components (HDPE-WCW) | 100% | 29-Jun-21 A | 29-Jun-21 A | 6.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WCW.1691 | 4242-SP1-200 Install-Piping & It's Components (HDPE-WCW) | 0% | 2021-08-25 | 2021-08-26 | 16.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WCW.1715 | 4242-SP1-300 Install-Piping & It's Components (HDPE-WCW) | 0% | 2021-09-01 | 2021-09-02 | 16.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WCW.1738 | 4242-SP1-400 Install-Piping & It's Components (HDPE-WCW) | 0% | 2021-10-12 | 2021-10-13 | 16.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WCW.1762 | 4242-SP1-500 Install-Piping & It's Components (HDPE-WCW) | 0% | 2021-09-22 | 2021-09-22 | 23.13 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1673 | 4242-SP1-100 Install-Piping & It's Components (HDPE-WPO) | 100% | 29-Jun-21 A | 01-Jul-21 A | 41.67 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.3 | 16.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1693 | 4242-SP1-200 Install-Piping & It's Components (HDPE-WPO) | 0% | 2021-08-26 | 2021-08-27 | 33.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1716 | 4242-SP1-300 Install-Piping & It's Components (HDPE-WPO) | 0% | 2021-09-02 | 2021-09-03 | 21.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1764 | 4242-SP1-500 Install-Piping & It's Components (HDPE-WPO) | 0% | 2021-09-22 | 2021-09-23 | 33.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1792 | 4242-SP1-600 Install-Piping & It's Components (HDPE-WPO) | 0% | 2021-09-06 | 2021-09-09 | 46.77 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1812 | 4242-SP1-700 Install-Piping & It's Components (HDPE-WPO) | 100% | 14-Jul-21 A | 15-Jul-21 A | 23.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1832 | 4242-SP1-800 Install-Piping & It's Components (HDPE-WPO) | 100% | 02-Jul-21 A | 06-Jul-21 A | 46.77 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WPO.1850 | 4242-SP1-900 Install-Piping & It's Components (HDPE-WPO) | 100% | 25-Jun-21 A | 05-Jul-21 A | 44.17 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.31 | 37.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRA.1766 | 4242-SP1-500 Install-Piping & It's Components (HDPE-WRA) | 0% | 2021-09-23 | 2021-09-24 | 18.26 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRA.1794 | 4242-SP1-600 Install-Piping & It's Components (HDPE-WRA) | 0% | 2021-09-09 | 2021-09-10 | 8.26 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRA.1812 | 4242-SP1-700 Install-Piping & It's Components (HDPE-WRA) | 100% | 14-Jul-21 A | 15-Jul-21 A | 8.26 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRA.1834 | 4242-SP1-800 Install-Piping & It's Components (HDPE-WRA) | 100% | 06-Jul-21 A | 07-Jul-21 A | 8.26 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRA.1852 | 4242-SP1-900 Install-Piping & It's Components (HDPE-WRA) | 100% | 05-Jul-21 A | 06-Jul-21 A | 12.72 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1675 | 4242-SP1-100 Install-Piping & It's Components (HDPE-WRO) | 100% | 25-Jun-21 A | 29-Jun-21 A | 34.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1695 | 4242-SP1-200 Install-Piping & It's Components (HDPE-WRO) | 0% | 2021-08-27 | 2021-08-28 | 35.7 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.4136 | 2.2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1717 | 4242-SP1-300 Install-Piping & It's Components (HDPE-WRO) | 0% | 2021-09-03 | 2021-09-06 | 41.55 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.1561 | 25.3939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1740 | 4242-SP1-400 Install-Piping & It's Components (HDPE-WRO) | 0% | 2021-10-13 | 2021-10-14 | 39.78 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1768 | 4242-SP1-500 Install-Piping & It's Components (HDPE-WRO) | 0% | 2021-09-30 | 2021-10-04 | 41.55 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.6113 | 19.9387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1796 | 4242-SP1-600 Install-Piping & It's Components (HDPE-WRO) | 0% | 2021-09-10 | 2021-09-13 | 34.55 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6991 | 31.8509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1814 | 4242-SP1-700 Install-Piping & It's Components (HDPE-WRO) | 100% | 14-Jul-21 A | 15-Jul-21 A | 11.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.HDPE-WRO.1836 | 4242-SP1-800 Install-Piping & It's Components (HDPE-WRO) | 100% | 07-Jul-21 A | 08-Jul-21 A | 26.63 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.75 | 8.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1792 | 4242-SP1-100 Install Insulation / Cladding | 0% | 2021-08-23 | 2021-08-25 | 6.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1794 | 4242-SP1-200 Install Insulation / Cladding | 0% | 2021-08-28 | 2021-09-01 | 15.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1796 | 4242-SP1-300 Install Insulation / Cladding | 0% | 2021-09-09 | 2021-09-24 | 33.57 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7632 | 15.9156 | 13.8911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1798 | 4242-SP1-400 Install Insulation / Cladding | 0% | 2021-11-09 | 2021-11-16 | 38.15 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.7984 | 13.3516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1800 | 4242-SP1-500 Install Insulation / Cladding | 0% | 2021-10-25 | 2021-11-01 | 48.71 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.4716 | 11.2384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1802 | 4242-SP1-600 Install Insulation / Cladding | 0% | 2021-09-17 | 2021-10-09 | 57.55 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67363 | 18.5117 | 18.5117 | 18.5117 | 1.3414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1804 | 4242-SP1-700 Install Insulation / Cladding | 0% | 2021-08-12 | 2021-08-16 | 11.36 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8812 | 5.4788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1806 | 4242-SP1-800 Install Insulation / Cladding | 0% | 2021-08-11 | 2021-08-14 | 16.53 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.3861 | 1.1439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1808 | 4242-SP1-900 Install Insulation / Cladding | 0% | 2021-08-09 | 2021-08-10 | 4.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1810 | 4242-TR-100 Install Insulation / Cladding | 0% | 2021-08-06 | 2021-08-13 | 3.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57326 | 3.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1812 | 4242-TR-400 Install Insulation / Cladding | 0% | 2021-11-15 | 2021-11-23 | 0.18 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.038607 | 0.14139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1814 | 4242-TR-500 Install Insulation / Cladding | 0% | 2021-11-13 | 2021-11-30 | 0.18 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072525 | 0.073881 | 0.033594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.INS.1816 | 4242-TR-600 Install Insulation / Cladding | 0% | 2021-12-09 | 2021-12-17 | 7.06 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1948 | 5.8652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1677 | 4242-SP1-100 Install-Piping & It's Components (SS-LPB) | 100% | 15-Jun-21 A | 16-Jun-21 A | 36.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1697 | 4242-SP1-200 Install-Piping & It's Components (SS-LPB) | 100% | 10-Jun-21 A | 17-Jun-21 A | 52.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1718 | 4242-SP1-300 Install-Piping & It's Components (SS-LPB) | 100% | 17-Jun-21 A | 24-Jun-21 A | 52.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.3817 | 7.5683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1742 | 4242-SP1-400 Install-Piping & It's Components (SS-LPB) | 0% | 2021-11-10 | 2021-11-12 | 46.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1770 | 4242-SP1-500 Install-Piping & It's Components (SS-LPB) | 0% | 2021-10-26 | 2021-10-28 | 46.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1798 | 4242-SP1-600 Install-Piping & It's Components (SS-LPB) | 0% | 2021-10-04 | 2021-10-06 | 34.47 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1816 | 4242-SP1-700 Install-Piping & It's Components (SS-LPB) | 100% | 23-Jun-21 A | 24-Jun-21 A | 9.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-LPB.1838 | 4242-SP1-800 Install-Piping & It's Components (SS-LPB) | 100% | 22-Jun-21 A | 22-Jun-21 A | 9.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1679 | 4242-SP1-100 Install-Piping & It's Components (SS-WSC) | 100% | 15-Jun-21 A | 16-Jun-21 A | 55.73 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1699 | 4242-SP1-200 Install-Piping & It's Components (SS-WSC) | 100% | 09-Jun-21 A | 10-Jun-21 A | 37.74 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1720 | 4242-SP1-300 Install-Piping & It's Components (SS-WSC) | 100% | 17-Jun-21 A | 24-Jun-21 A | 61.96 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1744 | 4242-SP1-400 Install-Piping & It's Components (SS-WSC) | 0% | 2021-11-12 | 2021-11-16 | 62.34 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.6986 | 43.6414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1772 | 4242-SP1-500 Install-Piping & It's Components (SS-WSC) | 0% | 2021-10-29 | 2021-11-01 | 41.12 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.4541 | 24.6659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1800 | 4242-SP1-600 Install-Piping & It's Components (SS-WSC) | 0% | 2021-10-06 | 2021-10-09 | 42.68 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.85 | 6.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1818 | 4242-SP1-700 Install-Piping & It's Components (SS-WSC) | 100% | 07-Jul-21 A | 08-Jul-21 A | 23.37 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1840 | 4242-SP1-800 Install-Piping & It's Components (SS-WSC) | 100% | 22-Jun-21 A | 24-Jun-21 A | 30.03 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.17 | 2.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242.T2.PI.SS-WSC.1854 | 4242-SP1-900 Install-Piping & It's Components (SS-WSC) | 100% | 16-Jun-21 A | 17-Jun-21 A | 51.6 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.CV.1000 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Centrate Tank Agitator (2252-AG-030) | 50% | 30-Jun-21 A | 2021-10-07 | 72.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1000 | 2252-1 - Crude LHM Evaporation & Crystallisation - 2252-SP-001_Crude LHM Crystallisation Sump Pump | 90% | 24-Jun-21 A | 2021-08-13 | 51.48 | Budgeted Labor Units | 25.74 | 25.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1010 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Scrubber Circulation Pumps 2252-PP-03A and 03B | 65% | 16-Jun-21 A | 2021-08-12 | 87.97 | Budgeted Labor Units | 87.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1030 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Concentrate pumps 2252-PP-013A and 013B | 65% | 15-Jun-21 A | 2021-08-10 | 85.39 | Budgeted Labor Units | 85.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1040 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Crystallisers Heat Exch (2252-HX-001) | 100% | 28-Jun-21 A | 29-Jul-21 A | 51.27 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8413 | 22.4287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1050 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Pumps (2252-PP-028 & 029) | 65% | 17-Jun-21 A | 2021-08-23 | 87.97 | Budgeted Labor Units | 0 | 0 | 87.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1060 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Centrifuges (2252-CF-009 & 010) | 100% | 21-Jul-21 A | 05-Aug-21 A | 118.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7294 | 111.5206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1070 | 2252-1 - Crude LHM Evaporation & Crystallisation - Carbonate Precipitation Scrubber Pump (2252-PP-021 & 021B) | 65% | 16-Jun-21 A | 2021-08-16 | 87.97 | Budgeted Labor Units | 0 | 87.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1090 | 2252-1 - Crude LHM Evaporation & Crystallisation- LIOH Crude LIOH Crystalliser Condensate Pump 2252-PP-02A | 65% | 14-Jun-21 A | 2021-08-06 | 64 | Budgeted Labor Units | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1140 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Redissolve Tank Agitators (2252-AG-009 010 011 & 012) | 90% | 22-Jun-21 A | 2021-09-18 | 236.57 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.1452 | 162.6354 | 14.7893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1150 | 2252-1 - Crude LHM Evaporation & Crystallisation - Carbonate Precipitation Scrubber (2252-SR-002) | 50% | 17-Jun-21 A | 2021-08-26 | 336.95 | Budgeted Labor Units | 0 | 0 | 336.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1170 | 2252-1 - Crude LHM Evaporation & Crystallisation - Cranes & Hoists (2252-CN-001 & 002 & 2252-Ht-001) | 0% | 2021-08-27 | 2021-09-02 | 362.6 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 359.6373 | 2.9627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1180 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Centrifuges (2252-CF-001 002 003 & 004) | 100% | 20-Jul-21 A | 29-Jul-21 A | 795 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347.8222 | 447.1778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1190 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Dissolver Tank Agitator (2252-AG-027) | 50% | 30-Jun-21 A | 2021-10-12 | 61.49 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.6537 | 22.8363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1210 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Centrifuges (2252-CF-005 006 007 & 008) | 100% | 20-Jul-21 A | 29-Jul-21 A | 473 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.1336 | 325.1774 | 88.6889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1230 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Crystallisers 1 To 4 (2252-CX-005,006,007 & 008) | 0% | 2021-09-02 | 2021-09-08 | 328 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.4 | 229.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1260 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Precipitation Tank 1 Agitator (2252-AG-028) - T2 | 50% | 28-Jun-21 A | 2021-10-19 | 72 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4 | 57.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1280 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Redissolve Tank Pumps (2252-PP-005 006 007 & 008) - T2 | 65% | 17-Jun-21 A | 2021-08-19 | 175.94 | Budgeted Labor Units | 0 | 175.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1295 | 2252-1 - Crude LHM Evaporation & Crystallisation - Safety Showers | 0% | 2021-10-06 | 2021-10-19 | 276 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215.0946 | 41.1043 | 19.8011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1483 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crystalliser Agitators (2252-AG-005 006 007 & 008) | 50% | 22-Jun-21 A | 2021-10-04 | 163.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157.5524 | 6.3976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.MC.1582 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Vent Scrubber (2252-SR-001) | 25% | 23-Jun-21 A | 2021-09-27 | 397.06 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.3456 | 262.7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PI.1080 | 2252-1 Piping-Hydrotest | 0% | 2022-02-01 | 2022-02-19 | 1016.96 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237.2953 | 372.8831 | 372.8831 | 33.8985 | 0 | 0 | 0 | 0
CN.2252-1.T2.PI.1090 | 2252-1 Piping-S/T & Insulation | 0% | 2022-01-25 | 2022-02-24 | 982.68 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.963 | 221.5106 | 221.5106 | 221.5106 | 181.1851 | 0 | 0 | 0 | 0
CN.2252-1.T2.PI.1094 | 2252-2 Piping-S/T & Insulation | 0% | 2021-11-23 | 2021-12-10 | 244.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.9471 | 95.8736 | 86.2892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.11102 | 2252-1 - Install & Align (S/S) Crude LiOH Redissolve Tank 4 (2252-TK-012) | 100% | 15-Jun-21 A | 21-Jul-21 A | 26.37 | Budgeted Labor Units | 6.5912 | 19.7788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.11106 | 2252-1 - Install & Align (S/S) Crude LiOH Centrate Tank 1 (2252-TK-013) | 100% | 17-Jun-21 A | 22-Jul-21 A | 60.14 | Budgeted Labor Units | 0 | 60.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.11110 | 2252-1 - Install & Align (S/S) Crude LIOH Centrifuge Distribution Feed Tank | 50% | 17-Jun-21 A | 2021-08-11 | 40.96 | Budgeted Labor Units | 0 | 20.48 | 20.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.11114 | 2252-1 - Install & Align(S/S) Lithium Carbonate Precipitation Tank 1 (2252-TK-028) | 50% | 17-Jun-21 A | 2021-08-13 | 82.02 | Budgeted Labor Units | 0 | 0 | 82.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.11118 | 2252-1 - Install & Align(Frp) Lithium Carbonate Centrate Tank (2252-TK-030) | 50% | 16-Jun-21 A | 2021-08-16 | 81.99 | Budgeted Labor Units | 0 | 0 | 78.7636 | 3.2264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.11122 | 2252-1 - Install & Align (Frp) Lithium Carbonate Dissolver Tank (2252-TK-027) | 70% | 24-Jun-21 A | 2021-08-18 | 92.28 | Budgeted Labor Units | 0 | 0 | 0 | 92.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.11126 | 2252-1 - Install Crude LiOH Centrifuge Solids Chutes (2252-CH-011,012,013,014,015,016,017,018 & 019) | 100% | 15-Jul-21 A | 22-Jul-21 A | 191.25 | Budgeted Labor Units | 0 | 0 | 0 | 114.75 | 76.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.1188 | 2252-1 - Align (S/S) Crude LiOH Redissolve Tank 1 (2252-TK-009) | 100% | 11-Jun-21 A | 16-Jul-21 A | 26.4 | Budgeted Labor Units | 26.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.1192 | 2252-1 - Align (S/S) Crude LiOH Redissolve Tank 2 (2252-TK-010) | 100% | 12-Jun-21 A | 19-Jul-21 A | 26.37 | Budgeted Labor Units | 26.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.PL.1196 | 2252-1 - Align (S/S) Crude LiOH Redissolve Tank 3 (2252-TK-011) | 100% | 14-Jun-21 A | 20-Jul-21 A | 26.38 | Budgeted Labor Units | 26.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1338 | 2252-1 - Install lower columns tie in beams and bracing to grid lines A and B | 100% | 01-Jun-21 A | 11-Jun-21 A | 273.4 | Budgeted Labor Units | 239.225 | 34.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1342 | 2252-1 - Install full level 1 floor module MM 120 between grid lines A and B | 100% | 02-Jun-21 A | 14-Jun-21 A | 426.47 | Budgeted Labor Units | 0 | 426.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1346 | 2252-1 - Install lower columns tie in beams and bracing to grid line C | 100% | 03-Jun-21 A | 14-Jun-21 A | 142.04 | Budgeted Labor Units | 0 | 142.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1350 | 2252-1 - Install full level 1 floor module MM 121 between grid lines B and C | 100% | 04-Jun-21 A | 15-Jun-21 A | 90.56 | Budgeted Labor Units | 0 | 90.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1354 | 2252-1 - Install lower columns tie in beams and bracing to grid line D | 100% | 05-Jun-21 A | 16-Jun-21 A | 146.05 | Budgeted Labor Units | 0 | 14.6337 | 131.4163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1358 | 2252-1 - Install full level 1 floor module MM 122 between grid lines C and D | 100% | 07-Jun-21 A | 16-Jun-21 A | 311.66 | Budgeted Labor Units | 0 | 0 | 311.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1362 | 2252-1 - Install lower columns tie in beams and bracing to grid line E | 95% | 08-Jun-21 A | 2021-08-06 | 142.2 | Budgeted Labor Units | 0 | 0 | 142.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1366 | 2252-1 - Install full level 1floor module MM 123 between grid lines D and E | 100% | 09-Jun-21 A | 17-Jun-21 A | 247.61 | Budgeted Labor Units | 0 | 0 | 49.3641 | 198.2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1370 | 2252-1 - Install lower level diagonal bracing between grid lines D and E | 100% | 17-Jun-21 A | 22-Jun-21 A | 66.27 | Budgeted Labor Units | 0 | 0 | 0 | 66.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1374 | 2252-1 - Install full level 2 floor module MM 130 between grid lines A and B | 100% | 22-Jun-21 A | 23-Jun-21 A | 660.13 | Budgeted Labor Units | 0 | 0 | 0 | 593.9799 | 66.1501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1378 | 2252-1 - Install full level 2 floor module MM 131 between grid lines B and C | 100% | 25-Jun-21 A | 26-Jun-21 A | 312.93 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 219.5429 | 93.3871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1382 | 2252-1 - Install full level 2 floor module MM 132 between grid lines C and D | 100% | 23-Jun-21 A | 24-Jun-21 A | 460.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 460.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1386 | 2252-1 - Install full level 2 floor module MM 133 between grid lines D and E | 100% | 28-Jun-21 A | 28-Jun-21 A | 457.49 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 411.3165 | 46.1735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1390 | 2252-1 - Install fully assembled western stair tower to level 2 MM100 | 100% | 17-Jun-21 A | 26-Jul-21 A | 405.06 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 405.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1394 | 2252-1 - Install southern pipe rack Grid A - E and level 1-2 | 95% | 05-Jul-21 A | 2021-08-12 | 392.24 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 244.6123 | 147.6277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1398 | 2252-1 - Install upper columns tie in beams and bracing to grid lines A and B | 0% | 12-Aug-21* | 2021-08-17 | 103.56 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.835 | 64.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1399 | 2252-1 - Install full level 3 floor module MM 170 between grid lines A and B | 0% | 2021-08-25 | 2021-08-27 | 381.59 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1402 | 2252-1 - Install upper columns tie in beams and bracing to grid line C | 0% | 2021-08-27 | 2021-08-30 | 7.84 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4716 | 5.3684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1406 | 2252-1 - Install full level 3 floor module MM 171 between grid lines B and C | 0% | 2021-08-30 | 2021-08-31 | 260.48 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1410 | 2252-1 - Install upper columns tie in beams and bracing to grid line D | 0% | 2021-08-31 | 2021-09-02 | 11.57 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1414 | 2252-1 - Install full level 3 floor module MM 172 between grid lines C and D | 0% | 2021-09-02 | 2021-09-04 | 289.57 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267.2823 | 22.2877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1418 | 2252-1 - Install upper columns tie in beams and bracing to grid lines E | 0% | 2021-09-04 | 2021-09-07 | 38.18 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1422 | 2252-1 - Install full level 3 floor module MM 173 between grid lines D and E | 0% | 2021-09-07 | 2021-09-08 | 316.4 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1430 | 2252-1 - Install full level 4 floor module MM 180 between grid lines A and B | 0% | 2021-09-10 | 2021-09-13 | 132.18 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.8432 | 79.3368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1434 | 2252-1 - Install full level 4 floor module MM 181 between grid lines B and C | 0% | 2021-09-13 | 2021-09-14 | 189.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1438 | 2252-1 - Install full level 4 floor module MM 182 between grid lines C and D | 0% | 2021-09-14 | 2021-09-15 | 163.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1442 | 2252-1 - Install full level 4 floor module MM 183 between grid lines D and E | 0% | 2021-09-15 | 2021-09-16 | 168.86 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1446 | 2252-1 - Install fully assembled western stair tower to level 4 MM 100-7 | 100% | 30-Jun-21 A | 29-Jul-21 A | 34.17 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1454 | 2252-1 - Install pipe supports and miscellaneous steel grid A - B under level 1 | 100% | 25-Jun-21 A | 28-Jun-21 A | 99.24 | Budgeted Labor Units | 86.7956 | 12.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1458 | 2252-1 - Install pipe supports and miscellaneous steel grid B - C under level 1 | 100% | 23-Jun-21 A | 22-Jul-21 A | 168.95 | Budgeted Labor Units | 0 | 168.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1462 | 2252-1 - Install pipe supports and miscellaneous steel grid C - D under level 1 | 100% | 01-Jul-21 A | 22-Jul-21 A | 92.2 | Budgeted Labor Units | 0 | 5.2793 | 86.9207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1466 | 2252-1 - Install pipe supports and miscellaneous steel grid D - E under level 1 | 100% | 01-Jul-21 A | 29-Jul-21 A | 188.12 | Budgeted Labor Units | 0 | 0 | 164.5375 | 23.5825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1470 | 2252-1 - Install pipe supports and miscellaneous steel grid A - B under level 2 | 100% | 22-Jun-21 A | 15-Jul-21 A | 723.51 | Budgeted Labor Units | 0 | 0 | 0 | 723.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1474 | 2252-1 - Install pipe supports and miscellaneous steel grid B - C under level 2 | 100% | 22-Jun-21 A | 15-Jul-21 A | 290.49 | Budgeted Labor Units | 0 | 0 | 0 | 72.6225 | 217.8675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1478 | 2252-1 - Install pipe supports and miscellaneous steel grid C - D under level 2 | 100% | 22-Jun-21 A | 15-Jul-21 A | 551.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 459.5833 | 91.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1482 | 2252-1 - Install pipe supports and miscellaneous steel grid D - E under level 2 | 100% | 08-Jul-21 A | 29-Jul-21 A | 462.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 462.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1486 | 2252-1 - Install pipe supports and miscellaneous steel grid A - B under level 3 | 20% | 30-Jul-21 A | 2021-08-11 | 343.37 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 85.8425 | 257.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1490 | 2252-1 - Install pipe supports and miscellaneous steel grid B - C under level 3 | 0% | 2021-08-11 | 2021-08-16 | 235.76 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.35 | 88.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1494 | 2252-1 - Install pipe supports and miscellaneous steel grid C - D under level 3 | 0% | 2021-08-17 | 2021-08-19 | 193.21 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1498 | 2252-1 - Install pipe supports and miscellaneous steel grid D - E under level 3 | 0% | 2021-08-20 | 2021-08-25 | 189.92 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.48 | 142.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1502 | 2252-1 - Install miscellaneous platforms and pipe supports to all four floors | 30% | 29-Jun-21 A | 2021-09-06 | 207.6 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.5544 | 126.5314 | 57.5143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1506 | 2252-1 - Tension, testing and quality completions | 40% | 24-Jun-21 A | 2021-09-18 | 1393.48 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185.8467 | 255.4467 | 255.4467 | 255.4467 | 255.4467 | 185.8467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-1.T2.ST.1510 | 2252-1 - Grouting | 20% | 01-Jul-21 A | 2021-09-18 | 348.32 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126.4438 | 198.6973 | 23.1789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1000 | 2252-2 - Pure LHM Filtration - Polishing Filters 1, 2 & 3 (2252-FL-001 002 & 003) Inc. Crane | 0% | 2021-09-09 | 2021-10-07 | 1488.77 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.6014 | 375.6629 | 375.6629 | 375.6629 | 342.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1020 | 2252-2 - Pure LHM Filtration - Redissolved LIOH Cake Reslurry Pumps 1, 2 & 3 (2252-PP-009, 011 & 030) | 60% | 24-Jun-21 A | 2021-08-17 | 132.04 | Budgeted Labor Units | 0 | 0 | 0 | 88.0267 | 44.0133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1030 | 2252-2 - Pure LHM Filtration - Redissolved LIOH Cake Reslurry Tank Agitators (2252-AG-015 017 & 031) | 90% | 10-Jun-21 A | 2021-08-13 | 347.12 | Budgeted Labor Units | 0 | 0 | 115.7467 | 231.3733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1040 | 2252-2 - Pure LHM Filtration - Redissolved LIOH Primary & Secondary Polishing Filtrate Pumps (2252-PP-010 & 012) - T2 | 60% | 24-Jun-21 A | 2021-08-20 | 87.97 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 87.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1050 | 2252-2 - Pure LHM Filtration - Redissolved LIOH Cloth & Core Wash Pumps (2252-PP-024 & 026) | 50% | 24-Jun-21 A | 2021-08-19 | 44.05 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 44.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1051 | 2252-2 - Pure LHM Filtration - Redissolve Bulk Bag | 0% | 2021-08-23 | 2021-08-30 | 88.86 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.1207 | 14.7393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1052 | 2252-2 - Pure LHM Filtration - Redissolve Seal Pot | 0% | 2021-08-19 | 2021-08-21 | 75 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.33 | 16.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1053 | 2252-2 - Pure LHM Filtration - Filtration Sump Pump | 100% | 08-Jul-21 A | 15-Jul-21 A | 51.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 51.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.MC.1054 | 2252-2 - Crude LHM Crystallisation Safety Showers | 0% | 2021-10-22 | 2021-11-02 | 108.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.6978 | 74.3142 | 26.998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.PI.1092 | 2252-2 Piping-Hydrotest | 0% | 2021-11-16 | 2021-12-06 | 832.47 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606.0308 | 15.9547 | 15.9547 | 194.5298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1230 | 2252-2 - Install (all) 20 columns C 1008 - C 1027 and level | 100% | 08-Jun-21 A | 10-Jun-21 A | 487.58 | Budgeted Labor Units | 0 | 487.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1240 | 2252-2 - Install module MM412 RL 19.350 Northern gridline on between grid 1 and 2 | 100% | 14-Jun-21 A | 15-Jun-21 A | 348.8 | Budgeted Labor Units | 0 | 26.724 | 322.076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1250 | 2252-2 - Install module MM411 RL 19.350 between grid 2 and 3 and A and C | 100% | 15-Jun-21 A | 16-Jun-21 A | 205.14 | Budgeted Labor Units | 0 | 0 | 205.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1260 | 2252-2 - Install stick steel horizontal tie in beams on southern grid lines RL 19.098 | 100% | 17-Jun-21 A | 22-Jun-21 A | 70.48 | Budgeted Labor Units | 0 | 0 | 70.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1270 | 2252-2 - Install level I North/East corners tie beams and bracing | 100% | 25-Jun-21 A | 25-Jun-21 A | 6.13 | Budgeted Labor Units | 0 | 0 | 0 | 6.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1280 | 2252-2 - Install level 1 walkway modules MM 413, 414 and 415 | 100% | 22-Jun-21 A | 24-Jun-21 A | 109.81 | Budgeted Labor Units | 0 | 0 | 76.867 | 32.943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1290 | 2252-2 - Install module MM417 RL 19.350 between grid 2 and 3 and C and E | 100% | 16-Jun-21 A | 17-Jun-21 A | 188.25 | Budgeted Labor Units | 0 | 0 | 188.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1300 | 2252-2 - Install tank access underslung modules MM 400,401 and 402 | 100% | 17-Jun-21 A | 24-Jun-21 A | 107.94 | Budgeted Labor Units | 0 | 0 | 0 | 107.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1310 | 2252-2 - Install level 1 module MM 410 south west corner | 100% | 14-Jun-21 A | 15-Jun-21 A | 94.76 | Budgeted Labor Units | 0 | 0 | 0 | 94.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1324 | 2252-2 - Install module MM 437 level 2 North East corner floor module | 100% | 05-Jul-21 A | 06-Jul-21 A | 237.15 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 237.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1328 | 2252-2 - Install module MM 421 level 2 North West corner floor module | 100% | 06-Jul-21 A | 07-Jul-21 A | 252.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 252.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1332 | 2252-2 - Install fully assembled stair tower module MM 481 North West Corner | 100% | 15-Jun-21 A | 12-Jul-21 A | 264.83 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 24.7873 | 240.0427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1336 | 2252-2 - Install module MM 420 level 2 South West corner floor module | 100% | 12-Jul-21 A | 13-Jul-21 A | 242.32 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 238.9752 | 3.3448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1340 | 2252-2 - Install module MM 436 level 2 South East corner floor module | 100% | 13-Jul-21 A | 14-Jul-21 A | 306.48 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 249.8615 | 56.6185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1344 | 2252-2 - Install walkway modules 431, 432, 433 and 434 to level 2 North side of building | 100% | 19-Jul-21 A | 21-Jul-21 A | 146.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.5317 | 129.6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1348 | 2252-2 - Install walkway modules 427, 428, 429 and 430 to level 2 North side of building | 50% | 30-Jul-21 A | 2021-08-09 | 155.97 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1352 | 2252-2 - Install fully assembled stair tower module MM 480 South East Corner | 100% | 16-Jun-21 A | 15-Jul-21 A | 199.05 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1356 | 2252-2 - Install staircase tie in modules to main building | 100% | 01-Jul-21 A | 08-Jul-21 A | 4.83 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1360 | 2252-2 - Install filter support modules MM 422, 423, 424 and 425 to top of structure | 90% | 22-Jul-21 A | 2021-08-11 | 90.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.198 | 63.462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1364 | 2252-2 - Install miscellaneous steel work and platforms to top level structure surrounding filters | 0% | 2021-08-11 | 2021-08-18 | 499.74 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.1145 | 455.6255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1368 | 2252-2 - Finish all diagonal and horizontal pipe bracing to building | 75% | 22-Jul-21 A | 2021-08-24 | 62.9 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.61 | 6.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1372 | 2252-2 - Install pipe supports and miscellaneous brackets to steel work under level 1 | 100% | 26-Jun-21 A | 22-Jul-21 A | 499.71 | Budgeted Labor Units | 0 | 0 | 0 | 75.4787 | 143.1437 | 143.1437 | 137.9438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1376 | 2252-2 - Install pipe supports and miscellaneous brackets to steel work under level 2 | 85% | 06-Jul-21 A | 2021-08-24 | 1019.09 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 315.6641 | 94.241 | 94.241 | 514.9439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1380 | 2252-2 - Install guard supports and guarding to crane rails bothe side full length of building | 0% | 2021-08-24 | 2021-09-01 | 8.55 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.275 | 4.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1384 | 2252-2 - Install pipe supports and stair modules around filter walkways | 0% | 2021-09-02 | 2021-09-09 | 233.61 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.87 | 155.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1388 | 2252-2 - Tension, testing and quality completions | 50% | 26-Jul-21 A | 2021-09-09 | 820.9 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.9547 | 179.8767 | 179.8767 | 179.8767 | 179.8767 | 29.4383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-2.T2.ST.1392 | 2252-2 - Grouting | 0% | 2021-09-09 | 2021-09-25 | 205.23 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.6833 | 86.8267 | 86.8267 | 7.8933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3 T2.Insul.1223 | 2252-3 - Insulation Works to 2252-PV-001 | 0% | 2021-10-12 | 2021-10-26 | 708.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236.2868 | 324.9448 | 147.7484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3 T2.Insul.1294 | 2252-3 - Insulation Works to 2252-HX-006 | 0% | 2021-09-21 | 2021-09-30 | 478.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.3573 | 431.6227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.Insul.1296 | 2252-3 - Insulation Works to 2252-PV-002 | 0% | 2021-10-01 | 2021-10-04 | 78 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.Insul.1298 | 2252-3 - Insulation Works to 2252-HX-004 | 0% | 2021-10-04 | 2021-10-06 | 78 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.Insul.1300 | 2252-3 - Insulation Works to 2252-HX-010 | 0% | 2021-10-06 | 2021-10-08 | 78 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.Insul.1302 | 2252-3 - Insulation Works to 2252-PV-003 | 0% | 2021-10-08 | 2021-10-11 | 76 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.Insul.1304 | 2252-3 - Insulation Works to 2252 Ducting Connections | 0% | 2021-10-27 | 2021-12-16 | 1259.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94.4252 | 173.1128 | 173.1128 | 173.1128 | 173.1128 | 173.1128 | 173.1128 | 125.9182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1001 | 2252-3 - Install CrudeLHM Cystaliser MVR compressor 2525-CP-001 and vacuum tank | 100% | 11-Jun-21 A | 15-Jun-21 A | 1185.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223.6238 | 961.3962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1200 | 2252-3 - Install CrudeLHM Crystalliser Compression water discharge tank 2252-TK-037 | 90% | 18-Jun-21 A | 2021-08-06 | 41.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1220 | 2252-3 - Install CrudeLHM Crystalliser Compressor drain pump 2252-PP-034 | 75% | 16-Jun-21 A | 2021-08-09 | 32 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4 | 25.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1272 | 2252-3 - Install CrudeLHM Crystalliser gland seal water pumps 2252-PP- 023A and 023B | 75% | 17-Jun-21 A | 2021-08-11 | 87.93 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1276 | 2252-3 - Install CrudeLHM Crystalliser gland seal water tank 2252-TK-005 | 90% | 23-Jun-21 A | 2021-08-12 | 41.03 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1283 | 2252-3 - Install CrudeLHM Crystalliser Concentrate pumps 2252-PP-032A and 032B | 75% | 17-Jun-21 A | 2021-08-14 | 132.15 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112.3275 | 19.8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1285 | 2252-3 - Install CrudeLHM Crystalliser vacuum pumps 2252-PP-033A and 033B (Level 2) | 75% | 17-Jun-21 A | 2021-08-16 | 175.03 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.7575 | 131.2725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1290 | 2252-3 - Install CrudeLHM Crystalliser vent condensor 2252-HX-004 9Level 4 - 5.5) | 0% | 2021-09-21 | 2021-09-23 | 51.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.MC.1291 | 2252-3 - Install CrudeLHM Crystalliser pre heater 5 2252-HX-004 | 0% | 2021-09-23 | 2021-09-27 | 205 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151.7 | 53.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1180 | 2252-3 - Assemble and install stairs to level 3 | 100% | 15-Jul-21 A | 22-Jul-21 A | 327.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 327.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1190 | 2252-3 - Install level 3 RL 31.400 floor module 120 | 100% | 22-Jul-21 A | 22-Jul-21 A | 89.24 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1200 | 2252-3 - Assemble and install level2 RL 25.400 north west module | 100% | 24-Jun-21 A | 30-Jun-21 A | 386.87 | Budgeted Labor Units | 0 | 0 | 0 | 386.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1210 | 2252-3 - Erect 8 off second tier columns | 100% | 18-Jun-21 A | 24-Jun-21 A | 211.76 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 211.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1220 | 2252-3 - Assemble and install stairs to level 2 | 100% | 02-Jul-21 A | 02-Jul-21 A | 39.8 | Budgeted Labor Units | 0 | 0 | 0 | 39.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1230 | 2252-3 - Install level 3.5 RL 31.400 module 122 | 100% | 21-Jul-21 A | 22-Jul-21 A | 18.79 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1250 | 2252-3 - Erect 8 off base columns (C 1001 - 1008) | 100% | 25-Jun-21 A | 25-Jun-21 A | 192.68 | Budgeted Labor Units | 0 | 0 | 192.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1260 | 2252-3 - Install level 1 RL 19.400 floor modules 100 and 101 | 100% | 12-Jun-21 A | 15-Jun-21 A | 305.8 | Budgeted Labor Units | 0 | 0 | 305.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1270 | 2252-3 - Install level 2 RL 25.400 floor modules 110 and 111 and 113 | 100% | 22-Jun-21 A | 29-Jun-21 A | 358.13 | Budgeted Labor Units | 0 | 0 | 0 | 358.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1280 | 2252-3 - Assemble and install remaining floor steel RL 31.400 | 80% | 08-Jul-21 A | 2021-09-09 | 154.86 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1290 | 2252-3 - Install stick steel pipe bracing | 100% | 01-Jul-21 A | 05-Jul-21 A | 197.53 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 197.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1300 | 2252-3 - Install level 4 RL 36.000 floor module 130 | 0% | 2021-09-09 | 2021-09-10 | 94.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1310 | 2252-3 - Assemble and install level 1 RL 19.400 north west module | 100% | 18-Jun-21 A | 21-Jun-21 A | 231.46 | Budgeted Labor Units | 0 | 0 | 231.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1320 | 2252-3 - Assemble and install stairs to level 1 | 100% | 26-Jun-21 A | 28-Jun-21 A | 184.41 | Budgeted Labor Units | 0 | 0 | 92.205 | 92.205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1324 | 2252-3 - Assemble and install remaining floor steel RL 36.000 | 30% | 29-Jul-21 A | 2021-09-14 | 47.27 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.5333 | 15.7367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1332 | 2252-3 - Install level 4 RL 40.200 floor modules 140 and 141 | 30% | 22-Jul-21 A | 2021-09-17 | 199 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1336 | 2252-3 - Assemble and install remaining tie in stick steel RL 40.200 | 30% | 29-Jul-21 A | 2021-09-20 | 5.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1344 | 2252-3 - Install level 5.5 module150 | 0% | 2021-09-21 | 2021-09-22 | 78.91 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1348 | 2252-3 - Erect 6 off third teir columns | 0% | 2021-09-22 | 2021-09-23 | 73.54 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1352 | 2252-3 - Install level 6 module 160 | 0% | 2021-09-23 | 2021-10-01 | 202.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.9535 | 154.4265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1360 | 2252-3 - Install southern piperack section between levels 1 and 2 | 100% | 19-Jul-21 A | 21-Jul-21 A | 129.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1364 | 2252-3 - Install remaining pipe bracing | 50% | 22-Jul-21 A | 2021-10-06 | 22.85 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1368 | 2252-3 - Install 2252-1 and 2252-3 tie in modules 102, 112, 121 and 131 | 0% | 2021-10-06 | 2021-10-07 | 142.75 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1372 | 2252-3 - Tension and testing | 20% | 08-Jul-21 A | 2021-10-07 | 576.31 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 347.6821 | 228.6279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-3.T2.ST.1376 | 2252-3 - Grouting | 0% | 2021-10-04 | 2021-10-07 | 144.07 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.PI.1094 | 2252-4 Piping-Hydrotest | 0% | 2021-10-18 | 2021-11-04 | 529.39 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.4185 | 194.1143 | 158.8572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.PI.1096 | 2252-4 Piping-S/T & Insulation | 0% | 2021-10-25 | 2021-11-10 | 717.56 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398.2261 | 53.8497 | 265.4841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1198 | 2252-4 - Pipe Support Pre-assembly | 100% | 25-Jun-21 A | 30-Jun-21 A | 772.71 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 772.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1202 | 2252-4 - Install Stair Tower Module 300 | 100% | 17-Jun-21 A | 09-Jul-21 A | 156.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.005 | 78.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1206 | 2252-4 - Panelise & Install Structures on Grid line D1 - E on grids 6-9 | 100% | 17-Jun-21 A | 04-Aug-21 A | 270.61 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1210 | 2252-4 - Stick Build Structures on Grid Line E - E1 on grids 7-9 | 80% | 24-Jun-21 A | 2021-08-18 | 246.29 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242.1573 | 4.1327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1214 | 2252-4 - Install Platform Module No: 311 over TK024 | 100% | 14-Jul-21 A | 15-Jul-21 A | 76.89 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.5736 | 58.3164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1218 | 2252-4 - Install Walkway Module 310 | 100% | 01-Jul-21 A | 22-Jul-21 A | 39.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1222 | 2252-4 - Install Walkway Module 312 | 100% | 01-Jul-21 A | 22-Jul-21 A | 13.73 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1226 | 2252-4 - Install Walkway Module 313 | 100% | 01-Jul-21 A | 22-Jul-21 A | 15.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1230 | 2252-4 - Install Platform Module No: 344 over TK004 | 100% | 17-Jun-21 A | 08-Jul-21 A | 56.61 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.644 | 33.966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1234 | 2252-4 - Install Two Sets of Interconnecting Stairs | 95% | 29-Jul-21 A | 2021-08-20 | 107.82 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1238 | 2252-4 - Install Platform Module No: 342 over TK003 | 100% | 17-Jun-21 A | 08-Jul-21 A | 54.72 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1242 | 2252-4 - Install Platform Module No: 340 over TK002 | 100% | 17-Jun-21 A | 08-Jul-21 A | 55.09 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1246 | 2252-4 - Install Platform Modules 341 & 343 plus Interconnecting Steelwork | 100% | 01-Jul-21 A | 29-Jul-21 A | 52.36 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6313 | 39.7287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1250 | 2252-4 - Install Valve Access Underslung Modules 320 & 321 | 90% | 29-Jun-21 A | 2021-08-25 | 110.86 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1254 | 2252-4 - Install Remaining Pipe Supports | 60% | 01-Jul-21 A | 2021-08-30 | 237.36 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.934 | 231.426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-4.T2.ST.1258 | 2252-4 - Tension, Testing, Survey & FIC Completions | 35% | 01-Jul-21 A | 2021-09-06 | 339.87 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.5216 | 314.3484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.MC.1286 | 2252-5 - Crude LHM Evaporation & Crystallisation - Pure LIOH Crystalliser Feed Pumps (2252-PP-031A, 031B) | 35% | 22-Jul-21 A | 2021-09-13 | 88.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.3333 | 58.6767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.MC.1288 | 2252-5 - Crude LHM Evaporation & Crystallisation - Crude LHM Crystalliser Recirculation Pump (2252-PP-027) | 0% | 2021-09-13 | 2021-09-27 | 591.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.2245 | 439.3176 | 112.708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.MC.1291 | 2252-5 - Crude LHM Evaporation & Crystallisation - Crude LIOH Crystalliser Cooling Condensate Surge Pump 2252-PP-025) | 35% | 22-Jul-21 A | 2021-09-13 | 43.96 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.MC.1374 | 2252-5 - Pre-assembly of all Pipe Supports | 100% | 26-Jul-21 A | 28-Jul-21 A | 103.62 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.MC.1378 | 2252-5 - Install Pre-assembled Tank Top Modules 362, 363 & 364 | 95% | 23-Jun-21 A | 2021-09-01 | 142.15 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.MC.1381 | 2252-5 - Crude LHM Evaporation & Crystallisation - Safety Showers | 0% | 2021-09-13 | 2021-09-21 | 12 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.4717 | 4.5283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.MC.1382 | 2252-5 - Assemble & Install Underslung Valve Access Modules 360 & 361 | 95% | 23-Jun-21 A | 2021-09-03 | 80.4 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.MC.1386 | 2252-5 - Tension Testing & FIC Completion | 25% | 08-Jul-21 A | 2021-09-04 | 57.58 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.PI.1098 | 2252-5 Piping-Hydrotest | 0% | 2021-09-13 | 2021-10-06 | 600.71 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466.1118 | 63.007 | 63.007 | 8.5842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-5.T2.PI.1100 | 2252-5 Piping-S/T & Insulation | 0% | 2021-09-17 | 2021-10-12 | 13.26 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68155 | 3.7395 | 3.7395 | 3.7395 | 1.3598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-6.T2.ST.1380 | 2252-6 - Crude LHM Ground Supports - Install Ground Supports | 100% | 09-Jul-21 A | 05-Aug-21 A | 354.1 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.322 | 88.4352 | 88.4352 | 88.4352 | 14.4724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-6.T2.ST.1390 | 2252-6 - Structural Steel Punch List and Construction Verification | 0% | 2021-08-18 | 2021-08-25 | 67.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.1174 | 39.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-7.T2.ST.1400 | 2252-7 - Crude LHM Ground Supports - Install Ground Supports | 80% | 09-Jul-21 A | 2021-09-16 | 212.17 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.1647 | 55.5691 | 55.5691 | 55.5691 | 29.2978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-7.T2.ST.1410 | 2252-7 - Structural Steel Punch List and Construction Verification | 0% | 2021-09-16 | 2021-09-25 | 140.63 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.4611 | 37.7305 | 27.4384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2252-7.T2.ST.1412 | 2252-7 - Grouting | 0% | 2021-09-25 | 2021-10-05 | 35.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.6155 | 9.5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262-4.T2.ST.1551 | 2262-4 - Install Miscellaneous Supports | 0% | 2022-02-09 | 2022-03-09 | 433.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146.4112 | 48.7751 | 48.7751 | 48.7751 | 140.9537 | 0 | 0
CN.2262-4.T2.ST.1554 | 2262-4 - Structural Steel Punch List and Construction Verification | 0% | 2022-03-08 | 2022-03-14 | 76.54 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.1713 | 18.3687 | 0
CN.2262.T2.MC.1010 | 2262-2 - Install Pure LHM Crystalliser Condensate Pump 2262-PP-002 | 75% | 09-Jul-21 A | 2021-08-06 | 22 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1020 | 2262-2 - Install Pure LHM Centrate Transfer Pump 2262-PP-006 | 75% | 17-Jul-21 A | 2021-08-09 | 38.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1030 | 2262-2 - Install Pure LHM Crystalliser Seal Water Pumps 2622- PP- 008A and 008B | 75% | 09-Jun-21 A | 2021-08-11 | 44 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1040 | 2262-2 - Install Pure LHM Crystalliser Recirculation Pump2622-PP-012 | 75% | 24-Jun-21 A | 2021-08-12 | 45.03 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1060 | 2262-1 Install Pure LHM Cyrstalliser Heat Exchanger 2262-HX-001 | 100% | 12-Jun-21 A | 21-Jun-21 A | 12.4 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1070 | 2262-2 - Install Pure LHM Crystalliser Blowdown Pump 2262-PP-009 | 75% | 09-Jun-21 A | 2021-08-13 | 22 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1080 | 2262-1 Install LIOH Crystalliser Cooling Condensate pump 2262-PP-011 | 100% | 07-Jun-21 A | 22-Jun-21 A | 124.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1090 | 2262-2 - Install Pure LHM Crystalliser Condesate Pumps 2262-PP-014A and 014B | 75% | 10-Jun-21 A | 2021-08-16 | 76 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1100 | 2262-2 - Install Pure LHM Crystalliser Compressor Drain Pump 2262-PP-016 | 75% | 10-Jun-21 A | 2021-08-17 | 22.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1120 | 2262-1 Install Pure LHM Cyrstalliser sump pump 2262-SP-001 | 100% | 15-Jun-21 A | 23-Jun-21 A | 30.32 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1160 | 2262-1 Install pure LIOH Concentrate pumps 2262-PP-004 and 005 | 100% | 16-Jun-21 A | 24-Jun-21 A | 111.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1172 | 2262-1 5 of Pure LIOH Centrifuges c/w hydraulic power packs 2262-HU-001 - 005 | 100% | 25-Jun-21 A | 04-Aug-21 A | 720.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220.2122 | 251.2941 | 249.4436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1173 | 2262-2 - Install Pure LHM Crystalliser MVR Compressor 2262-CP-001 with access and maitenanace platform | 50% | 14-Jul-21 A | 2021-08-20 | 212.43 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1174 | 2262-2 - Install Pure LHM Crystalliser Sump Pump 2262-SP-002 with support platform and grating | 80% | 22-Jul-21 A | 2021-08-24 | 22.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1175 | 2262-2 - Install Pure LHM Crystalliser Compressor Water Discharge Tank 2262-TK-015 | 100% | 06-Jul-21 A | 08-Jul-21 A | 17.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1176 | 2262-2 - Install Pure LHM Crystalliser Gland Seal Water Tank 2262-TK-004 | 100% | 07-Jul-21 A | 08-Jul-21 A | 26.11 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1177 | 2262-2 - Install Pure LHM Crystalliser Condenstae tank 2262-PV-002 | 100% | 07-Jul-21 A | 08-Jul-21 A | 63 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1178 | 2262-2 - Install Pure LHM Crystalliser Vacuum Pumps 2262- PP-015A and 015B | 75% | 24-Jun-21 A | 2021-08-09 | 87.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.9875 | 65.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1179 | 2262-2 - Install Pure LHM Crystalliser Vacuum Pump Seal Water Tank 2262-TK-001 | 100% | 23-Jun-21 A | 23-Jun-21 A | 17.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1180 | 2262-2 - Install LHM Crystalliser Feed Pre-heaters 2262-HX-002A and 002B | 100% | 30-Jun-21 A | 01-Jul-21 A | 700.7 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1181 | 2262-2 - Install LHM Crystalliser Feed Pre-heaters 2262-HX-003A and 003B | 100% | 30-Jun-21 A | 01-Jul-21 A | 12 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1182 | 2262-2 - Install Pure LHM Crystalliser Concentrate Pumps 2262- PP-001A and 001B | 75% | 09-Jul-21 A | 2021-08-11 | 77.15 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1183 | 2262-2 - Install LHM Pure Cyrstalliser Feed Pre-heater 5 2260-HX-009 | 0% | 2021-08-25 | 2021-08-30 | 8.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.408 | 1.602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1187 | 2262-1 5 of Pure LIOH Centrifuges c/w hydraulic power packs 2262-HU-006 - 010 | 100% | 25-Jun-21 A | 05-Aug-21 A | 748.56 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.8135 | 274.4665 | 274.4665 | 99.8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1191 | 2262-1 Install 4 off Pure LIOH Crystallisers 2262-CX-004 - 007 c/w Agitaters | 0% | 2021-08-24 | 2021-09-18 | 797.86 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138.2352 | 217.2268 | 217.2268 | 217.2268 | 7.9444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1195 | 2262-1 Assemble and install Pure LIOH Centrifuge and Cyrstalliser Gantry crane (2262-CN - 001) | 0% | 2021-09-28 | 2021-10-02 | 326.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.0574 | 201.9626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1199 | 2262-1 Install Pure LIOH Venturi Scrubber 2262-SR-001 | 100% | 09-Jun-21 A | 04-Aug-21 A | 200.8 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1203 | 2262-1 Assemble and install 18 safety showers | 20% | 29-Jul-21 A | 2021-10-11 | 179.97 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.8255 | 142.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1211 | 2262-2 - Install Pure LHM Cyrstalliser Noncodensables vent condenser 2262-HX-004 | 0% | 2021-08-30 | 2021-09-02 | 26.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1215 | 2262-2 - Final alignments to Pure LIOH Crystalliser Condensate tank 2262-TK-003 | 0% | 2021-08-10 | 2021-08-11 | 44.97 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1219 | 2262-2 - Final alignments to Pure LIOH Centrate Transfer tank 2262-TK-010 | 0% | 2021-08-12 | 2021-08-13 | 44.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1221 | 2262-2 - Insulation Works to 2262-PV-001 | 0% | 2021-10-12 | 2021-10-27 | 379.51 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.5981 | 202.6303 | 15.2817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1225 | 2262-2 - Insulation Works to 2262-TK-015 | 0% | 2021-10-28 | 2021-10-29 | 55 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.MC.1227 | 2262-2 - Insulation Works to 2262 Ducting Connections | 0% | 2021-10-30 | 2021-11-25 | 630 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 165 | 165 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1304 | 2261-1 Install South Side Centrifuge access platforms (13 modules) | 85% | 25-Jun-21 A | 2021-08-10 | 235.85 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78.6167 | 157.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1314 | 2261-1 Install North Side Centrifuge access platforms (13 modules) | 85% | 29-Jun-21 A | 2021-08-13 | 175.77 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1324 | 2262-1 Install upper columns, tie in beams and bracing to grid A | 100% | 24-Jun-21 A | 20-Jul-21 A | 165.92 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.184 | 132.736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1334 | 2262-1 Install upper columns, tie in beams and bracing to grid B | 100% | 24-Jun-21 A | 21-Jul-21 A | 73.66 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1344 | 2262-1 Install upper columns, tie in beams and bracing to grid C | 100% | 24-Jun-21 A | 22-Jul-21 A | 77.08 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8881 | 71.1919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1354 | 2262-1 Install upper columns, tie in beams and bracing to grid D | 100% | 24-Jun-21 A | 22-Jul-21 A | 68.2 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1364 | 2262-1 Install upper columns, tie in beams and bracing to grid E | 100% | 24-Jun-21 A | 22-Jul-21 A | 71.68 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.3213 | 28.3587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1374 | 2262-1 Install upper columns, tie in beams and bracing to grid F | 0% | 2021-08-13 | 2021-08-16 | 83.34 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6134 | 79.7266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1384 | 2262-1 Install east/west tie in beams and bracing accross all grid lines | 70% | 23-Jun-21 A | 2021-08-28 | 10.53 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.265 | 5.265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1394 | 2262-1 Install level 3 module 130 between grid lines 2 and 3 | 90% | 01-Jul-21 A | 2021-08-31 | 342.48 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1404 | 2262-1 Install level 3 modules 131 - 138 | 70% | 16-Jun-21 A | 2021-09-06 | 174.32 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135.1435 | 39.1765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1424 | 2262-2 - Complete grating installation to level 1 (RL19.780) | 100% | 18-Jun-21 A | 22-Jun-21 A | 39.84 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.28 | 26.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1434 | 2262-2 - Complete grating installation to level 2 (RL25.380) | 100% | 22-Jun-21 A | 25-Jun-21 A | 70.62 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1444 | 2262-2 - Complete grating installation to level 3 (RL 30.780) | 100% | 26-Jun-21 A | 30-Jun-21 A | 154.59 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1454 | 2262-2 - Install second teir level column panels with bracing | 85% | 02-Jul-21 A | 2021-08-18 | 247.88 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192.1126 | 55.7674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1464 | 2262-2 - Install Level 4 modules and stick steel | 100% | 08-Jul-21 A | 22-Jul-21 A | 150.36 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.18 | 75.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1474 | 2262-2 - Install stairways and caged ladders to level 4 | 70% | 21-Jul-21 A | 2021-08-21 | 100.64 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1494 | 2262-2 - Complete level 4 grating | 90% | 21-Jul-21 A | 2021-08-25 | 59.62 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1504 | 2262-2 - Install level 5 modules and stick steel | 75% | 20-Jul-21 A | 2021-09-08 | 207.29 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.916 | 124.374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1514 | 2262-2 - Install stairways and caged ladders to level 5 | 50% | 02-Aug-21 A | 2021-09-13 | 64.5 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.1817 | 2.3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1524 | 2262-2 - Complete level 5 grating | 50% | 20-Jul-21 A | 2021-09-16 | 63.22 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1534 | 2262-2 - Install level 6 modules and stick steel | 75% | 21-Jul-21 A | 2021-09-22 | 217.6 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188.3741 | 29.2259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1544 | 2262-2 - Install stairways and caged ladders to level 6 | 10% | 03-Aug-21 A | 2021-09-27 | 81.3 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.7414 | 13.5586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1554 | 2262-2 - Complete level 6 grating | 50% | 21-Jul-21 A | 2021-09-30 | 37.14 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1564 | 2262-2 - Install level 7 modules and stick steel | 0% | 2021-09-30 | 2021-10-06 | 137.82 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.3716 | 85.4484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1574 | 2262-1 Install level 3 remining tie in beams and bracing | 25% | 01-Jul-21 A | 2021-09-10 | 349.38 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262.1473 | 87.2327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1594 | 2262-1 Install level 4 module 140 between grid lines 2 and 3 | 0% | 2021-09-14 | 2021-09-15 | 367.76 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 367.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1598 | 2262-1 Install level 4 remaining tie in beams and bracing | 0% | 2021-09-16 | 2021-09-22 | 190.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76.38 | 114.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1602 | 2262-1 Install level 4 emaining modules 142 a and b and 143 a,b and c | 0% | 2021-09-22 | 2021-09-24 | 330.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1610 | 2262-1 Installation of pipe supports | 40% | 25-Jun-21 A | 2021-09-28 | 1589.05 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139.25 | 218.425 | 218.425 | 218.425 | 218.425 | 218.425 | 218.425 | 139.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1614 | 2262-1 Tension, testing and quality | 0% | 2021-09-28 | 2021-10-25 | 1070.19 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192.4354 | 273.3645 | 273.3645 | 273.3645 | 57.6612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1615 | 2262-2 - Install stairways and caged ladders to level 7 | 0% | 2021-10-06 | 2021-10-11 | 12.28 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.824 | 2.456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1618 | 2262-1 Install, survey and align crane rails | 0% | 2021-09-21 | 2021-09-28 | 48.32 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.1734 | 16.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1622 | 2262-1 Grouting | 0% | 2021-09-06 | 2021-10-04 | 267.55 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.5889 | 65.9881 | 65.9881 | 65.9881 | 17.9967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1625 | 2262-2 - Complete level 7 grating | 0% | 2021-10-11 | 2021-10-14 | 27.19 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1634 | 2262-2 - Complete horizontal and vertical bracing installation | 0% | 2021-10-14 | 2021-10-18 | 91.03 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.6523 | 33.3777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1638 | 2262-2 - Survey, tension, testing and inspections | 0% | 2021-10-18 | 2021-10-27 | 629.18 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 395.4846 | 233.6954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1642 | 2262-2 - Install interconnecting pipe racks between 2262 MVR and crystallisation building | 90% | 20-Jul-21 A | 2021-11-04 | 265.56 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.8139 | 151.7461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1644 | 2262-2 - Install 2262- 2 Grouting | 0% | 2021-11-04 | 2021-11-13 | 141.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94.369 | 39.5117 | 7.1393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2262.T2.ST.1678 | 2262-1 Miscellaneous Structural Steel | 0% | 2021-08-23 | 2021-10-25 | 2099.91 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683.517 | 57.3964 | 57.3964 | 57.3964 | 57.3964 | 57.3964 | 57.3964 | 57.3964 | 57.3964 | 957.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1000 | 2272-2 Place Dried Reject Hoppers and Support Frames 2272-HP-024 and 025 | 0% | 2021-08-28 | 2021-08-30 | 36 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1010 | 2272-2 Place Dryers to level 1 2272-DR-001-004 (RL17.500) | 0% | 2021-09-10 | 2021-09-13 | 327.59 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 181.9944 | 145.5956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1020 | 2272-2 Place vacuum tank and pump sets to level 1 (RL17.500) 2272-PP-019 and 020 | 0% | 2021-09-13 | 2021-09-13 | 56 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1030 | 2272-2 Mechanical completions to screens including transfer and rejects hoppers 2272-SC-001 and 002 | 0% | 2021-10-20 | 2021-10-28 | 201.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72.1417 | 129.8483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1040 | 2272-2 Place Screw Feeders x 2 2272-FE-007 and 008 | 0% | 2021-09-23 | 2021-09-24 | 124.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1050 | 2272-2 Place and align wet cake transfer screw conveyors 2272-CV-009 and 010 | 0% | 2021-10-12 | 2021-11-06 | 603.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.8429 | 166.4694 | 166.4694 | 166.4694 | 6.759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1070 | 2272-2 Mechanical completions to LIOH Cooler screw feeders and hoppers | 0% | 2021-11-06 | 2021-11-19 | 229.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117.2145 | 112.7755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1080 | 2272-2 Place Dried LIOH screens 2272-SC-001 and 002 onto concrete pedestals | 0% | 2021-08-10 | 2021-08-27 | 447.04 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.4611 | 186.8977 | 235.6812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1090 | 2272-2 Install LIOH Cooler hoppers into support frames 2272-HP-003 and 004 | 0% | 2021-10-11 | 2021-10-12 | 82.68 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1100 | 2272-2 Mechanical completions Dryers 2272-DR-001-004 | 0% | 2021-10-06 | 2021-10-20 | 365.25 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.4357 | 179.1425 | 97.6719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1120 | 2272-2 Place Dried LIOH Transfer Hoppers 2272-HP-010 and 011 onto concrete pedestals | 0% | 2021-08-27 | 2021-08-28 | 112.68 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.4287 | 67.2513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1160 | 2272-1 Mechanical completions between Dust Collector and Dust Collector Hoppers | 0% | 2021-10-07 | 2021-10-11 | 465.27 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.5452 | 387.7248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1180 | 2272-1 Mechanical completions between Magnetic Screens and Screen Feed Hoppers | 0% | 2021-10-18 | 2021-11-04 | 660.08 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223.3539 | 245.1509 | 191.5752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1191 | 2272-1 Mechanical Completions between Vacuum Transfer Receivers and Magnetic Screen Hoppers | 0% | 2021-11-04 | 2021-11-13 | 606.33 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1159 | 585.5198 | 3.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1210 | 2272-2 Place Cooled LIOH Transfer intermediate hoppers onto support frames 2272-HP-012 and 013 | 0% | 2021-08-07 | 2021-08-10 | 210.68 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1211 | 2272-1 Mechanical Completions between Demagnetised large bag Receivers and Packaging Feed Hoppers | 0% | 2021-11-13 | 2021-11-22 | 1343.03 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1163.1788 | 179.8512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1220 | 2272-1 Mechanical completions between Magnetic screens and Intermediate Hoppers | 0% | 2021-10-11 | 2021-10-16 | 278.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132.1916 | 145.8284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1221 | 2272-2 Mechanical completions between dryers 3 and 4 and the Cooled LIOH Intermediate Hoppers | 0% | 2021-10-29 | 2021-11-01 | 74 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1222 | 2272-2 Mechanical installation of LIOH Cooler Vent Scrubbers 2272-SR-001 and 002 | 50% | 28-Jun-21 A | 2021-11-19 | 654.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.2412 | 243.3885 | 243.3885 | 123.9719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.MC.1224 | 2272-1 Atmospheric Controlled Packaging Room | 0% | 2021-12-02 | 2022-02-11 | 295.26 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6627 | 36.1912 | 36.1912 | 0 | 0 | 32.2587 | 36.1912 | 36.1912 | 36.1912 | 36.1912 | 36.1912 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1320 | 2272-2 Place Cooled LIOH Transfer intermediate hoppers support frames x 2 to ground floor | 0% | 2021-08-06 | 2021-08-06 | 7.9 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1330 | 2272-2 Assemble and Place Screen Access Platforms, Modules 101 and 102 | 100% | 15-Jul-21 A | 05-Aug-21 A | 15.97 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1340 | 2272-2 Place 4 x LIOH Dryer support structures, Modules 103,104,105 and 106. | 100% | 15-Jul-21 A | 15-Jul-21 A | 20.65 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1350 | 2272-2 Install level 1 support columns x 15 | 0% | 2021-08-30 | 2021-08-31 | 39.29 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1360 | 2272-2 Install Grating and Handrails to level 1 Module MM110 | 0% | 2021-08-31 | 2021-09-01 | 14.51 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1364 | 2272-2 Install level a floor module (RL 17.500) onto column supports | 0% | 2021-09-01 | 2021-09-03 | 301.32 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1368 | 2272-2 Assemble and install lower level staircase x 2 | 0% | 2021-09-04 | 2021-09-06 | 58.19 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1376 | 2272-2 Install level 2 support columns x 15 | 0% | 2021-09-13 | 2021-09-14 | 37.57 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1380 | 2272-2 Install Grating and Handrails to level 2 module MM 120, 121 and 122 | 0% | 2021-09-14 | 2021-09-16 | 58.68 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1381 | 2272-3 Install portal cover structural steelwork and bracing | 0% | 2021-10-15 | 2021-11-25 | 1641.54 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4393 | 288.1519 | 288.1519 | 288.1519 | 288.1519 | 288.1519 | 199.3411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1384 | 2272-2 Install modules MM 120, 121 and 122 | 0% | 2021-09-16 | 2021-09-17 | 134.58 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1388 | 2272-2 Assemble and install second level stair cases to RL20.100 | 0% | 2021-09-17 | 2021-09-21 | 190.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.3844 | 171.0656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1392 | 2272-2 Install All Vertical Bracing from ground floor to level 2 at RL20.100 | 0% | 2021-09-21 | 2021-09-23 | 22.2 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1396 | 2272-2 Install LIOH Cooler hopper support frames Modules MM 123 and 124 | 0% | 2021-09-24 | 2021-09-27 | 28.31 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9534 | 18.3566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1400 | 2272-2 Complete installation of all pipe supports Including Chemical Anchors | 0% | 2021-09-27 | 2021-10-06 | 9.07 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.442 | 3.628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1401 | 2272-3 Install portal cover wall girts and roof purlins | 0% | 2021-12-03 | 2022-01-03 | 369.71 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1616 | 169.4512 | 169.4512 | 0 | 0 | 24.646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1404 | 2272-2 Tension, testing and quality checks | 0% | 2021-10-06 | 2021-10-11 | 246.95 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235.2963 | 11.6537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1408 | 2272-2 Grouting | 0% | 2021-10-29 | 2021-11-19 | 42.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2575 | 14.2346 | 14.2346 | 11.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1430 | 2272-1 Install five (5) grid line panels for grids A1 - B1 and tie in together with sufficient tie in beams | 60% | 22-Jul-21 A | 2021-08-13 | 150.41 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1461 | 2272-1 Install stick steel to level 1 platform at RL 18.180 | 10% | 03-Aug-21 A | 2021-08-27 | 371.54 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64.6647 | 177.6441 | 129.2312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1465 | 2272-1 Install pipe supports to steelwork underside of level 1 | 0% | 2021-08-28 | 2021-08-31 | 198.93 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1469 | 2272-1 Install handrail and grating to level 1 platform at RL 18.180 | 0% | 2021-09-01 | 2021-09-02 | 174.96 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1485 | 2272-1 Install stick steel to level 2 platform at RL 20.780 | 0% | 2021-09-07 | 2021-09-09 | 198.56 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1489 | 2272-1 Install pipe supports to steelwork underside of level 2 | 0% | 2021-09-10 | 2021-09-13 | 116.88 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.44 | 58.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1493 | 2272-1 Install handrail and grating to level 2 platform at RL 20.780 | 0% | 2021-09-13 | 2021-09-15 | 174.9 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1497 | 2272-1 Assemble and install stair modules from ground to level 2 | 0% | 2021-09-15 | 2021-09-16 | 45.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1501 | 2272-1 Install stick steel to level 3 platform at RL 23.380 | 0% | 2021-09-16 | 2021-09-21 | 304.76 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.6415 | 191.1185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1505 | 2272-1 Install handrail and grating to level 3 platform at RL 23.380 | 0% | 2021-09-22 | 2021-09-24 | 295.84 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1509 | 2272-1 Install pipe supports to level 3 steelwork | 0% | 2021-09-25 | 2021-09-28 | 467.07 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 467.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1513 | 2272-1 Install stair module level 2 - level 3 | 0% | 2021-09-28 | 2021-09-29 | 19.86 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1533 | 2272-1 Install level (RL 26.380) modules MM 110, 111 and 112 and associated tie in steelwork | 0% | 2021-10-06 | 2021-10-08 | 71.23 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1537 | 2272-1 Install level (RL 26.380) grating and handrails | 0% | 2021-10-08 | 2021-10-13 | 148.72 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.2482 | 127.4718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1541 | 2272-1 Install stair module level 3 - level 4 | 0% | 2021-10-13 | 2021-10-14 | 20.71 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1545 | 2272-1 Install fully assembled floor module MM 114 to Northern grid at RL27.180 | 0% | 2021-10-14 | 2021-10-15 | 84.02 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1549 | 2272-1 Complete assemble and installation of modularised platforms MM 120 and 121 | 0% | 2021-10-15 | 2021-10-18 | 72.01 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.0025 | 54.0075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1553 | 2272-1 Complete assemble and installation of remaining stairways | 0% | 2021-10-19 | 2021-10-20 | 14.98 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1565 | 2272-1 Install Level five steel module complete with handrail and grating | 0% | 2021-10-23 | 2021-10-26 | 112.33 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1573 | 2272-1 Tension, testing and quality | 0% | 2021-10-22 | 2021-10-28 | 449.7 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89.94 | 359.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1577 | 2272-1 Survey and grouting to steel structure only | 0% | 2021-10-23 | 2021-10-28 | 112.42 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1581 | 2272-3 Install portal cover wall and roof sheeting | 0% | 2022-01-03 | 2022-01-24 | 3549.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2916.7907 | 38.5382 | 38.5382 | 555.5829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1593 | 2272-3 Grouting | 0% | 2022-02-04 | 2022-02-10 | 402.37 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.6055 | 380.7645 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1598 | 2272-5 - Miscellaneous Pipe Supports | 0% | 2021-09-28 | 2021-10-20 | 221.09 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145.4919 | 28.4928 | 28.4928 | 18.6125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1606 | 2272-4 - Remove northern wall sheeting and purlins | 0% | 2021-08-09 | 2021-08-11 | 16.05 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1618 | 2272-4 - Install Structure | 0% | 2021-08-15 | 2021-08-15 | 18.36 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1622 | 2272-4 - Install mezzanine floor and ladder | 0% | 2021-08-16 | 2021-08-17 | 176.21 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1626 | 2272-4 - Install large bag CER air conditioner 2272-XM-018 | 0% | 2021-08-27 | 2021-09-30 | 1350 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.127 | 276.8269 | 276.8269 | 276.8269 | 276.8269 | 235.5654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1672 | 2272-1 Install stick steel to level 4 platform at RL 25.380 | 0% | 2021-10-14 | 2021-10-16 | 89.59 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.1759 | 22.4141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1674 | 2272-1 Install stick steel to level 5 platform at RL 30.780 | 0% | 2021-10-21 | 2021-10-22 | 52.88 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.2272.T2.ST.1676 | 2272-3 Supports | 0% | 2022-01-03 | 2022-01-07 | 316.29 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.IN.1665 | 4242-SP1-500 Install Node | 0% | 30-Aug-21* | 2021-08-31 | 67.18 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1637 | 4242-TR-100 Install Pipe Supports | 100% | 11-Jun-21 A | 14-Jun-21 A | 39.8 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.11 | 17.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1641 | 4242-SP1-200 Install Pipe Supports | 100% | 01-Jun-21 A | 17-Jun-21 A | 90 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84.5619 | 5.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1645 | 4242-SP1-300 Install Pipe Supports | 100% | 07-Jun-21 A | 17-Jun-21 A | 90.16 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1649 | 4242-SP1-400 Install Pipe Supports | 22% | 22-Jun-21 A | 2021-09-06 | 54.69 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.345 | 27.345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1650 | 4242-TR-300 Install Pipe Supports | 100% | 16-Jun-21 A | 17-Jun-21 A | 47.32 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.4618 | 37.8582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1653 | 4242-SP1-500 Install Pipe Supports | 0% | 2021-09-06 | 2021-09-08 | 51.29 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1657 | 4242-SP1-700 Install Pipe Supports | 100% | 03-Jun-21 A | 11-Jun-21 A | 23.54 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1658 | 4242-TR-400 Install Pipe Supports | 0% | 2021-09-06 | 2021-09-11 | 79.4 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71.46 | 7.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1661 | 4242-SP1-800 Install Pipe Supports | 100% | 07-Jun-21 A | 16-Jun-21 A | 60.45 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.PS.1663 | 4242-SP1-600 Install Pipe Supports | 0% | 2021-09-08 | 2021-09-10 | 52.6 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.ST.1629 | 4242-TR-400 Installation | 0% | 2021-09-01 | 2021-09-02 | 52.13 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.ST.1633 | 4242-TR-500 Installation | 0% | 2021-09-03 | 2021-09-06 | 47.99 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.995 | 23.995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.WW.1645 | 4242-SP1-200 Install Walkway | 100% | 04-Jun-21 A | 07-Jun-21 A | 8.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.WW.1653 | 4242-SP1-300 Install Walkway | 100% | 07-Jun-21 A | 10-Jun-21 A | 8.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6745 | 7.1355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.WW.1661 | 4242-SP1-400 Install Walkway | 0% | 2021-09-06 | 2021-09-07 | 8.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.WW.1665 | 4242-SP1-500 Install Walkway | 0% | 2021-09-08 | 2021-09-09 | 8.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.WW.1669 | 4242-SP1-700 Install Walkway | 100% | 04-Jun-21 A | 14-Jun-21 A | 8.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN.4242.T2.WW.1673 | 4242-SP1-800 Install Walkway | 100% | 08-Jun-21 A | 10-Jun-21 A | 8.81 | Budgeted Labor Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## lookup
Activity ID | Activity Name | Area | Sub Area | Discipline
2252-1.T2.PI.1095 | 2252-1 Tank Trim | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-AIN.1000 | 2252-1 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-AIN.1032 | 2252-1 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-AIN.1055 | 2252-1 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-AIN.1056 | 2252-1 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-AIN.1061 | 2252-1 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-GCD.1003 | 2252-1 Install-Piping & It's Components [CS-GCD] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-GCD.1045 | 2252-1 Install-Piping & It's Components [CS-GCD] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-GSL.1006 | 2252-1 Install-Piping & It's Components [CS-GSL] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-GSL.1027 | 2252-1 Install-Piping & It's Components [CS-GSL] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-GVE.1028 | 2252-1 Install-Piping & It's Components [CS-GVE] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-GVE.1041 | 2252-1 Install-Piping & It's Components [CS-GVE] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-GVE.1042 | 2252-1 Install-Piping & It's Components [CS-GVE] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-LPB.1022 | 2252-1 Install-Piping & It's Components [CS-LPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-LPB.1029 | 2252-1 Install-Piping & It's Components [CS-LPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-LPB.1046 | 2252-1 Install-Piping & It's Components [CS-LPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-LPB.1047 | 2252-1 Install-Piping & It's Components [CS-LPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-LPN.1047 | 2252-1 Install-Piping & It's Components [CS-LPN] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-LSH.1048 | 2252-1 Install-Piping & It's Components [CS-LSH] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-LSH.1049 | 2252-1 Install-Piping & It's Components [FRP-LSD] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-SPB.1042 | 2252-1 Install-Piping & It's Components [CS-SPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-SPB.1043 | 2252-1 Install-Piping & It's Components [FRP-GVE] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-WFI.1057 | 2252-1 Install-Piping & It's Components [CS-WFI] | 2252 | 2252-1 | Pipe
2252-1T2.PI.CS-WFI.1058 | 2252-1 Install-Piping & It's Components [CS-WFI] | 2252 | 2252-1 | Pipe
2252-1T2.PI.FRP-LPA.1012 | 2252-1 Install-Piping & It's Components [FRP-LPA] | 2252 | 2252-1 | Pipe
2252-1T2.PI.FRP-LPA.1024 | 2252-1 Install-Piping & It's Components [FRP-LPA] | 2252 | 2252-1 | Pipe
2252-1T2.PI.HDPE-WCW.1015 | 2252-1 Install-Piping & It's Components [HDPE-WCW] | 2252 | 2252-1 | Pipe
2252-1T2.PI.HDPE-WFI.1016 | 2252-1 Install-Piping & It's Components [HDPE-WFI] | 2252 | 2252-1 | Pipe
2252-1T2.PI.HDPE-WPO.1058 | 2252-1 Install-Piping & It's Components [HDPE-WPO] | 2252 | 2252-1 | Pipe
2252-1T2.PI.HDPE-WRO.1059 | 2252-1 Install-Piping & It's Components [HDPE-WRO] | 2252 | 2252-1 | Pipe
2252-1T2.PI.HDPE-WRO.1060 | 2252-1 Install-Piping & It's Components [HDPE-WRO] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-GVE.1018 | 2252-1 Install-Piping & It's Components [SS-GVE] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-GVE.1030 | 2252-1 Install-Piping & It's Components [SS-GVE] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-GVE.1036 | 2252-1 Install-Piping & It's Components [SS-GVE] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-GVE.1044 | 2252-1 Install-Piping & It's Components [SS-GVE] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-LPB.1019 | 2252-1 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-LPB.1025 | 2252-1 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-LPB.1051 | 2252-1 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-SPB.1031 | 2252-1 Install-Piping & It's Components [SS-SPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-SPB.1034 | 2252-1 Install-Piping & It's Components [SS-SPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-SPB.1037 | 2252-1 Install-Piping & It's Components [SS-SPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-SPB.1039 | 2252-1 Install-Piping & It's Components [SS-SPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-SPB.1052 | 2252-1 Install-Piping & It's Components [SS-SPB] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WCW.1020 | 2252-1 Install-Piping & It's Components [SS-WCW] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WPO.1060 | 2252-1 Install-Piping & It's Components [SS-WPO] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WRO.1053 | 2252-1 Install-Piping & It's Components [SS-WRO] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WRO.1059 | 2252-1 Install-Piping & It's Components [SS-WRO] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WRO.1060 | 2252-1 Install-Piping & It's Components [SS-WRO] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WSC.1021 | 2252-1 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WSC.1026 | 2252-1 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WSC.1038 | 2252-1 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WSC.1040 | 2252-1 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-1 | Pipe
2252-1T2.PI.SS-WSC.1054 | 2252-1 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-1 | Pipe
2252-2T2.PI.CS-AIN.1055 | 2252-2 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-2 | Pipe
2252-2T2.PI.CS-AIN.1075 | 2252-2 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-2 | Pipe
2252-2T2.PI.CS-AIN.1083 | 2252-2 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-2 | Pipe
2252-2T2.PI.CS-SPB.1047 | 2252-2 Install-Piping & It's Components [CS-SPB] | 2252 | 2252-2 | Pipe
2252-2T2.PI.CS-SPB.1061 | 2252-2 Install-Piping & It's Components [CS-SPB] | 2252 | 2252-2 | Pipe
2252-2T2.PI.CS-SPB.1069 | 2252-2 Install-Piping & It's Components [CS-SPB] | 2252 | 2252-2 | Pipe
2252-2T2.PI.CS-WFI.1077 | 2252-2 Install-Piping & It's Components [CS-WFI] | 2252 | 2252-2 | Pipe
2252-2T2.PI.CS-WFI.1081 | 2252-2 Install-Piping & It's Components [CS-WFI] | 2252 | 2252-2 | Pipe
2252-2T2.PI.HDPE-WRO.10 | 2252-2 Install-Piping & It's Components [HDPE-WRO] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-LPB.1049 | 2252-2 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-LPB.1051 | 2252-2 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-LPB.1057 | 2252-2 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-LPB.1063 | 2252-2 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-LPB.1067 | 2252-2 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-LPB.1071 | 2252-2 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-WPO.1085 | 2252-2 Install-Piping & It's Components [SS-WPO] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-WRO.1079 | 2252-2 Install-Piping & It's Components [SS-WRO] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-WSC.1053 | 2252-2 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-WSC.1059 | 2252-2 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-WSC.1065 | 2252-2 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-2 | Pipe
2252-2T2.PI.SS-WSC.1073 | 2252-2 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-2 | Pipe
2252-3 T2.Flush. 9176 | 2252-3 SPB System Flush | 2252 | 2252-3 | Pipe
2252-3 T2.Flush. 9178 | 2252-3 LPB System Flush | 2252 | 2252-3 | Pipe
2252-3 T2.Flush. 9180 | 2252-3 WSC System Flush | 2252 | 2252-3 | Pipe
2252-3 T2.HYDRO. 9168 | 2252-3 SPB System Hydrotest | 2252 | 2252-3 | Pipe
2252-3 T2.HYDRO. 9170 | 2252-3 LPB System Hydrotest | 2252 | 2252-3 | Pipe
2252-3 T2.HYDRO. 9172 | 2252-3 GSL System Hydrotest | 2252 | 2252-3 | Pipe
2252-3 T2.Insul. 9182 | 2252-3 GVE System Insulation | 2252 | 2252-3 | Pipe
2252-3 T2.Insul. 9184 | 2252-3 SPB System Insulation | 2252 | 2252-3 | Pipe
2252-3 T2.Insul. 9186 | 2252-3 LPB System Insulation | 2252 | 2252-3 | Pipe
2252-3 T2.Insul. 9188 | 2252-3 WSC System Insulation | 2252 | 2252-3 | Pipe
2252-3 T2.Insul. 9190 | 2252-3 GSL System Insulation | 2252 | 2252-3 | Pipe
2252-3 T2.PI.CS-AIN. 9160 | 2252-3 RL2 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.CS-AIN. 9688 | 2252-3 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.CS-GSL. 9153 | 2252-3 RL1 Install-Piping & It's Components [CS-GSL] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.CS-GSL. 9164 | 2252-3 RL2 Install-Piping & It's Components [CS-GSL] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.CS-LPB. 9372 | 2252-3 RL5 Install-Piping & It's Components [CS-LPB] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.CS-LPB. 9374 | 2252-3 RL5 Install-Piping & It's Components [CS-LPB] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.CS-WFI. 9692 | 2252-3 Install-Piping & It's Components [CS-WFI] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.HDPE-WRO. 94 | 2252-3 Install-Piping & It's Components [HDPE-WRO] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.PS .9161 | 2252-3 RL1 Install Pipe Supports | 2252 | 2252-3 | Struct
2252-3 T2.PI.PS .9163 | 2252-3 RL2 Install Pipe Supports | 2252 | 2252-3 | Struct
2252-3 T2.PI.PS .9165 | 2252-3 RL3 Install Pipe Supports | 2252 | 2252-3 | Struct
2252-3 T2.PI.PS .9167 | 2252-3 RL4 Install Pipe Supports | 2252 | 2252-3 | Struct
2252-3 T2.PI.PS .9169 | 2252-3 RL5 Install Pipe Supports | 2252 | 2252-3 | Struct
2252-3 T2.PI.PS .9171 | 2252-3 RL6 Install Pipe Supports | 2252 | 2252-3 | Struct
2252-3 T2.PI.PS .9173 | 2252-3 RL7 Install Pipe Supports | 2252 | 2252-3 | Struct
2252-3 T2.PI.PS .9175 | 2252-3 RL8 Install Pipe Supports | 2252 | 2252-3 | Struct
2252-3 T2.PI.SS-GSL. 9162 | 2252-3 RL2 Install-Piping & It's Components [SS-GSL] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-GSL. 9164 | 2252-3 RL3 Install-Piping & It's Components [SS-GSL] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-GSL. 9366 | 2252-3 RL7 Install-Piping & It's Components [SS-GSL] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-GVE. 9154 | 2252-3 RL1 Install-Piping & It's Components [SS-GVE] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-GVE. 9164 | 2252-3 RL5 Install-Piping & It's Components [SS-GVE] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-GVE. 9165 | 2252-3 RL3 Install-Piping & It's Components [SS-GVE] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-GVE. 9166 | 2252-3 RL2 Install-Piping & It's Components [SS-GVE] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-GVE. 9368 | 2252-3 RL7 Install-Piping & It's Components [SS-GVE] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-LPB. 9167 | 2252-3 RL3 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-LPB. 9170 | 2252-3 RL2 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-LPB. 9270 | 2252-3 RL4 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-LPB. 9271 | 2252-3 RL4 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-SPB. 9157 | 2252-3 RL1 Install-Piping & It's Components [SS-SPB] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WCW. 9158 | 2252-3 RL1 Install-Piping & It's Components [SS-WCW] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WCW. 9172 | 2252-3 RL3 Install-Piping & It's Components [SS-WCW] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WCW. 9174 | 2252-3 RL2 Install-Piping & It's Components [SS-WCW] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WCW. 9374 | 2252-3 RL5 Install-Piping & It's Components [SS-WCW] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WGS. 9159 | 2252-3 RL1 Install-Piping & It's Components [SS-WGS] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WPO. 9694 | 2252-3 Install-Piping & It's Components [SS-WPO] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WPR. 9176 | 2252-3 RL3 Install-Piping & It's Components [SS-WPR] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WRO. 9160 | 2252-3 RL1 Install-Piping & It's Components [SS-WRO] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WRO. 9690 | 2252-3 Install-Piping & It's Components [SS-WRO] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WRO. 9691 | 2252-3 RL1 Install-Piping & It's Components [SS-WRO] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WSC. 9162 | 2252-3 RL1 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WSC. 9178 | 2252-3 RL2 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WSC. 9180 | 2252-3 RL3 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WSC. 9276 | 2252-3 RL4 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WSC. 9368 | 2252-3 RL8 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WSC. 9370 | 2252-3 RL7 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WSC. 9376 | 2252-3 RL5 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-3 | Pipe
2252-3 T2.PI.SS-WSC. 9378 | 2252-3 RL6 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-3 | Pipe
2252-4T2.PI.CS-AIN.1100 | 2252-4 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-4 | Pipe
2252-4T2.PI.CS-LPB.1081 | 2252-4 Install-Piping & It's Components [CS-LPB] | 2252 | 2252-4 | Pipe
2252-4T2.PI.CS-LPB.1085 | 2252-4 Install-Piping & It's Components [CS-LPB] | 2252 | 2252-4 | Pipe
2252-4T2.PI.CS-LPB.1087 | 2252-4 Install-Piping & It's Components [CS-LPB] | 2252 | 2252-4 | Pipe
2252-4T2.PI.HDPE-WRO.89 | 2252-4 Install-Piping & It's Components [HDPE-WRO] | 2252 | 2252-4 | Pipe
2252-4T2.PI.HDPE-WRO.96 | 2252-4 Install-Piping & It's Components [HDPE-WRO] | 2252 | 2252-4 | Pipe
2252-4T2.PI.SS-LPB.1075 | 2252-4 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-4 | Pipe
2252-4T2.PI.SS-LPB.1092 | 2252-4 Install-Piping & It's Components [SS-LPB] | 2252 | 2252-4 | Pipe
2252-4T2.PI.SS-SPB.1077 | 2252-4 Install-Piping & It's Components [SS-SPB] | 2252 | 2252-4 | Pipe
2252-4T2.PI.SS-WPO.1102 | 2252-4 Install-Piping & It's Components [SS-WPO] | 2252 | 2252-4 | Pipe
2252-4T2.PI.SS-WRO.1098 | 2252-4 Install-Piping & It's Components [SS-WRO] | 2252 | 2252-4 | Pipe
2252-4T2.PI.SS-WSC.1079 | 2252-4 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-4 | Pipe
2252-4T2.PI.SS-WSC.1083 | 2252-4 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-4 | Pipe
2252-4T2.PI.SS-WSC.1094 | 2252-4 Install-Piping & It's Components [SS-WSC] | 2252 | 2252-4 | Pipe
2252-5T2.PI.CS-AIN.1094 | 2252-5 Install-Piping & It's Components [CS-AIN] | 2252 | 2252-5 | Pipe
2252-5T2.PI.SS-WPO.1098 | 2252-5 Install-Piping & It's Components [SS-WPO] | 2252 | 2252-5 | Pipe
2252-5T2.PI.SS-WRO.1096 | 2252-5 Install-Piping & It's Components [SS-WRO] | 2252 | 2252-5 | Pipe
2262-1T2.PI.9277 | 2262-1 Tank Trim | 2262 | 2262-1 | Pipe
2262-1T2.PI.CS-AIN.9203 | 2262-1 Install-Piping & It's Components (CS-AIN) | 2262 | 2262-1 | Pipe
2262-1T2.PI.CS-AIN.9207 | 2262-1 Install-Piping & It's Components (SS-SPB) | 2262 | 2262-1 | Pipe
2262-1T2.PI.CS-AIN.9279 | 2262-1 Install-Piping & It's Components (CS-AIN) | 2262 | 2262-1 | Pipe
2262-1T2.PI.CS-AIN.9315 | 2262-1 Install-Piping & It's Components (CS-AIN) | 2262 | 2262-1 | Pipe
2262-1T2.PI.CS-LPB.9235 | 2262-1 Install-Piping & It's Components (CS-LPB) | 2262 | 2262-1 | Pipe
2262-1T2.PI.CS-WFI.9283 | 2262-1 Install-Piping & It's Components (CS-WFI) | 2262 | 2262-1 | Pipe
2262-1T2.PI.CS-WFI.9299 | 2262-1 Install-Piping & It's Components (CS-WFI) | 2262 | 2262-1 | Pipe
2262-1T2.PI.HDPE-WCW.9239 | 2262-1 Install-Piping & It's Components (HDPE-WCW) | 2262 | 2262-1 | Pipe
2262-1T2.PI.HDPE-WCW.9259 | 2262-1 Install-Piping & It's Components (HDPE-WCW) | 2262 | 2262-1 | Pipe
2262-1T2.PI.HDPE-WRO.9291 | 2262-1 Install-Piping & It's Components (HDPE-WRO) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-GVE.9195 | 2262-1 Install-Piping & It's Components (SS-GVE) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-GVE.9215 | 2262-1 Install-Piping & It's Components (SS-GVE) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-GVE.9243 | 2262-1 Install-Piping & It's Components (SS-GVE) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-LPB.9199 | 2262-1 Install-Piping & It's Components (SS-LPB) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-LPB.9251 | 2262-1 Install-Piping & It's Components (SS-LPB) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-LPB.9267 | 2262-1 Install-Piping & It's Components (SS-LPB) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-SPB.9207 | 2262-1 Install-Piping & It's Components (SS-SPB) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-SPB.9219 | 2262-1 Install-Piping & It's Components (SS-SPB) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-SPB.9227 | 2262-1 Install-Piping & It's Components (SS-SPB) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-SPB.9271 | 2262-1 Install-Piping & It's Components (SS-SPB) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WPO.9303 | 2262-1 Install-Piping & It's Components (SS-WPO) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WRO.9295 | 2262-1 Install-Piping & It's Components (SS-WRO) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WRO.9311 | 2262-1 Install-Piping & It's Components (SS-WRO) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WRO.9312 | 2262-1 Install-Piping & It's Components (SS-WRO) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WSC.9211 | 2262-1 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WSC.9223 | 2262-1 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WSC.9231 | 2262-1 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WSC.9247 | 2262-1 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WSC.9255 | 2262-1 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WSC.9263 | 2262-1 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-1 | Pipe
2262-1T2.PI.SS-WSC.9275 | 2262-1 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-1 | Pipe
2262-2 T2.Flush. 9181 | 2262-2 GSL System Flush | 2262 | 2262-2 | Pipe
2262-2 T2.Flush. 9182 | 2262-2 SPB System Flush | 2262 | 2262-2 | Pipe
2262-2 T2.Flush. 9183 | 2262-2 LPB System Flush | 2262 | 2262-2 | Pipe
2262-2 T2.Flush. 9184 | 2262-2 WSC System Flush | 2262 | 2262-2 | Pipe
2262-2 T2.HYDRO. 9173 | 2262-2 SPB System Hydrotest | 2262 | 2262-2 | Pipe
2262-2 T2.HYDRO. 9174 | 2262-2 LPB System Hydrotest | 2262 | 2262-2 | Pipe
2262-2 T2.HYDRO. 9175 | 2262-2 GSL System Hydrotest | 2262 | 2262-2 | Pipe
2262-2 T2.Insul. 9191 | 2262-2 GVE System Insulation | 2262 | 2262-2 | Pipe
2262-2 T2.Insul. 9192 | 2262-2 SPB System Insulation | 2262 | 2262-2 | Pipe
2262-2 T2.Insul. 9193 | 2262-2 LPB System Insulation | 2262 | 2262-2 | Pipe
2262-2 T2.Insul. 9194 | 2262-2 WSC System Insulation | 2262 | 2262-2 | Pipe
2262-2 T2.Insul. 9195 | 2262-2 GSL System Insulation | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-GSL. 9367 | 2262-2 RL1 Install-Piping & It's Components [SS-GSL] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-GSL. 9368 | 2262-2 RL2 Install-Piping & It's Components [SS-GSL] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-GSL. 9369 | 2262-2 RL3 Install-Piping & It's Components [SS-GSL] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-GSL. 9372 | 2262-2 RL8 Install-Piping & It's Components [SS-GSL] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-GVE. 9369 | 2262-2 RL1 Install-Piping & It's Components [SS-GVE] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-GVE. 9371 | 2262-2 RL3 Install-Piping & It's Components [SS-GVE] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-GVE. 9372 | 2262-2 RL4 Install-Piping & It's Components [SS-GVE] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-GVE. 9373 | 2262-2 RL5 Install-Piping & It's Components [SS-GVE] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-GVE. 9697 | 2262-2 RL6 Install-Piping & It's Components [SS-GVE] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-LPB. 9471 | 2262-2 RL1 Install-Piping & It's Components [SS-LPB] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-LPB. 9473 | 2262-2 RL3 Install-Piping & It's Components [SS-LPB] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-LPB. 9474 | 2262-2 RL4 Install-Piping & It's Components [SS-LPB] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-LPB. 9475 | 2262-2 RL5 Install-Piping & It's Components [SS-LPB] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-SPB. 9173 | 2262-2 RL1 Install-Piping & It's Components [SS-SPB] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-SPB. 9390 | 2262-2 RL4 Install-Piping & It's Components [SS-SPB] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-SPB. 9391 | 2262-2 RL5 Install-Piping & It's Components [SS-SPB] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WCW. 9375 | 2262-2 RL1 Install-Piping & It's Components [SS-WCW] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WCW. 9376 | 2262-2 RL2 Install-Piping & It's Components [SS-WCW] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WCW. 9377 | 2262-2 RL3 Install-Piping & It's Components [SS-WCW] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WCW. 9378 | 2262-2 RL4 Install-Piping & It's Components [SS-WCW] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WGS. 9160 | 2262-2 RL1 Install-Piping & It's Components [SS-WGS] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WGS. 9705 | 2262-2 RL3 Install-Piping & It's Components [SS-WGS] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WGS. 9707 | 2262-2 RL4 Install-Piping & It's Components [SS-WGS] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WPR. 9177 | 2262-2 RL3 Install-Piping & It's Components [SS-WPR] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WSC. 9379 | 2262-2 RL1 Install-Piping & It's Components [SS-WSC] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WSC. 9380 | 2262-2 RL2 Install-Piping & It's Components [SS-WSC] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WSC. 9381 | 2262-2 RL3 Install-Piping & It's Components [SS-WSC] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WSC. 9382 | 2262-2 RL4 Install-Piping & It's Components [SS-WSC] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WSC. 9384 | 2262-2 RL6 Install-Piping & It's Components [SS-WSC] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WSC. 9385 | 2262-2 RL7 Install-Piping & It's Components [SS-WSC] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WSC. 9386 | 2262-2 RL8 Install-Piping & It's Components [SS-WSC] | 2262 | 2262-2 | Pipe
2262-2 T2.PI.SS-WWW. 9709 | 2262-2 RL3 Install-Piping & It's Components [SS-WWW] | 2262 | 2262-2 | Pipe
2262-2.T2.PI.CS-GSL.9203 | 2262-2 Install-Piping & It's Components (CS-GSL) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.CS-GVE.9190 | 2262-2 Install-Piping & It's Components (CS-GVE) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.CS-LPB.9189 | 2262-2 Install-Piping & It's Components (CS-LPB) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.CS-LPN.9179 | 2262-2 Install-Piping & It's Components (CS-LPN) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.CS-WFI.9646 | 2262-2 Install-Piping & It's Components (CS-WFI) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.HDPE-WCW.80 | 2262-2 Install-Piping & It's Components (HDPE-WCW) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.HDPE-WRO.92 | 2262-2 Install-Piping & It's Components (HDPE-WRO) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.SS-LPB.9181 | 2262-2 Install-Piping & It's Components (SS-LPB) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.SS-SPB.9223 | 2262-2 Install-Piping & It's Components (SS-SPB) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.SS-WPO.9650 | 2262-2 Install-Piping & It's Components (SS-WPO) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.SS-WRO.9654 | 2262-2 Install-Piping & It's Components (SS-WRO) | 2262 | 2262-2 | Pipe
2262-2.T2.PI.SS-WSC.9239 | 2262-2 Install-Piping & It's Components (CS-AIN) | 2262 | 2262-2 | Pipe
2262-3.T2.PI.1435 | 2262-3 Tank Trim | 2262 | 2262-3 | Pipe
2262-3.T2.PI.CS-GSL.1394 | 2262-3 Install-Piping & It's Components (CS-GSL) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.CS-GSL.1426 | 2262-3 Install-Piping & It's Components (CS-GSL) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.CS-GSL.1438 | 2262-3 Install-Piping & It's Components (CS-GSL) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.CS-LPB.1442 | 2262-3 Install-Piping & It's Components (CS-LPB) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.CS-LPN.1446 | 2262-3 Install-Piping & It's Components (CS-LPN) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.CS-WRA.1439 | 2262-3 Install-Piping & It's Components (CS-WRA) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.HDPE-WR.1440 | 2262-3 Install-Piping & It's Components (HDPE-WRO) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.PS.1434 | 2262-3 Install Pipe Supports and Miscellaneous Steel | 2262 | 2262-3 | Struct
2262-3.T2.PI.SS-LPB.1430 | 2262-3 Install-Piping & It's Components (SS-LPB) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.SS-SPB.1454 | 2262-3 Install-Piping & It's Components (SS-SPB) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.SS-SPB.1458 | 2262-3 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.SS-WSC.1422 | 2262-3 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-3 | Pipe
2262-3.T2.PI.SS-WSC.1434 | 2262-3 Install-Piping & It's Components (SS-WSC) | 2262 | 2262-3 | Pipe
2272-1.T2.PI.1224 | 2272-1 Run and align 2272-80-PLH-2002-S2l1 LINE FROM HP 1012 (Drying area) to HP 018 (Packaging area) | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1225 | 2272-1 Run and align 2272-80-PLH-2004-S2l1 LINE FROM HP 1013 (Drying area) to HP 021 (Packaging area) | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1228 | 2272-1 Run and align screw feeder (FE 011 and 012) interconnection lines to Manetic screens 003 and 004 | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1229 | 2272-1 Run and align screw feeder (FE 013 and 014) interconnection lines to Manetic screens 001 and 002 | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1230 | 2272-1 Run and align Magnetic screen discharge piping from MS 003 and 004 - Intermediate hoppers HP 016 and 017 | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1232 | 2272-1 Run and align piping from Hoppers 016 and 017 - Hopper 23 including diversion line | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1233 | 2272-1 Run and align piping from Hoppers 014 and 015 - Hopper 22 including diversion line | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1234 | 2272-1 Run and align Vacuum pump (PP 024 - 027) to Transfer Reciever Vessel Piping | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1235 | 2272-1 Run and align Vacuum pump (PP 024 - 027) vents | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1236 | 2272-1 Site run and fit all instrucmnt air pipe, manifolds and tubing | 2272 | 2272-1 | Pipe
2272-1.T2.PI.1238 | 2272-1 Assemble and Install 11 Safety Showers | 2272 | 2272-1 | Pipe
2272-2.T2.HY.1164 | 2272-2 Hydrotesting | 2272 | 2272-2 | Pipe
2272-2.T2.IN.1168 | 2272-2 Piping insulation | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1140 | 2272-2 Run and align off gas ducting from Dryers 001 and 002 back to Vent Scrubber 001 | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1144 | 2272-2 Run and align Steam Condensate Lines from Dryer Hot Water Tank 2272-TK-001 to Dryers 1 and 2 | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1146 | 2272-2 Run and align Steam Condensate Lines from Dryers 1 and 2 - Dryer Hot Water Tank 2272-TK-001 | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1148 | 2272-2 Run and align Steam Condensate Lines from 2260-PP-002 to Dryer Hot Water Tank 2272-TK-001 | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1150 | 2272-2 Cooling water supply and return lines for Dryer 1 | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1152 | 2272-2 Cooling water supply and return lines for Dryer 2 | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1154 | 2272-2 Cooling water supply and return lines for Dryer 3 | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1156 | 2272-2 Cooling water supply and return lines for Dryer 4 | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1158 | 2272-2 Run and align sump pump discharge line back to 2262-SU-001 (Area 2262 Sump) | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1162 | 2272-2 Site run and install Instrument air piping | 2272 | 2272-2 | Pipe
2272-2.T2.PI.1166 | 2272-2 Installation and chem anchoring of ground pipe supports | 2272 | 2272-2 | Struct
4242.T2.PI.CS-AIN.1663 | 4242-SP1-100 Install-Piping & It's Components (CS-AIN) | 4242 | 4242 | Pipe
4242.T2.PI.CS-AIN.1681 | 4242-SP1-200 Install-Piping & It's Components (CS-AIN) | 4242 | 4242 | Pipe
4242.T2.PI.CS-AIN.1701 | 4242-SP1-300 Install-Piping & It's Components (CS-AIN) | 4242 | 4242 | Pipe
4242.T2.PI.CS-AIN.1722 | 4242-SP1-400 Install-Piping & It's Components (CS-AIN) | 4242 | 4242 | Pipe
4242.T2.PI.CS-AIN.1746 | 4242-SP1-500 Install-Piping & It's Components (CS-AIN) | 4242 | 4242 | Pipe
4242.T2.PI.CS-AIN.1774 | 4242-SP1-600 Install-Piping & It's Components (CS-AIN) | 4242 | 4242 | Pipe
4242.T2.PI.CS-AIN.1802 | 4242-SP1-700 Install-Piping & It's Components (CS-AIN) | 4242 | 4242 | Pipe
4242.T2.PI.CS-AIN.1820 | 4242-SP1-800 Install-Piping & It's Components (CS-AIN) | 4242 | 4242 | Pipe
4242.T2.PI.CS-AIN.1842 | 4242-SP1-900 Install-Piping & It's Components (CS-AIN) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GCD.1665 | 4242-SP1-100 Install-Piping & It's Components (CS-GCD) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GCD.1683 | 4242-SP1-200 Install-Piping & It's Components (CS-GCD) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GCD.1703 | 4242-SP1-300 Install-Piping & It's Components (CS-GCD) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GSL.1705 | 4242-SP1-300 Install-Piping & It's Components (CS-GSL) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GSL.1724 | 4242-SP1-400 Install-Piping & It's Components (CS-GSL) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GSL.1748 | 4242-SP1-500 Install-Piping & It's Components (CS-GSL) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GSL.1776 | 4242-SP1-600 Install-Piping & It's Components (CS-GSL) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GSL.1856 | 4242-TR-100 Install-Piping & It's Components (CS-GSL) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GSL.1858 | 4242-TR-400 Install-Piping & It's Components (CS-GSL) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GSL.1860 | 4242-TR-500 Install-Piping & It's Components (CS-GSL) | 4242 | 4242 | Pipe
4242.T2.PI.CS-GSL.1862 | 4242-TR-600 Install-Piping & It's Components (CS-GSL) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LCC.1750 | 4242-SP1-500 Install-Piping & It's Components (CS-LCC) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LCC.1778 | 4242-SP1-600 Install-Piping & It's Components (CS-LCC) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LPB.1685 | 4242-SP1-200 Install-Piping & It's Components (CS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LPB.1707 | 4242-SP1-300 Install-Piping & It's Components (CS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LPB.1726 | 4242-SP1-400 Install-Piping & It's Components (CS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LPB.1752 | 4242-SP1-500 Install-Piping & It's Components (CS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LPB.1780 | 4242-SP1-600 Install-Piping & It's Components (CS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LPB.1804 | 4242-SP1-700 Install-Piping & It's Components (CS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LPB.1822 | 4242-SP1-800 Install-Piping & It's Components (CS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LSH.1709 | 4242-SP1-300 Install-Piping & It's Components (CS-LSH) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LSH.1728 | 4242-SP1-400 Install-Piping & It's Components (CS-LSH) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LSH.1754 | 4242-SP1-500 Install-Piping & It's Components (CS-LSH) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LSH.1782 | 4242-SP1-600 Install-Piping & It's Components (CS-LSH) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LSH.1806 | 4242-SP1-700 Install-Piping & It's Components (CS-LSH) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LSH.1824 | 4242-SP1-800 Install-Piping & It's Components (CS-LSH) | 4242 | 4242 | Pipe
4242.T2.PI.CS-LSH.1844 | 4242-SP1-900 Install-Piping & It's Components (CS-LSH) | 4242 | 4242 | Pipe
4242.T2.PI.CS-SPB.1711 | 4242-SP1-300 Install-Piping & It's Components (CS-SPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-SPB.1730 | 4242-SP1-400 Install-Piping & It's Components (CS-SPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-SPB.1756 | 4242-SP1-500 Install-Piping & It's Components (CS-SPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-SPB.1784 | 4242-SP1-600 Install-Piping & It's Components (CS-SPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-SPB.1808 | 4242-SP1-700 Install-Piping & It's Components (CS-SPB) | 4242 | 4242 | Pipe
4242.T2.PI.CS-SPB.1826 | 4242-SP1-800 Install-Piping & It's Components (CS-SPB) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LPA.1667 | 4242-SP1-100 Install-Piping & It's Components (FRP-LPA) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LPA.1687 | 4242-SP1-200 Install-Piping & It's Components (FRP-LPA) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LPA.1712 | 4242-SP1-300 Install-Piping & It's Components (FRP-LPA) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LPA.1732 | 4242-SP1-400 Install-Piping & It's Components (FRP-LPA) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LPA.1758 | 4242-SP1-500 Install-Piping & It's Components (FRP-LPA) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LPA.1786 | 4242-SP1-600 Install-Piping & It's Components (FRP-LPA) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LPA.1810 | 4242-SP1-700 Install-Piping & It's Components (FRP-LPA) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LPA.1828 | 4242-SP1-800 Install-Piping & It's Components (FRP-LPA) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LPA.1846 | 4242-SP1-900 Install-Piping & It's Components (FRP-LPA) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LSD.1713 | 4242-SP1-300 Install-Piping & It's Components (FRP-LSD) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LSD.1734 | 4242-SP1-400 Install-Piping & It's Components (FRP-LSD) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LSD.1788 | 4242-SP1-600 Install-Piping & It's Components (FRP-LSD) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LSD.1830 | 4242-SP1-800 Install-Piping & It's Components (FRP-LSD) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-LSD.1848 | 4242-SP1-900 Install-Piping & It's Components (FRP-LSD) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-WCW.1669 | 4242-SP1-100 Install-Piping & It's Components (FRP-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-WCW.1689 | 4242-SP1-200 Install-Piping & It's Components (FRP-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-WCW.1714 | 4242-SP1-300 Install-Piping & It's Components (FRP-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-WCW.1736 | 4242-SP1-400 Install-Piping & It's Components (FRP-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-WCW.1760 | 4242-SP1-500 Install-Piping & It's Components (FRP-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.FRP-WCW.1790 | 4242-SP1-600 Install-Piping & It's Components (FRP-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WCW.1671 | 4242-SP1-100 Install-Piping & It's Components (HDPE-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WCW.1691 | 4242-SP1-200 Install-Piping & It's Components (HDPE-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WCW.1715 | 4242-SP1-300 Install-Piping & It's Components (HDPE-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WCW.1738 | 4242-SP1-400 Install-Piping & It's Components (HDPE-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WCW.1762 | 4242-SP1-500 Install-Piping & It's Components (HDPE-WCW) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WPO.1673 | 4242-SP1-100 Install-Piping & It's Components (HDPE-WPO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WPO.1693 | 4242-SP1-200 Install-Piping & It's Components (HDPE-WPO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WPO.1716 | 4242-SP1-300 Install-Piping & It's Components (HDPE-WPO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WPO.1764 | 4242-SP1-500 Install-Piping & It's Components (HDPE-WPO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WPO.1792 | 4242-SP1-600 Install-Piping & It's Components (HDPE-WPO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WPO.1812 | 4242-SP1-700 Install-Piping & It's Components (HDPE-WPO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WPO.1832 | 4242-SP1-800 Install-Piping & It's Components (HDPE-WPO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WPO.1850 | 4242-SP1-900 Install-Piping & It's Components (HDPE-WPO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRA.1766 | 4242-SP1-500 Install-Piping & It's Components (HDPE-WRA) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRA.1794 | 4242-SP1-600 Install-Piping & It's Components (HDPE-WRA) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRA.1812 | 4242-SP1-700 Install-Piping & It's Components (HDPE-WRA) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRA.1834 | 4242-SP1-800 Install-Piping & It's Components (HDPE-WRA) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRA.1852 | 4242-SP1-900 Install-Piping & It's Components (HDPE-WRA) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRO.1675 | 4242-SP1-100 Install-Piping & It's Components (HDPE-WRO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRO.1695 | 4242-SP1-200 Install-Piping & It's Components (HDPE-WRO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRO.1717 | 4242-SP1-300 Install-Piping & It's Components (HDPE-WRO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRO.1740 | 4242-SP1-400 Install-Piping & It's Components (HDPE-WRO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRO.1768 | 4242-SP1-500 Install-Piping & It's Components (HDPE-WRO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRO.1796 | 4242-SP1-600 Install-Piping & It's Components (HDPE-WRO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRO.1814 | 4242-SP1-700 Install-Piping & It's Components (HDPE-WRO) | 4242 | 4242 | Pipe
4242.T2.PI.HDPE-WRO.1836 | 4242-SP1-800 Install-Piping & It's Components (HDPE-WRO) | 4242 | 4242 | Pipe
4242.T2.PI.INS.1792 | 4242-SP1-100 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1794 | 4242-SP1-200 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1796 | 4242-SP1-300 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1798 | 4242-SP1-400 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1800 | 4242-SP1-500 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1802 | 4242-SP1-600 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1804 | 4242-SP1-700 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1806 | 4242-SP1-800 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1808 | 4242-SP1-900 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1810 | 4242-TR-100 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1812 | 4242-TR-400 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1814 | 4242-TR-500 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.INS.1816 | 4242-TR-600 Install Insulation / Cladding | 4242 | 4242 | Pipe
4242.T2.PI.SS-LPB.1677 | 4242-SP1-100 Install-Piping & It's Components (SS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.SS-LPB.1697 | 4242-SP1-200 Install-Piping & It's Components (SS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.SS-LPB.1718 | 4242-SP1-300 Install-Piping & It's Components (SS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.SS-LPB.1742 | 4242-SP1-400 Install-Piping & It's Components (SS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.SS-LPB.1770 | 4242-SP1-500 Install-Piping & It's Components (SS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.SS-LPB.1798 | 4242-SP1-600 Install-Piping & It's Components (SS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.SS-LPB.1816 | 4242-SP1-700 Install-Piping & It's Components (SS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.SS-LPB.1838 | 4242-SP1-800 Install-Piping & It's Components (SS-LPB) | 4242 | 4242 | Pipe
4242.T2.PI.SS-WSC.1679 | 4242-SP1-100 Install-Piping & It's Components (SS-WSC) | 4242 | 4242 | Pipe
4242.T2.PI.SS-WSC.1699 | 4242-SP1-200 Install-Piping & It's Components (SS-WSC) | 4242 | 4242 | Pipe
4242.T2.PI.SS-WSC.1720 | 4242-SP1-300 Install-Piping & It's Components (SS-WSC) | 4242 | 4242 | Pipe
4242.T2.PI.SS-WSC.1744 | 4242-SP1-400 Install-Piping & It's Components (SS-WSC) | 4242 | 4242 | Pipe
4242.T2.PI.SS-WSC.1772 | 4242-SP1-500 Install-Piping & It's Components (SS-WSC) | 4242 | 4242 | Pipe
4242.T2.PI.SS-WSC.1800 | 4242-SP1-600 Install-Piping & It's Components (SS-WSC) | 4242 | 4242 | Pipe
4242.T2.PI.SS-WSC.1818 | 4242-SP1-700 Install-Piping & It's Components (SS-WSC) | 4242 | 4242 | Pipe
4242.T2.PI.SS-WSC.1840 | 4242-SP1-800 Install-Piping & It's Components (SS-WSC) | 4242 | 4242 | Pipe
4242.T2.PI.SS-WSC.1854 | 4242-SP1-900 Install-Piping & It's Components (SS-WSC) | 4242 | 4242 | Pipe
CN.2252-1.T2.CV.1000 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Centrate Tank Agitator (2252-AG-030) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1000 | 2252-1 - Crude LHM Evaporation & Crystallisation - 2252-SP-001_Crude LHM Crystallisation Sump Pump | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1010 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Scrubber Circulation Pumps 2252-PP-03A and 03B | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1030 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Concentrate pumps 2252-PP-013A and 013B | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1040 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Crystallisers Heat Exch (2252-HX-001) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1050 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Pumps (2252-PP-028 & 029) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1060 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Centrifuges (2252-CF-009 & 010) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1070 | 2252-1 - Crude LHM Evaporation & Crystallisation - Carbonate Precipitation Scrubber Pump (2252-PP-021 & 021B) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1090 | 2252-1 - Crude LHM Evaporation & Crystallisation- LIOH Crude LIOH Crystalliser Condensate Pump 2252-PP-02A | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1140 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Redissolve Tank Agitators (2252-AG-009 010 011 & 012) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1150 | 2252-1 - Crude LHM Evaporation & Crystallisation - Carbonate Precipitation Scrubber (2252-SR-002) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1170 | 2252-1 - Crude LHM Evaporation & Crystallisation - Cranes & Hoists (2252-CN-001 & 002 & 2252-Ht-001) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1180 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Centrifuges (2252-CF-001 002 003 & 004) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1190 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Dissolver Tank Agitator (2252-AG-027) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1210 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Centrifuges (2252-CF-005 006 007 & 008) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1230 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Crystallisers 1 To 4 (2252-CX-005,006,007 & 008) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1260 | 2252-1 - Crude LHM Evaporation & Crystallisation - Lithium Carbonate Precipitation Tank 1 Agitator (2252-AG-028) - T2 | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1280 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Redissolve Tank Pumps (2252-PP-005 006 007 & 008) - T2 | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1295 | 2252-1 - Crude LHM Evaporation & Crystallisation - Safety Showers | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1483 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crystalliser Agitators (2252-AG-005 006 007 & 008) | 2252 | 2252-1 | Mech
CN.2252-1.T2.MC.1582 | 2252-1 - Crude LHM Evaporation & Crystallisation - Crude LIOH Vent Scrubber (2252-SR-001) | 2252 | 2252-1 | Mech
CN.2252-1.T2.PI.1080 | 2252-1 Piping-Hydrotest SS-SPB | 2252 | 2252-1 | Pipe
CN.2252-1.T2.PI.1090 | 2252-1 Piping-S/T & Insulation | 2252 | 2252-1 | Pipe
CN.2252-1.T2.PI.1094 | 2252-2 Piping-S/T & Insulation | 2252 | 2252-2 | Pipe
CN.2252-1.T2.PL.11102 | 2252-1 - Install & Align (S/S) Crude LiOH Redissolve Tank 4 (2252-TK-012) | 2252 | 2252-1 | Mech
CN.2252-1.T2.PL.11106 | 2252-1 - Install & Align (S/S) Crude LiOH Centrate Tank 1 (2252-TK-013) | 2252 | 2252-1 | Mech
CN.2252-1.T2.PL.11110 | 2252-1 - Install & Align (S/S) Crude LIOH Centrifuge Distribution Feed Tank | 2252 | 2252-1 | Mech
CN.2252-1.T2.PL.11114 | 2252-1 - Install & Align(S/S) Lithium Carbonate Precipitation Tank 1 (2252-TK-028) | 2252 | 2252-1 | Mech
CN.2252-1.T2.PL.11118 | 2252-1 - Install & Align(Frp) Lithium Carbonate Centrate Tank (2252-TK-030) | 2252 | 2252-1 | Mech
CN.2252-1.T2.PL.11122 | 2252-1 - Install & Align (Frp) Lithium Carbonate Dissolver Tank (2252-TK-027) | 2252 | 2252-1 | Mech
CN.2252-1.T2.PL.11126 | 2252-1 - Install Crude LiOH Centrifuge Solids Chutes (2252-CH-011,012,013,014,015,016,017,018 & 019) | 2252 | 2252-1 | Mech
CN.2252-1.T2.PL.1188 | 2252-1 - Align (S/S) Crude LiOH Redissolve Tank 1 (2252-TK-009) | 2252 | 2252-1 | Mech
CN.2252-1.T2.PL.1192 | 2252-1 - Align (S/S) Crude LiOH Redissolve Tank 2 (2252-TK-010) | 2252 | 2252-1 | Mech
CN.2252-1.T2.PL.1196 | 2252-1 - Align (S/S) Crude LiOH Redissolve Tank 3 (2252-TK-011) | 2252 | 2252-1 | Mech
CN.2252-1.T2.ST.1338 | 2252-1 - Install lower columns tie in beams and bracing to grid lines A and B | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1342 | 2252-1 - Install full level 1 floor module MM 120 between grid lines A and B | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1346 | 2252-1 - Install lower columns tie in beams and bracing to grid line C | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1350 | 2252-1 - Install full level 1 floor module MM 121 between grid lines B and C | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1354 | 2252-1 - Install lower columns tie in beams and bracing to grid line D | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1358 | 2252-1 - Install full level 1 floor module MM 122 between grid lines C and D | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1362 | 2252-1 - Install lower columns tie in beams and bracing to grid line E | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1366 | 2252-1 - Install full level 1floor module MM 123 between grid lines D and E | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1370 | 2252-1 - Install lower level diagonal bracing between grid lines D and E | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1374 | 2252-1 - Install full level 2 floor module MM 130 between grid lines A and B | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1378 | 2252-1 - Install full level 2 floor module MM 131 between grid lines B and C | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1382 | 2252-1 - Install full level 2 floor module MM 132 between grid lines C and D | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1386 | 2252-1 - Install full level 2 floor module MM 133 between grid lines D and E | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1390 | 2252-1 - Install fully assembled western stair tower to level 2 MM100 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1394 | 2252-1 - Install southern pipe rack Grid A - E and level 1-2 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1398 | 2252-1 - Install upper columns tie in beams and bracing to grid lines A and B | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1399 | 2252-1 - Install full level 3 floor module MM 170 between grid lines A and B | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1402 | 2252-1 - Install upper columns tie in beams and bracing to grid line C | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1406 | 2252-1 - Install full level 3 floor module MM 171 between grid lines B and C | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1410 | 2252-1 - Install upper columns tie in beams and bracing to grid line D | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1414 | 2252-1 - Install full level 3 floor module MM 172 between grid lines C and D | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1418 | 2252-1 - Install upper columns tie in beams and bracing to grid lines E | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1422 | 2252-1 - Install full level 3 floor module MM 173 between grid lines D and E | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1430 | 2252-1 - Install full level 4 floor module MM 180 between grid lines A and B | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1434 | 2252-1 - Install full level 4 floor module MM 181 between grid lines B and C | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1438 | 2252-1 - Install full level 4 floor module MM 182 between grid lines C and D | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1442 | 2252-1 - Install full level 4 floor module MM 183 between grid lines D and E | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1446 | 2252-1 - Install fully assembled western stair tower to level 4 MM 100-7 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1454 | 2252-1 - Install pipe supports and miscellaneous steel grid A - B under level 1 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1458 | 2252-1 - Install pipe supports and miscellaneous steel grid B - C under level 1 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1462 | 2252-1 - Install pipe supports and miscellaneous steel grid C - D under level 1 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1466 | 2252-1 - Install pipe supports and miscellaneous steel grid D - E under level 1 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1470 | 2252-1 - Install pipe supports and miscellaneous steel grid A - B under level 2 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1474 | 2252-1 - Install pipe supports and miscellaneous steel grid B - C under level 2 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1478 | 2252-1 - Install pipe supports and miscellaneous steel grid C - D under level 2 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1482 | 2252-1 - Install pipe supports and miscellaneous steel grid D - E under level 2 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1486 | 2252-1 - Install pipe supports and miscellaneous steel grid A - B under level 3 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1490 | 2252-1 - Install pipe supports and miscellaneous steel grid B - C under level 3 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1494 | 2252-1 - Install pipe supports and miscellaneous steel grid C - D under level 3 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1498 | 2252-1 - Install pipe supports and miscellaneous steel grid D - E under level 3 | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1502 | 2252-1 - Install miscellaneous platforms and pipe supports to all four floors | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1506 | 2252-1 - Tension, testing and quality completions | 2252 | 2252-1 | Struct
CN.2252-1.T2.ST.1510 | 2252-1 - Grouting | 2252 | 2252-1 | Struct
CN.2252-2.T2.MC.1000 | 2252-2 - Pure LHM Filtration - Polishing Filters 1, 2 & 3 (2252-FL-001 002 & 003) Inc. Crane | 2252 | 2252-2 | Mech
CN.2252-2.T2.MC.1020 | 2252-2 - Pure LHM Filtration - Redissolved LIOH Cake Reslurry Pumps 1, 2 & 3 (2252-PP-009, 011 & 030) | 2252 | 2252-2 | Mech
CN.2252-2.T2.MC.1030 | 2252-2 - Pure LHM Filtration - Redissolved LIOH Cake Reslurry Tank Agitators (2252-AG-015 017 & 031) | 2252 | 2252-2 | Mech
CN.2252-2.T2.MC.1040 | 2252-2 - Pure LHM Filtration - Redissolved LIOH Primary & Secondary Polishing Filtrate Pumps (2252-PP-010 & 012) - T2 | 2252 | 2252-2 | Mech
CN.2252-2.T2.MC.1050 | 2252-2 - Pure LHM Filtration - Redissolved LIOH Cloth & Core Wash Pumps (2252-PP-024 & 026) | 2252 | 2252-2 | Mech
CN.2252-2.T2.MC.1051 | 2252-2 - Pure LHM Filtration - Redissolve Bulk Bag | 2252 | 2252-2 | Mech
CN.2252-2.T2.MC.1052 | 2252-2 - Pure LHM Filtration - Redissolve Seal Pot | 2252 | 2252-2 | Mech
CN.2252-2.T2.MC.1053 | 2252-2 - Pure LHM Filtration - Filtration Sump Pump | 2252 | 2252-2 | Mech
CN.2252-2.T2.MC.1054 | 2252-2 - Crude LHM Crystallisation Safety Showers | 2252 | 2252-2 | Mech
CN.2252-2.T2.PI.1092 | 2252-2 Piping-Hydrotest | 2252 | 2252-2 | Pipe
CN.2252-2.T2.ST.1230 | 2252-2 - Install (all) 20 columns C 1008 - C 1027 and level | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1240 | 2252-2 - Install module MM412 RL 19.350 Northern gridline on between grid 1 and 2 | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1250 | 2252-2 - Install module MM411 RL 19.350 between grid 2 and 3 and A and C | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1260 | 2252-2 - Install stick steel horizontal tie in beams on southern grid lines RL 19.098 | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1270 | 2252-2 - Install level I North/East corners tie beams and bracing | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1280 | 2252-2 - Install level 1 walkway modules MM 413, 414 and 415 | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1290 | 2252-2 - Install module MM417 RL 19.350 between grid 2 and 3 and C and E | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1300 | 2252-2 - Install tank access underslung modules MM 400,401 and 402 | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1310 | 2252-2 - Install level 1 module MM 410 south west corner | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1324 | 2252-2 - Install module MM 437 level 2 North East corner floor module | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1328 | 2252-2 - Install module MM 421 level 2 North West corner floor module | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1332 | 2252-2 - Install fully assembled stair tower module MM 481 North West Corner | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1336 | 2252-2 - Install module MM 420 level 2 South West corner floor module | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1340 | 2252-2 - Install module MM 436 level 2 South East corner floor module | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1344 | 2252-2 - Install walkway modules 431, 432, 433 and 434 to level 2 North side of building | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1348 | 2252-2 - Install walkway modules 427, 428, 429 and 430 to level 2 North side of building | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1352 | 2252-2 - Install fully assembled stair tower module MM 480 South East Corner | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1356 | 2252-2 - Install staircase tie in modules to main building | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1360 | 2252-2 - Install filter support modules MM 422, 423, 424 and 425 to top of structure | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1364 | 2252-2 - Install miscellaneous steel work and platforms to top level structure surrounding filters | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1368 | 2252-2 - Finish all diagonal and horizontal pipe bracing to building | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1372 | 2252-2 - Install pipe supports and miscellaneous brackets to steel work under level 1 | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1376 | 2252-2 - Install pipe supports and miscellaneous brackets to steel work under level 2 | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1380 | 2252-2 - Install guard supports and guarding to crane rails bothe side full length of building | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1384 | 2252-2 - Install pipe supports and stair modules around filter walkways | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1388 | 2252-2 - Tension, testing and quality completions | 2252 | 2252-2 | Struct
CN.2252-2.T2.ST.1392 | 2252-2 - Grouting | 2252 | 2252-2 | Struct
CN.2252-3 T2.Insul.1223 | 2252-3 - Insulation Works to 2252-PV-001 | 2252 | 2252-3 | Pipe
CN.2252-3 T2.Insul.1294 | 2252-3 - Insulation Works to 2252-HX-006 | 2252 | 2252-3 | Pipe
CN.2252-3.T2.Insul.1296 | 2252-3 - Insulation Works to 2252-PV-002 | 2252 | 2252-3 | Pipe
CN.2252-3.T2.Insul.1298 | 2252-3 - Insulation Works to 2252-HX-004 | 2252 | 2252-3 | Pipe
CN.2252-3.T2.Insul.1300 | 2252-3 - Insulation Works to 2252-HX-010 | 2252 | 2252-3 | Pipe
CN.2252-3.T2.Insul.1302 | 2252-3 - Insulation Works to 2252-PV-003 | 2252 | 2252-3 | Pipe
CN.2252-3.T2.Insul.1304 | 2252-3 - Insulation Works to 2252 Ducting Connections | 2252 | 2252-3 | Pipe
CN.2252-3.T2.MC.1001 | 2252-3 - Install CrudeLHM Cystaliser MVR compressor 2525-CP-001 and vacuum tank | 2252 | 2252-3 | Mech
CN.2252-3.T2.MC.1200 | 2252-3 - Install CrudeLHM Crystalliser Compression water discharge tank 2252-TK-037 | 2252 | 2252-3 | Mech
CN.2252-3.T2.MC.1220 | 2252-3 - Install CrudeLHM Crystalliser Compressor drain pump 2252-PP-034 | 2252 | 2252-3 | Mech
CN.2252-3.T2.MC.1272 | 2252-3 - Install CrudeLHM Crystalliser gland seal water pumps 2252-PP- 023A and 023B | 2252 | 2252-3 | Mech
CN.2252-3.T2.MC.1276 | 2252-3 - Install CrudeLHM Crystalliser gland seal water tank 2252-TK-005 | 2252 | 2252-3 | Mech
CN.2252-3.T2.MC.1283 | 2252-3 - Install CrudeLHM Crystalliser Concentrate pumps 2252-PP-032A and 032B | 2252 | 2252-3 | Mech
CN.2252-3.T2.MC.1285 | 2252-3 - Install CrudeLHM Crystalliser vacuum pumps 2252-PP-033A and 033B (Level 2) | 2252 | 2252-3 | Mech
CN.2252-3.T2.MC.1290 | 2252-3 - Install CrudeLHM Crystalliser vent condensor 2252-HX-004 9Level 4 - 5.5) | 2252 | 2252-3 | Mech
CN.2252-3.T2.MC.1291 | 2252-3 - Install CrudeLHM Crystalliser pre heater 5 2252-HX-004 | 2252 | 2252-3 | Mech
CN.2252-3.T2.ST.1180 | 2252-3 - Assemble and install stairs to level 3 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1190 | 2252-3 - Install level 3 RL 31.400 floor module 120 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1200 | 2252-3 - Assemble and install level2 RL 25.400 north west module | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1210 | 2252-3 - Erect 8 off second tier columns | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1220 | 2252-3 - Assemble and install stairs to level 2 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1230 | 2252-3 - Install level 3.5 RL 31.400 module 122 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1250 | 2252-3 - Erect 8 off base columns (C 1001 - 1008) | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1260 | 2252-3 - Install level 1 RL 19.400 floor modules 100 and 101 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1270 | 2252-3 - Install level 2 RL 25.400 floor modules 110 and 111 and 113 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1280 | 2252-3 - Assemble and install remaining floor steel RL 31.400 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1290 | 2252-3 - Install stick steel pipe bracing | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1300 | 2252-3 - Install level 4 RL 36.000 floor module 130 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1310 | 2252-3 - Assemble and install level 1 RL 19.400 north west module | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1320 | 2252-3 - Assemble and install stairs to level 1 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1324 | 2252-3 - Assemble and install remaining floor steel RL 36.000 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1332 | 2252-3 - Install level 4 RL 40.200 floor modules 140 and 141 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1336 | 2252-3 - Assemble and install remaining tie in stick steel RL 40.200 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1344 | 2252-3 - Install level 5.5 module150 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1348 | 2252-3 - Erect 6 off third teir columns | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1352 | 2252-3 - Install level 6 module 160 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1360 | 2252-3 - Install southern piperack section between levels 1 and 2 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1364 | 2252-3 - Install remaining pipe bracing | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1368 | 2252-3 - Install 2252-1 and 2252-3 tie in modules 102, 112, 121 and 131 | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1372 | 2252-3 - Tension and testing | 2252 | 2252-3 | Struct
CN.2252-3.T2.ST.1376 | 2252-3 - Grouting | 2252 | 2252-3 | Struct
CN.2252-4.T2.PI.1094 | 2252-4 Piping-Hydrotest | 2252 | 2252-4 | Pipe
CN.2252-4.T2.PI.1096 | 2252-4 Piping-S/T & Insulation | 2252 | 2252-4 | Pipe
CN.2252-4.T2.ST.1198 | 2252-4 - Pipe Support Pre-assembly | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1202 | 2252-4 - Install Stair Tower Module 300 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1206 | 2252-4 - Panelise & Install Structures on Grid line D1 - E on grids 6-9 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1210 | 2252-4 - Stick Build Structures on Grid Line E - E1 on grids 7-9 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1214 | 2252-4 - Install Platform Module No: 311 over TK024 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1218 | 2252-4 - Install Walkway Module 310 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1222 | 2252-4 - Install Walkway Module 312 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1226 | 2252-4 - Install Walkway Module 313 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1230 | 2252-4 - Install Platform Module No: 344 over TK004 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1234 | 2252-4 - Install Two Sets of Interconnecting Stairs | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1238 | 2252-4 - Install Platform Module No: 342 over TK003 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1242 | 2252-4 - Install Platform Module No: 340 over TK002 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1246 | 2252-4 - Install Platform Modules 341 & 343 plus Interconnecting Steelwork | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1250 | 2252-4 - Install Valve Access Underslung Modules 320 & 321 | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1254 | 2252-4 - Install Remaining Pipe Supports | 2252 | 2252-4 | Struct
CN.2252-4.T2.ST.1258 | 2252-4 - Tension, Testing, Survey & FIC Completions | 2252 | 2252-4 | Struct
CN.2252-5.T2.MC.1286 | 2252-5 - Crude LHM Evaporation & Crystallisation - Pure LIOH Crystalliser Feed Pumps (2252-PP-031A, 031B) | 2252 | 2252-5 | Mech
CN.2252-5.T2.MC.1288 | 2252-5 - Crude LHM Evaporation & Crystallisation - Crude LHM Crystalliser Recirculation Pump (2252-PP-027) | 2252 | 2252-5 | Mech
CN.2252-5.T2.MC.1291 | 2252-5 - Crude LHM Evaporation & Crystallisation - Crude LIOH Crystalliser Cooling Condensate Surge Pump 2252-PP-025) | 2252 | 2252-5 | Mech
CN.2252-5.T2.MC.1374 | 2252-5 - Pre-assembly of all Pipe Supports | 2252 | 2252-5 | Struct
CN.2252-5.T2.MC.1378 | 2252-5 - Install Pre-assembled Tank Top Modules 362, 363 & 364 | 2252 | 2252-5 | Struct
CN.2252-5.T2.MC.1381 | 2252-5 - Crude LHM Evaporation & Crystallisation - Safety Showers | 2252 | 2252-5 | Mech
CN.2252-5.T2.MC.1382 | 2252-5 - Assemble & Install Underslung Valve Access Modules 360 & 361 | 2252 | 2252-5 | Struct
CN.2252-5.T2.MC.1386 | 2252-5 - Tension Testing & FIC Completion | 2252 | 2252-5 | Struct
CN.2252-5.T2.PI.1098 | 2252-5 Piping-Hydrotest | 2252 | 2252-5 | Pipe
CN.2252-5.T2.PI.1100 | 2252-5 Piping-S/T & Insulation | 2252 | 2252-5 | Pipe
CN.2252-6.T2.ST.1380 | 2252-6 - Crude LHM Ground Supports - Install Ground Supports | 2252 | 2252-6 | Struct
CN.2252-6.T2.ST.1390 | 2252-6 - Structural Steel Punch List and Construction Verification | 2252 | 2252-6 | Struct
CN.2252-7.T2.ST.1400 | 2252-7 - Crude LHM Ground Supports - Install Ground Supports | 2252 | 2252-7 | Struct
CN.2252-7.T2.ST.1410 | 2252-7 - Structural Steel Punch List and Construction Verification | 2252 | 2252-7 | Struct
CN.2252-7.T2.ST.1412 | 2252-7 - Grouting | 2252 | 2252-7 | Struct
CN.2262-4.T2.ST.1551 | 2262-4 - Install Miscellaneous Supports | 2262 | 2262-4 | Struct
CN.2262-4.T2.ST.1554 | 2262-4 - Structural Steel Punch List and Construction Verification | 2262 | 2262-4 | Struct
CN.2262.T2.MC.1010 | 2262-2 - Install Pure LHM Crystalliser Condensate Pump 2262-PP-002 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1020 | 2262-2 - Install Pure LHM Centrate Transfer Pump 2262-PP-006 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1030 | 2262-2 - Install Pure LHM Crystalliser Seal Water Pumps 2622- PP- 008A and 008B | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1040 | 2262-2 - Install Pure LHM Crystalliser Recirculation Pump2622-PP-012 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1060 | 2262-1 Install Pure LHM Cyrstalliser Heat Exchanger 2262-HX-001 | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1070 | 2262-2 - Install Pure LHM Crystalliser Blowdown Pump 2262-PP-009 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1080 | 2262-1 Install LIOH Crystalliser Cooling Condensate pump 2262-PP-011 | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1090 | 2262-2 - Install Pure LHM Crystalliser Condesate Pumps 2262-PP-014A and 014B | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1100 | 2262-2 - Install Pure LHM Crystalliser Compressor Drain Pump 2262-PP-016 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1120 | 2262-1 Install Pure LHM Cyrstalliser sump pump 2262-SP-001 | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1160 | 2262-1 Install pure LIOH Concentrate pumps 2262-PP-004 and 005 | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1172 | 2262-1 5 of Pure LIOH Centrifuges c/w hydraulic power packs 2262-HU-001 - 005 | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1173 | 2262-2 - Install Pure LHM Crystalliser MVR Compressor 2262-CP-001 with access and maitenanace platform | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1174 | 2262-2 - Install Pure LHM Crystalliser Sump Pump 2262-SP-002 with support platform and grating | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1175 | 2262-2 - Install Pure LHM Crystalliser Compressor Water Discharge Tank 2262-TK-015 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1176 | 2262-2 - Install Pure LHM Crystalliser Gland Seal Water Tank 2262-TK-004 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1177 | 2262-2 - Install Pure LHM Crystalliser Condenstae tank 2262-PV-002 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1178 | 2262-2 - Install Pure LHM Crystalliser Vacuum Pumps 2262- PP-015A and 015B | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1179 | 2262-2 - Install Pure LHM Crystalliser Vacuum Pump Seal Water Tank 2262-TK-001 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1180 | 2262-2 - Install LHM Crystalliser Feed Pre-heaters 2262-HX-002A and 002B | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1181 | 2262-2 - Install LHM Crystalliser Feed Pre-heaters 2262-HX-003A and 003B | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1182 | 2262-2 - Install Pure LHM Crystalliser Concentrate Pumps 2262- PP-001A and 001B | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1183 | 2262-2 - Install LHM Pure Cyrstalliser Feed Pre-heater 5 2260-HX-009 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1187 | 2262-1 5 of Pure LIOH Centrifuges c/w hydraulic power packs 2262-HU-006 - 010 | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1191 | 2262-1 Install 4 off Pure LIOH Crystallisers 2262-CX-004 - 007 c/w Agitaters | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1195 | 2262-1 Assemble and install Pure LIOH Centrifuge and Cyrstalliser Gantry crane (2262-CN - 001) | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1199 | 2262-1 Install Pure LIOH Venturi Scrubber 2262-SR-001 | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1203 | 2262-1 Assemble and install 18 safety showers | 2262 | 2262-1 | Mech
CN.2262.T2.MC.1211 | 2262-2 - Install Pure LHM Cyrstalliser Noncodensables vent condenser 2262-HX-004 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1215 | 2262-2 - Final alignments to Pure LIOH Crystalliser Condensate tank 2262-TK-003 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1219 | 2262-2 - Final alignments to Pure LIOH Centrate Transfer tank 2262-TK-010 | 2262 | 2262-2 | Mech
CN.2262.T2.MC.1221 | 2262-2 - Insulation Works to 2262-PV-001 | 2262 | 2262-2 | Pipe
CN.2262.T2.MC.1225 | 2262-2 - Insulation Works to 2262-TK-015 | 2262 | 2262-2 | Pipe
CN.2262.T2.MC.1227 | 2262-2 - Insulation Works to 2262 Ducting Connections | 2262 | 2262-2 | Pipe
CN.2262.T2.ST.1304 | 2261-1 Install South Side Centrifuge access platforms (13 modules) | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1314 | 2261-1 Install North Side Centrifuge access platforms (13 modules) | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1324 | 2262-1 Install upper columns, tie in beams and bracing to grid A | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1334 | 2262-1 Install upper columns, tie in beams and bracing to grid B | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1344 | 2262-1 Install upper columns, tie in beams and bracing to grid C | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1354 | 2262-1 Install upper columns, tie in beams and bracing to grid D | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1364 | 2262-1 Install upper columns, tie in beams and bracing to grid E | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1374 | 2262-1 Install upper columns, tie in beams and bracing to grid F | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1384 | 2262-1 Install east/west tie in beams and bracing accross all grid lines | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1394 | 2262-1 Install level 3 module 130 between grid lines 2 and 3 | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1404 | 2262-1 Install level 3 modules 131 - 138 | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1424 | 2262-2 - Complete grating installation to level 1 (RL19.780) | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1434 | 2262-2 - Complete grating installation to level 2 (RL25.380) | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1444 | 2262-2 - Complete grating installation to level 3 (RL 30.780) | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1454 | 2262-2 - Install second teir level column panels with bracing | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1464 | 2262-2 - Install Level 4 modules and stick steel | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1474 | 2262-2 - Install stairways and caged ladders to level 4 | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1494 | 2262-2 - Complete level 4 grating | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1504 | 2262-2 - Install level 5 modules and stick steel | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1514 | 2262-2 - Install stairways and caged ladders to level 5 | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1524 | 2262-2 - Complete level 5 grating | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1534 | 2262-2 - Install level 6 modules and stick steel | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1544 | 2262-2 - Install stairways and caged ladders to level 6 | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1554 | 2262-2 - Complete level 6 grating | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1564 | 2262-2 - Install level 7 modules and stick steel | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1574 | 2262-1 Install level 3 remining tie in beams and bracing | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1594 | 2262-1 Install level 4 module 140 between grid lines 2 and 3 | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1598 | 2262-1 Install level 4 remaining tie in beams and bracing | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1602 | 2262-1 Install level 4 emaining modules 142 a and b and 143 a,b and c | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1610 | 2262-1 Installation of pipe supports | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1614 | 2262-1 Tension, testing and quality | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1615 | 2262-2 - Install stairways and caged ladders to level 7 | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1618 | 2262-1 Install, survey and align crane rails | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1622 | 2262-1 Grouting | 2262 | 2262-1 | Struct
CN.2262.T2.ST.1625 | 2262-2 - Complete level 7 grating | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1634 | 2262-2 - Complete horizontal and vertical bracing installation | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1638 | 2262-2 - Survey, tension, testing and inspections | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1642 | 2262-2 - Install interconnecting pipe racks between 2262 MVR and crystallisation building | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1643 | 2262-2 - Install 2262- 2 site wide pipe supports | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1644 | 2262-2 - Install 2262- 2 Grouting | 2262 | 2262-2 | Struct
CN.2262.T2.ST.1678 | 2262-1 Miscellaneous Structural Steel | 2262 | 2262-1 | Struct
CN.2272.T2.MC.1000 | 2272-2 Place Dried Reject Hoppers and Support Frames 2272-HP-024 and 025 | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1010 | 2272-2 Place Dryers to level 1 2272-DR-001-004 (RL17.500) | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1020 | 2272-2 Place vacuum tank and pump sets to level 1 (RL17.500) 2272-PP-019 and 020 | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1030 | 2272-2 Mechanical completions to screens including transfer and rejects hoppers 2272-SC-001 and 002 | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1040 | 2272-2 Place Screw Feeders x 2 2272-FE-007 and 008 | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1050 | 2272-2 Place and align wet cake transfer screw conveyors 2272-CV-009 and 010 | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1070 | 2272-2 Mechanical completions to LIOH Cooler screw feeders and hoppers | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1080 | 2272-2 Place Dried LIOH screens 2272-SC-001 and 002 onto concrete pedestals | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1090 | 2272-2 Install LIOH Cooler hoppers into support frames 2272-HP-003 and 004 | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1100 | 2272-2 Mechanical completions Dryers 2272-DR-001-004 | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1120 | 2272-2 Place Dried LIOH Transfer Hoppers 2272-HP-010 and 011 onto concrete pedestals | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1160 | 2272-1 Mechanical completions between Dust Collector and Dust Collector Hoppers | 2272 | 2272-1 | Mech
CN.2272.T2.MC.1180 | 2272-1 Mechanical completions between Magnetic Screens and Screen Feed Hoppers | 2272 | 2272-1 | Mech
CN.2272.T2.MC.1191 | 2272-1 Mechanical Completions between Vacuum Transfer Receivers and Magnetic Screen Hoppers | 2272 | 2272-1 | Mech
CN.2272.T2.MC.1210 | 2272-2 Place Cooled LIOH Transfer intermediate hoppers onto support frames 2272-HP-012 and 013 | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1211 | 2272-1 Mechanical Completions between Demagnetised large bag Receivers and Packaging Feed Hoppers | 2272 | 2272-1 | Mech
CN.2272.T2.MC.1220 | 2272-1 Mechanical completions between Magnetic screens and Intermediate Hoppers | 2272 | 2272-1 | Mech
CN.2272.T2.MC.1221 | 2272-2 Mechanical completions between dryers 3 and 4 and the Cooled LIOH Intermediate Hoppers | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1222 | 2272-2 Mechanical installation of LIOH Cooler Vent Scrubbers 2272-SR-001 and 002 | 2272 | 2272-2 | Mech
CN.2272.T2.MC.1224 | 2272-1 Atmospheric Controlled Packaging Room | 2272 | 2272-1 | Mech
CN.2272.T2.ST.1320 | 2272-2 Place Cooled LIOH Transfer intermediate hoppers support frames x 2 to ground floor | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1330 | 2272-2 Assemble and Place Screen Access Platforms, Modules 101 and 102 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1340 | 2272-2 Place 4 x LIOH Dryer support structures, Modules 103,104,105 and 106. | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1350 | 2272-2 Install level 1 support columns x 15 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1360 | 2272-2 Install Grating and Handrails to level 1 Module MM110 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1364 | 2272-2 Install level a floor module (RL 17.500) onto column supports | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1368 | 2272-2 Assemble and install lower level staircase x 2 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1376 | 2272-2 Install level 2 support columns x 15 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1380 | 2272-2 Install Grating and Handrails to level 2 module MM 120, 121 and 122 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1381 | 2272-3 Install portal cover structural steelwork and bracing | 2272 | 2272-3 | Struct
CN.2272.T2.ST.1384 | 2272-2 Install modules MM 120, 121 and 122 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1388 | 2272-2 Assemble and install second level stair cases to RL20.100 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1392 | 2272-2 Install All Vertical Bracing from ground floor to level 2 at RL20.100 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1396 | 2272-2 Install LIOH Cooler hopper support frames Modules MM 123 and 124 | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1400 | 2272-2 Complete installation of all pipe supports Including Chemical Anchors | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1401 | 2272-3 Install portal cover wall girts and roof purlins | 2272 | 2272-3 | Struct
CN.2272.T2.ST.1404 | 2272-2 Tension, testing and quality checks | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1408 | 2272-2 Grouting | 2272 | 2272-2 | Struct
CN.2272.T2.ST.1430 | 2272-1 Install five (5) grid line panels for grids A1 - B1 and tie in together with sufficient tie in beams | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1461 | 2272-1 Install stick steel to level 1 platform at RL 18.180 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1465 | 2272-1 Install pipe supports to steelwork underside of level 1 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1469 | 2272-1 Install handrail and grating to level 1 platform at RL 18.180 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1485 | 2272-1 Install stick steel to level 2 platform at RL 20.780 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1489 | 2272-1 Install pipe supports to steelwork underside of level 2 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1493 | 2272-1 Install handrail and grating to level 2 platform at RL 20.780 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1497 | 2272-1 Assemble and install stair modules from ground to level 2 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1501 | 2272-1 Install stick steel to level 3 platform at RL 23.380 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1505 | 2272-1 Install handrail and grating to level 3 platform at RL 23.380 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1509 | 2272-1 Install pipe supports to level 3 steelwork | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1513 | 2272-1 Install stair module level 2 - level 3 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1533 | 2272-1 Install level (RL 26.380) modules MM 110, 111 and 112 and associated tie in steelwork | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1537 | 2272-1 Install level (RL 26.380) grating and handrails | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1541 | 2272-1 Install stair module level 3 - level 4 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1545 | 2272-1 Install fully assembled floor module MM 114 to Northern grid at RL27.180 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1549 | 2272-1 Complete assemble and installation of modularised platforms MM 120 and 121 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1553 | 2272-1 Complete assemble and installation of remaining stairways | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1565 | 2272-1 Install Level five steel module complete with handrail and grating | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1573 | 2272-1 Tension, testing and quality | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1577 | 2272-1 Survey and grouting to steel structure only | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1581 | 2272-3 Install portal cover wall and roof sheeting | 2272 | 2272-3 | Struct
CN.2272.T2.ST.1593 | 2272-3 Grouting | 2272 | 2272-3 | Struct
CN.2272.T2.ST.1598 | 2272-5 - Miscellaneous Pipe Supports | 2272 | 2272-5 | Struct
CN.2272.T2.ST.1606 | 2272-4 - Remove northern wall sheeting and purlins | 2272 | 2272-4 | Struct
CN.2272.T2.ST.1618 | 2272-4 - Install Structure | 2272 | 2272-4 | Struct
CN.2272.T2.ST.1622 | 2272-4 - Install mezzanine floor and ladder | 2272 | 2272-4 | Struct
CN.2272.T2.ST.1626 | 2272-4 - Install large bag CER air conditioner 2272-XM-018 | 2272 | 2272-4 | Struct
CN.2272.T2.ST.1672 | 2272-1 Install stick steel to level 4 platform at RL 25.380 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1674 | 2272-1 Install stick steel to level 5 platform at RL 30.780 | 2272 | 2272-1 | Struct
CN.2272.T2.ST.1676 | 2272-3 Supports | 2272 | 2272-3 | Struct
CN.4242.T2.IN.1665 | 4242-SP1-500 Install Node | 4242 | 4242 | Struct
CN.4242.T2.PS.1637 | 4242-TR-100 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.PS.1641 | 4242-SP1-200 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.PS.1645 | 4242-SP1-300 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.PS.1649 | 4242-SP1-400 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.PS.1650 | 4242-TR-300 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.PS.1653 | 4242-SP1-500 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.PS.1657 | 4242-SP1-700 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.PS.1658 | 4242-TR-400 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.PS.1661 | 4242-SP1-800 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.PS.1663 | 4242-SP1-600 Install Pipe Supports | 4242 | 4242 | Struct
CN.4242.T2.ST.1629 | 4242-TR-400 Installation | 4242 | 4242 | Struct
CN.4242.T2.ST.1633 | 4242-TR-500 Installation | 4242 | 4242 | Struct
CN.4242.T2.WW.1645 | 4242-SP1-200 Install Walkway | 4242 | 4242 | Struct
CN.4242.T2.WW.1653 | 4242-SP1-300 Install Walkway | 4242 | 4242 | Struct
CN.4242.T2.WW.1661 | 4242-SP1-400 Install Walkway | 4242 | 4242 | Struct
CN.4242.T2.WW.1665 | 4242-SP1-500 Install Walkway | 4242 | 4242 | Struct
CN.4242.T2.WW.1669 | 4242-SP1-700 Install Walkway | 4242 | 4242 | Struct
CN.4242.T2.WW.1673 | 4242-SP1-800 Install Walkway | 4242 | 4242 | Struct